## MakeReadySummary
Pole_ID | SCID | Pole_tag | Make_Ready_State | Make_ready_notes | Latitude | Longitude | jobname
P:0248 | 1 | 58247N45960 | No MR | Low Power: Drip_loop at 21'-4". Gigapower LLC Guy at 17'-0": Attach | 41.4087 | -75.626 | APP_306525
P:0036 | 2 | 58239N45969 | MR Resolved | Low Power: Drip_loop at 25'-4". PPL Company Transformer at 27'-7": Raise 8" to 28'-3". Secondary at 25'-7": Raise 8" to 26'-3". PPL Company Drip Loop at 25'-4": Raise 8" to 26'-0". Gigapower LLC Fiber Optic Com at 23'-6": Attach. Bond to ground wire. Gigapower LLC Down Guy at 23'-6": Attach. Place on existing anchor rod with 14' lead at 213° and attach 6.6M (1/4" EHS) (7/0) guy. Gigapower LLC Guy at 23'-6": Attach. Comcast - Duryea Down Guy at 21'-6": Transfer Comcast - Duryea Down Guy from anchor at 14' lead at 213° to the new Gigapower LLC anchor at 8' lead. Verizon Pennsylvania Inc. Down Guy at 20'-2": Transfer Verizon Pennsylvania Inc. Down Guy from anchor at 14' lead at 213° to the new Gigapower LLC anchor at 8' lead | 41.4089 | -75.6265 | APP_306525
P:0038 | 3 | 58231N45977 | MR Resolved | Low Power: Street_light at 21'-0". Secondary at 26'-0": Raise 36" to 29'-0". Secondary at 25'-9": Raise 36" to 28'-9". PPL Company Riser at 24'-11": Extend 30" to 27'-5". PPL Company Riser at 24'-11": Extend 30" to 27'-5". PPL Company Down Guy at 24'-4": Raise 30" to 26'-10". Dunmore Boro, Lackawanna Co. Street Light at 23'-1": Raise 18" to 24'-7". Dunmore Boro, Lackawanna Co. Drip Loop at 22'-7": Raise 18" to 24'-1". Gigapower LLC Fiber Optic Com at 21'-9": Attach. Gigapower LLC Down Guy at 21'-9": Attach and install new anchor. Place on new Gigapower LLC anchor rod with 15' lead at 204° and attach 6.6M (1/4" EHS) (7/0) guy. North Penn Long Distance Corporation Down Guy at 20'-9": Attach and install new anchor. Place on new Gigapower LLC anchor rod with 15' lead at 204° and attach 6.6M (1/4" EHS) (7/0) guy | 41.4091 | -75.6268 | APP_306525
P:0040 | 4 | 58211N45994 | MR Resolved | Low Power: Street_light at 23'-8". Gigapower LLC Down Guy at 21'-0": Attach. Install on aux eye and place on existing anchor rod with 20' lead at 167° and attach 6.6M (1/4" EHS) (7/0) guy. North Penn Long Distance Corporation Fiber Optic Com at 21'-0": Lower 12" to 20'-0". Gigapower LLC Fiber Optic Com at 21'-0": Attach. Gigapower LLC Fiber Optic Com at 21'-0": Attach. Gigapower LLC Guy at 21'-0": Attach. Comcast - Duryea CATV Com at 20'-0": Lower 12" to 19'-0". Power Guy at 19'-5": Lower 47" to 15'-6". Verizon Pennsylvania Inc. Telco Com at 18'-8": Lower 10" to 17'-10". Verizon Pennsylvania Inc. Down Guy at 18'-8": Lower 10" to 17'-10". Verizon Pennsylvania Inc. Down Guy at 17'-10": Lower 10" to 17'-0". Verizon Pennsylvania Inc. Fiber Optic Com at 17'-4": Attach. Remove fiber from PPG in span bearing 125° (NE) and install at slack tension at 17'-4". Verizon Pennsylvania Inc. Guy at 11'-2": Raise 46" to 15'-0" | 41.4096 | -75.6275 | APP_306525
P:0039 | 5 | 58208N45999 | MR Resolved | Low Power: Secondary at 25'-0". Gigapower LLC Fiber Optic Com at 27'-0": Attach. Gigapower LLC Fiber Optic Com at 27'-0": Attach. Pole Top: Replace 60' class 2 pole with 40' class 3 pole. Secondary at 25'-8": Raise 88" to 33'-0". Secondary at 25'-0": Raise 90" to 32'-6". Verizon Pennsylvania Inc. Telco Com at 22'-0": Raise 48" to 26'-0", Transfer to new pole at 26'-0". North Penn Long Distance Corporation Fiber Optic Com at 21'-2": Raise 52" to 25'-6", Transfer to new pole at 25'-6". Comcast - Duryea CATV Com at 20'-2": Raise 46" to 24'-0", Transfer to new pole at 24'-0". Comcast - Duryea CATV Com at 20'-2": Raise 52" to 24'-6", Transfer to new pole at 24'-6". Verizon Pennsylvania Inc. Telco Com at 19'-0": Raise 48" to 23'-0", Transfer to new pole at 23'-0". Verizon Pennsylvania Inc. Telco Com at 18'-7": Raise 41" to 22'-0", Transfer to new pole at 22'-0". Verizon Pennsylvania Inc. Telco Com at 18'-4": Raise 38" to 21'-6", Transfer to new pole at 21'-6". Verizon Pennsylvania Inc. Telco Com at 17'-11": Raise 37" to 21'-0", Transfer to new pole at 21'-0" | 41.4097 | -75.6276 | APP_306525
P:0145 | 6 | 58204N46005 | MR Resolved | Gigapower LLC Fiber Optic Com at 23'-0": Attach. Attach on PPL vang. Gigapower LLC Fiber Optic Com at 23'-0": Attach. Attach on PPL vang. Gigapower LLC Down Guy at 23'-0": Attach and install new anchor. Place on new Gigapower LLC anchor rod with 15' lead at 121° and attach 6.6M (1/4" EHS) (7/0) guy. Attach on PPL vang | 41.4098 | -75.6277 | APP_306525
P:0053 | 7 | 58201N46003 | No MR | Gigapower LLC Fiber Optic Com at 19'-8": Attach | 41.4098 | -75.6279 | APP_306525
P:0056 | 8 | 58192N46009 | MR Resolved | Low Power: Drip_loop at 25'-8". Gigapower LLC Fiber Optic Com at 20'-8": Attach. Attach on PPL vang | 41.41 | -75.6283 | APP_306525
P:0055 | 9 | 58182N46014 | No MR | Low Power: Secondary at 26'-8". Gigapower LLC Fiber Optic Com at 20'-7": Attach | 41.4102 | -75.6286 | APP_306525
P:0058 | 10 | 58172N46021 | MR Resolved | Low Power: Drip_loop at 23'-0". Secondary at 25'-7": Raise 24" to 27'-7". Secondary at 25'-7": Raise 24" to 27'-7". Secondary at 25'-5": Raise 24" to 27'-5". Secondary at 25'-1": Raise 24" to 27'-1". Dunmore Boro, Lackawanna Co. Street Light at 24'-5": Ground Bracket. PPL Company Drip Loop at 23'-0": Raise 40" to 26'-4", Ground to pole. Attach on PPL vang. Gigapower LLC Fiber Optic Com at 20'-10": Attach. Ground to pole. Attach using pole banding. Gigapower LLC Fiber Optic Com at 20'-10": Attach. Ground to pole. Attach using pole banding. Gigapower LLC Guy at 20'-10": Attach. Ground to pole. Attach using pole banding. North Penn Long Distance Corporation Fiber Optic Com at 20'-10": Lower 12" to 19'-10". North Penn Long Distance Corporation Fiber Optic Com at 20'-10": Lower 12" to 19'-10". Comcast - Duryea CATV Com at 19'-10": Lower 12" to 18'-10", Attach via pole banding. Comcast - Duryea CATV Com at 19'-10": Lower 12" to 18'-10", Attach via pole banding. Comcast - Duryea Strand at 19'-10": Lower 12" to 18'-10", Attach via pole banding | 41.4104 | -75.6289 | APP_306525
P:0114 | 12 | 58179N46031 | MR Resolved | Low Power: Service at 27'-2". Service at 28'-2": Raise 24" to 30'-2". Secondary at 28'-1": Raise 24" to 30'-1". Secondary at 28'-1": Raise 24" to 30'-1". Secondary at 27'-10": Raise 24" to 29'-10". Service at 27'-3": Raise 24" to 29'-3". Service at 27'-2": Raise 24" to 29'-2". Gigapower LLC Fiber Optic Com at 22'-3": Attach | 41.4106 | -75.6287 | APP_306525
P:0117 | 13 | 58185N46040 | MR Resolved | Low Power: Drip_loop at 25'-10". Gigapower LLC Fiber Optic Com at 22'-4": Attach. Bond to ground wire | 41.4109 | -75.6284 | APP_306525
P:0074 | 14 | 58188N46046 | MR Resolved | Low Power: Street_light at 21'-0". Dunmore Boro, Lackawanna Co. Street Light at 23'-1": Raise 6" to 23'-7". Dunmore Boro, Lackawanna Co. Drip Loop at 22'-0": Raise 6" to 22'-6". Gigapower LLC Fiber Optic Com at 20'-10": Attach. Gigapower LLC Fiber Optic Com at 20'-10": Attach. Gigapower LLC Fiber Optic Com at 20'-10": Attach | 41.4111 | -75.6283 | APP_306525
P:0071 | 15 | 58196N46043 | MR Resolved | Low Power: Secondary at 23'-7". Secondary at 23'-7": Install ground rod and bond neutral to ground. Gigapower LLC Fiber Optic Com at 21'-1": Attach. Bond to ground wire. Verizon Pennsylvania Inc. Down Guy at 15'-6": Attach and install new anchor. Place on new Verizon Pennsylvania Inc. anchor rod with 15' lead at 301° and attach 10M (3/8" UG) (7/0) guy. Verizon Pennsylvania Inc. Guy at 15'-6": Attach | 41.411 | -75.628 | APP_306525
P:0043 | 16 | 58203N46039 | MR Resolved | Low Power: Street_light at 21'-11". Dunmore Boro, Lackawanna Co. Street Light at 24'-0": Raise 10" to 24'-10". Dunmore Boro, Lackawanna Co. Drip Loop at 23'-4": Raise 10" to 24'-2". Gigapower LLC Fiber Optic Com at 22'-4": Attach. Gigapower LLC Fiber Optic Com at 22'-4": Attach. Gigapower LLC Guy at 22'-4": Attach. Verizon Pennsylvania Inc. Guy at 18'-1": Attach | 41.4109 | -75.6278 | APP_306525
P:0046 | 17 | 58206N46040 | MR Resolved | Low Power: Secondary at 27'-11". Gigapower LLC Fiber Optic Com at 23'-2": Attach. Gigapower LLC Down Guy at 23'-2": Attach. Place on existing anchor rod with 12' lead at 85° and attach 6.6M (1/4" EHS) (7/0) guy. Gigapower LLC Guy at 23'-2": Attach. Gigapower LLC Guy at 23'-2": Attach | 41.4109 | -75.6277 | APP_306525
P:0044 | 18 | 58204N46030 | No MR | Low Power: Drip_loop at 24'-0". Gigapower LLC Fiber Optic Com at 20'-2": Attach | 41.4106 | -75.6277 | APP_306525
P:0041 | 19 | 58206N46019 | MR Resolved | Low Power: Street_light at 21'-0". Dunmore Boro, Lackawanna Co. Drip Loop at 21'-6": Insulate drip loop. Gigapower LLC Fiber Optic Com at 20'-8": Attach | 41.4103 | -75.6277 | APP_306525
P:0042 | 20 | 58207N46010 | MR Resolved | Low Power: Vertical_banner at 14'-6". Secondary at 24'-0": Raise 8" to 24'-8". PPL Company Drip Loop at 23'-8": Raise 8" to 24'-4". Dunmore Boro, Lackawanna Co. Drip Loop at 21'-5": Raise 8" to 22'-1", Insulate drip loop. Gigapower LLC Fiber Optic Com at 21'-5": Attach. Bond to ground wire | 41.41 | -75.6276 | APP_306525
P:0141 | 21 | 58160N46028 | MR Resolved | Low Power: Secondary at 28'-1". Gigapower LLC Fiber Optic Com at 22'-2": Attach. Attach on PPL vang | 41.4106 | -75.6293 | APP_306525
P:0142 | 22 | 58146N46037 | MR Resolved | Low Power: Street_light at 22'-3". Dunmore Boro, Lackawanna Co. Street Light at 22'-3": Ground Bracket. Gigapower LLC Fiber Optic Com at 20'-5": Attach | 41.4108 | -75.6298 | APP_306525
P:0139 | 23 | 58134N46044 | MR Resolved | Low Power: Secondary at 25'-10". Gigapower LLC Fiber Optic Com at 22'-6": Attach. Attach on PPL vang | 41.411 | -75.6303 | APP_306525
P:0107 | 24 | 58125N46049 | MR Resolved | Low Power: Street_light at 20'-1". PPL Company Riser at 22'-7": Extend 24" to 24'-7". Dunmore Boro, Lackawanna Co. Street Light at 22'-1": Raise 10" to 22'-11". Dunmore Boro, Lackawanna Co. Drip Loop at 21'-4": Raise 10" to 22'-2". Gigapower LLC Fiber Optic Com at 20'-5": Attach. Gigapower LLC Fiber Optic Com at 20'-5": Attach. Gigapower LLC Guy at 20'-5": Attach. North Penn Long Distance Corporation Guy at 19'-1": Attach. CTSI, LLC, Dba Frontier Communications Guy at 17'-0": Attach | 41.4112 | -75.6306 | APP_306525
P:0108 | 26 | 58131N46059 | MR Resolved | Low Power: Drip_loop at 20'-4". Pole Top: Replace 35' class 5 pole with 40' class 3 pole. Primary at 25'-9": Raise 87" to 33'-0". PPL Company Cutout Arrestor at 24'-3": Raise 90" to 31'-9". Secondary at 21'-2": Raise 82" to 28'-0". Gigapower LLC Fiber Optic Com at 21'-0": Attach. Neutral at 20'-11": Raise 81" to 27'-8". Service at 20'-10": Raise 78" to 27'-4". PPL Company Drip Loop at 20'-4": Raise 80" to 27'-0". North Penn Long Distance Corporation Fiber Optic Com at 18'-4": Raise 20" to 20'-0", Transfer to new pole at 20'-0". Comcast - Duryea CATV Com at 17'-4": Raise 20" to 19'-0", Transfer to new pole at 19'-0". CTSI, LLC, Dba Frontier Communications Fiber Optic Com at 16'-8": Raise 16" to 18'-0", Transfer to new pole at 18'-0". Power Guy at 15'-8": Lower 2" to 15'-6" | 41.4114 | -75.6304 | APP_306525
P:0105 | 27 | 58136N46068 | No MR | Low Power: Neutral at 27'-10". Gigapower LLC Fiber Optic Com at 22'-10": Attach | 41.4117 | -75.6301 | APP_306525
P:0077 | 28 | 58141N46075 | MR Resolved | Low Power: Drip_loop at 23'-6". Dunmore Boro, Lackawanna Co. Street Light at 23'-6": Ground Bracket. Gigapower LLC Fiber Optic Com at 21'-6": Attach. Gigapower LLC Fiber Optic Com at 21'-6": Attach | 41.4119 | -75.63 | APP_306525
P:0078 | 29 | 58149N46069 | No MR | Low Power: Secondary at 27'-10". Gigapower LLC Fiber Optic Com at 22'-8": Attach | 41.4117 | -75.6297 | APP_306525
P:0075 | 30 | 58158N46064 | MR Resolved | Low Power: Drip_loop at 22'-9". Gigapower LLC Fiber Optic Com at 19'-0": Attach. Bond to ground wire | 41.4116 | -75.6294 | APP_306525
P:0076 | 31 | 58170N46057 | MR Resolved | Low Power: Secondary at 26'-0". North Penn Long Distance Corporation Fiber Optic Com at 21'-7": Lower 12" to 20'-7". Gigapower LLC Fiber Optic Com at 21'-7": Attach. Comcast - Duryea CATV Com at 20'-7": Lower 12" to 19'-7" | 41.4114 | -75.6289 | APP_306525
P:0073 | 32 | 58178N46052 | No MR | Low Power: Secondary at 26'-1". Gigapower LLC Fiber Optic Com at 22'-7": Attach | 41.4112 | -75.6286 | APP_306525
P:0138 | 33 | 58114N46056 | MR Resolved | Low Power: Secondary at 27'-10". Gigapower LLC Fiber Optic Com at 19'-2": Attach. Attach on PPL vang | 41.4114 | -75.631 | APP_306525
P:0135 | 34 | 58105N46061 | MR Resolved | Low Power: Street_light at 19'-1". Dunmore Boro, Lackawanna Co. Street Light at 19'-1": Ground Bracket. Gigapower LLC Fiber Optic Com at 17'-6": Attach | 41.4115 | -75.6313 | APP_306525
P:0134 | 35 | 58093N46069 | MR Resolved | Low Power: Drip_loop at 20'-6". Dunmore Boro, Lackawanna Co. Street Light at 21'-7": Ground Bracket. Dunmore Boro, Lackawanna Co. Drip Loop at 20'-6": Raise 8" to 21'-2", Insulate drip loop. Gigapower LLC Fiber Optic Com at 20'-0": Attach. Attach on PPL vang | 41.4118 | -75.6318 | APP_306525
P:0057 | 36 | 58092N46065 | MR Resolved | Low Power: Riser at 22'-4". Secondary at 23'-11": Raise 10" to 24'-9". PPL Company Riser at 22'-4": Extend 16" to 23'-8". Gigapower LLC Fiber Optic Com at 20'-0": Attach. Gigapower LLC Down Guy at 20'-0": Attach. Place on existing anchor rod with 13' lead at 206° and attach 6.6M (1/4" EHS) (7/0) guy. Verizon Pennsylvania Inc. Down Guy at 17'-4": Upgrade existing down guy strand to a 10M (3/8" UG) (7/0) strand size | 41.4117 | -75.6318 | APP_306525
P:0166 | 37 | 58098N46077 | MR Resolved | Low Power: Secondary at 24'-10". Secondary at 24'-10": Raise 18" to 26'-4", Install ground rod and bond neutral to ground. Gigapower LLC Fiber Optic Com at 22'-1": Attach. Bond to ground wire | 41.412 | -75.6316 | APP_306525
P:0109 | 38 | 58102N46084 | MR Resolved | Low Power: Street_light at 21'-5". Dunmore Boro, Lackawanna Co. Street Light at 23'-4": Raise 6" to 23'-10", Ground Bracket. Dunmore Boro, Lackawanna Co. Drip Loop at 22'-8": Raise 6" to 23'-2". Gigapower LLC Fiber Optic Com at 21'-3": Attach. Bond to ground wire | 41.4121 | -75.6314 | APP_306525
P:0084 | 39 | 58108N46094 | MR Resolved | Low Power: Street_light at 22'-5". Secondary at 27'-3": Raise 24" to 29'-3". Secondary at 26'-8": Raise 24" to 28'-8". PPL Company Strand at 25'-7": Raise 24" to 27'-7". Dunmore Boro, Lackawanna Co. Street Light at 24'-6": Raise 15" to 25'-9", Ground Bracket. Dunmore Boro, Lackawanna Co. Drip Loop at 23'-7": Raise 15" to 24'-10". Gigapower LLC Fiber Optic Com at 23'-3": Attach. Gigapower LLC Fiber Optic Com at 23'-3": Attach. Gigapower LLC Fiber Optic Com at 23'-3": Attach | 41.4125 | -75.6311 | APP_306525
P:0081 | 40 | 58120N46087 | MR Resolved | Low Power: Secondary at 26'-2". Gigapower LLC Fiber Optic Com at 18'-9": Attach | 41.4122 | -75.6307 | APP_306525
P:0082 | 41 | 58125N46084 | No MR | Low Power: Secondary at 26'-11". Gigapower LLC Fiber Optic Com at 19'-8": Attach | 41.4122 | -75.6305 | APP_306525
P:0079 | 42 | 58130N46081 | No MR | Low Power: Drip_loop at 23'-10". Gigapower LLC Fiber Optic Com at 20'-4": Attach | 41.4121 | -75.6304 | APP_306525
P:0131 | 43 | 58084N46074 | No MR | Low Power: Service at 23'-3". Gigapower LLC Fiber Optic Com at 19'-3": Attach | 41.4119 | -75.6321 | APP_306525
P:0132 | 44 | 58075N46080 | MR Resolved | Low Power: Drip_loop at 22'-9". Dunmore Boro, Lackawanna Co. Street Light at 23'-4": Ground Bracket. Gigapower LLC Fiber Optic Com at 20'-8": Attach. Attach on PPL vang | 41.4121 | -75.6324 | APP_306525
P:0129 | 45 | 58063N46088 | MR Resolved | Low Power: Street_light at 21'-10". Dunmore Boro, Lackawanna Co. Street Light at 24'-11": Raise 12" to 25'-11". Dunmore Boro, Lackawanna Co. Drip Loop at 23'-2": Raise 12" to 24'-2". Gigapower LLC Fiber Optic Com at 22'-2": Attach. Gigapower LLC Fiber Optic Com at 22'-2": Attach. Gigapower LLC Guy at 22'-2": Attach | 41.4123 | -75.6328 | APP_306525
P:0060 | 46 | 58060N46085 | MR Resolved | Low Power: Neutral at 29'-1". Gigapower LLC Down Guy at 21'-8": Attach. Place on existing anchor rod with 6' lead at 232° and attach 6.6M (1/4" EHS) (7/0) guy. Gigapower LLC Guy at 21'-8": Attach. Comcast - Duryea Down Guy at 19'-6": Attach. Place on existing anchor rod with 6' lead at 232° and attach 6.6M (1/4" EHS) (7/0) guy | 41.4122 | -75.6329 | APP_306525
P:0112 | 47 | 58072N46102 | MR Resolved | Low Power: Drip_loop at 21'-8". Dunmore Boro, Lackawanna Co. Drip Loop at 21'-8": Raise 4" to 22'-0", Insulate drip loop. Gigapower LLC Fiber Optic Com at 21'-6": Attach | 41.4127 | -75.6325 | APP_306525
P:0111 | 48 | 58074N46106 | MR Resolved | Low Power: Service at 24'-7". Gigapower LLC Fiber Optic Com at 21'-2": Attach. Gigapower LLC Down Guy at 21'-2": Attach. Place on existing anchor rod with 15' lead at 35° and attach 6.6M (1/4" EHS) (7/0) guy. Gigapower LLC Fiber Optic Com at 20'-7": Attach | 41.4128 | -75.6324 | APP_306525
P:0088 | 49 | 58078N46113 | MR Resolved | Low Power: Drip_loop at 22'-9". Pole Top: Replace 40' class 3 pole with 45' class 3 pole. Primary at 32'-11": Raise 60" to 37'-11". Primary at 32'-6": Raise 60" to 37'-6". Secondary at 28'-3": Raise 57" to 33'-0". Secondary at 27'-11": Raise 57" to 32'-8". Secondary at 27'-9": Raise 55" to 32'-4". Dunmore Boro, Lackawanna Co. Street Light at 25'-3": Raise 18" to 26'-9", Transfer to new pole at 24'-6". Gigapower LLC Fiber Optic Com at 23'-0": Attach. Gigapower LLC Fiber Optic Com at 23'-0": Attach. Dunmore Boro, Lackawanna Co. Drip Loop at 22'-9": Raise 18" to 24'-3", Transfer to new pole at 24'-3". North Penn Long Distance Corporation Fiber Optic Com at 21'-4": Raise 8" to 22'-0", Transfer to new pole at 22'-0". North Penn Long Distance Corporation Fiber Optic Com at 21'-4": Raise 8" to 22'-0", Transfer to new pole at 22'-0". North Penn Long Distance Corporation Strand at 21'-4": Raise 8" to 22'-0", Transfer to new pole at 22'-0". Comcast - Duryea CATV Com at 20'-6": Raise 6" to 21'-0", Transfer to new pole at 21'-0". Comcast - Duryea CATV Com at 20'-6": Raise 6" to 21'-0", Transfer to new pole at 21'-0". Comcast - Duryea CATV Com at 20'-6": Raise 6" to 21'-0", Transfer to new pole at 21'-0". CTSI, LLC, Dba Frontier Communications Fiber Optic Com at 19'-9": Raise 3" to 20'-0", Transfer to new pole at 20'-0". Verizon Pennsylvania Inc. Telco Com at 18'-10": Raise 2" to 19'-0", Transfer to new pole at 19'-0" | 41.413 | -75.6322 | APP_306525
P:0085 | 50 | 58086N46108 | MR Resolved | Low Power: Drip_loop at 22'-9". Pole Top: Replace 40' class 3 pole with 45' class 3 pole. Primary at 32'-1": Raise 68" to 37'-9". Power Guy at 31'-3": Raise 68" to 36'-11". PPL Company Cutout Arrestor at 29'-7": Raise 68" to 35'-3". PPL Company Transformer at 26'-9": Raise 60" to 31'-9". Secondary at 24'-0": Raise 63" to 29'-3". PPL Company Drip Loop at 24'-0": Raise 67" to 29'-7". Secondary at 23'-9": Raise 62" to 28'-11". Service at 23'-4": Raise 62" to 28'-6". Service at 23'-3": Raise 63" to 28'-6". Service at 23'-1": Raise 65" to 28'-6". Gigapower LLC Fiber Optic Com at 23'-0": Attach. Transfer to new pole at 19'-0". PPL Company Drip Loop at 22'-9": Raise 63" to 28'-0". North Penn Long Distance Corporation Strand at 19'-10": Raise 26" to 22'-0", Transfer to new pole at 19'-0". Comcast - Duryea CATV Com at 19'-4": Raise 20" to 21'-0", Transfer to new pole at 19'-0". CTSI, LLC, Dba Frontier Communications Fiber Optic Com at 18'-6": Raise 18" to 20'-0", Transfer to new pole at 19'-0". Verizon Pennsylvania Inc. Telco Com at 16'-10": Raise 26" to 19'-0", Transfer to new pole at 19'-0". Ensure proper midspan clearances | 41.4129 | -75.6319 | APP_306525
P:0086 | 51 | 58096N46103 | No MR | Low Power: Drip_loop at 21'-11". Gigapower LLC Fiber Optic Com at 17'-9": Attach | 41.4127 | -75.6316 | APP_306525
P:0130 | 52 | 58053N46093 | MR Resolved | Low Power: Secondary at 26'-2". Gigapower LLC Fiber Optic Com at 22'-6": Attach. Attach to PPL vang | 41.4124 | -75.6332 | APP_306525
P:0127 | 53 | 58045N46098 | MR Resolved | Low Power: Drip_loop at 23'-6". Dunmore Boro, Lackawanna Co. Street Light at 25'-2": Ground Bracket. Dunmore Boro, Lackawanna Co. Drip Loop at 23'-6": Raise 14" to 24'-8". Gigapower LLC Fiber Optic Com at 23'-0": Attach. Bond to pole. Attach on PPL vang | 41.4126 | -75.6335 | APP_306525
P:0128 | 54 | 58035N46104 | MR Resolved | Low Power: Street_light at 19'-0". Secondary at 23'-3": Install ground rod and bond neutral to ground. Dunmore Boro, Lackawanna Co. Street Light at 21'-2": Raise 6" to 21'-8", Ground Bracket. Dunmore Boro, Lackawanna Co. Drip Loop at 20'-3": Raise 6" to 20'-9". Gigapower LLC Fiber Optic Com at 18'-9": Attach. Bond to ground wire. Gigapower LLC Fiber Optic Com at 18'-9": Attach | 41.4128 | -75.6338 | APP_306525
P:0097 | 55 | 58034N46110 | MR Resolved | Low Power: Drip_loop at 24'-1". Gigapower LLC Fiber Optic Com at 21'-5": Attach. Bond to ground wire. Gigapower LLC Down Guy at 21'-5": Attach. Install on aux eye and place on existing anchor rod with 22' lead at 213° and attach 6.6M (1/4" EHS) (7/0) guy. Gigapower LLC Fiber Optic Com at 21'-1": Attach. Bond to ground wire | 41.4129 | -75.6339 | APP_306525
P:0100 | 56 | 58041N46121 | MR Resolved | Low Power: Drip_loop at 22'-10". Dunmore Boro, Lackawanna Co. Street Light at 23'-6": Ground Bracket. Gigapower LLC Fiber Optic Com at 21'-10": Attach | 41.4132 | -75.6336 | APP_306525
P:0099 | 57 | 58042N46123 | No MR | Low Power: Secondary at 28'-10". Gigapower LLC Fiber Optic Com at 21'-3": Attach | 41.4133 | -75.6335 | APP_306525
P:0092 | 58 | 58047N46132 | MR Resolved | Low Power: Secondary at 26'-2". Secondary at 26'-4": Raise 48" to 30'-4", Install ground rod and bond neutral to ground. Gigapower LLC Fiber Optic Com at 22'-1": Attach. Bond to ground wire | 41.4135 | -75.6333 | APP_306525
P:0089 | 59 | 58051N46130 | MR Resolved | Low Power: Drip_loop at 21'-7". Dunmore Boro, Lackawanna Co. Drip Loop at 21'-7": Insulate drip loop. Gigapower LLC Fiber Optic Com at 21'-0": Attach | 41.4135 | -75.6332 | APP_306525
P:0090 | 60 | 58060N46124 | MR Resolved | Low Power: Street_light at 21'-0". Pole Top: Replace 40' class 3 pole with 45' class 3 pole. Primary at 32'-11": Raise 60" to 37'-11". PPL Company Cutout Arrestor at 31'-3": Raise 47" to 35'-2". PPL Company Transformer at 26'-7": Raise 67" to 32'-2". Secondary at 23'-10": Raise 70" to 29'-8". Secondary at 23'-9": Raise 67" to 29'-4". PPL Company Drip Loop at 23'-7": Raise 53" to 28'-0". Dunmore Boro, Lackawanna Co. Street Light at 22'-6": Raise 18" to 24'-0", Transfer to new pole at 22'-6". Gigapower LLC Fiber Optic Com at 22'-0": Attach. Dunmore Boro, Lackawanna Co. Drip Loop at 21'-7": Raise 20" to 23'-3", Transfer to new pole at 23'-3". North Penn Long Distance Corporation Strand at 19'-4": Raise 20" to 21'-0", Transfer to new pole at 21'-0". Comcast - Duryea CATV Com at 18'-7": Raise 17" to 20'-0", Transfer to new pole at 20'-0". CTSI, LLC, Dba Frontier Communications Fiber Optic Com at 17'-8": Raise 16" to 19'-0", Transfer to new pole at 19'-0". Verizon Pennsylvania Inc. Telco Com at 16'-10": Raise 14" to 18'-0", Transfer to new pole at 18'-0". Power Guy at 12'-6": Raise 36" to 15'-6" | 41.4133 | -75.6329 | APP_306525
P:0087 | 61 | 58069N46119 | MR Resolved | Low Power: Secondary at 25'-3". Pole Top: Replace 40' class 3 pole with 45' class 3 pole. Primary at 33'-5": Raise 54" to 37'-11". Secondary at 25'-3": Raise 57" to 30'-0". Gigapower LLC Fiber Optic Com at 22'-0": Attach. North Penn Long Distance Corporation Strand at 19'-1": Raise 23" to 21'-0", Transfer to new pole at 21'-0". Comcast - Duryea CATV Com at 18'-4": Raise 20" to 20'-0", Transfer to new pole at 20'-0". CTSI, LLC, Dba Frontier Communications Fiber Optic Com at 17'-6": Raise 18" to 19'-0", Transfer to new pole at 19'-0". Verizon Pennsylvania Inc. Telco Com at 15'-10": Raise 26" to 18'-0", Transfer to new pole at 18'-0" | 41.4132 | -75.6325 | APP_306525
P:0133 | 62 | 58052N46141 | No MR | Low Power: Drip_loop at 26'-3". Gigapower LLC Fiber Optic Com at 22'-9": Attach | 41.4137 | -75.6331 | APP_306525
P:0202 | 63 | 58058N46151 | MR Resolved | Low Power: Drip_loop at 20'-5". Dunmore Boro, Lackawanna Co. Street Light at 21'-2": Ground Bracket. Gigapower LLC Fiber Optic Com at 19'-1": Attach. Bond to ground wire | 41.414 | -75.6329 | APP_306525
P:0137 | 64 | 58147N46085 | No MR | Low Power: Secondary at 29'-2". Gigapower LLC Fiber Optic Com at 23'-7": Attach | 41.4122 | -75.6297 | APP_306525
P:0140 | 65 | 58153N46095 | MR Resolved | Low Power: Secondary at 26'-10". Secondary at 26'-10": Install ground rod and bond neutral to ground. North Penn Long Distance Corporation Fiber Optic Com at 23'-3": Lower 18" to 21'-9". Gigapower LLC Fiber Optic Com at 22'-9": Attach. Bond to ground wire. Comcast - Duryea CATV Com at 22'-3": Lower 18" to 20'-9". Verizon Pennsylvania Inc. Telco Com at 21'-7": Lower 22" to 19'-9". Verizon Pennsylvania Inc. Guy at 21'-7": Lower 22" to 19'-9" | 41.4125 | -75.6295 | APP_306525
P:0122 | 66 | 58205N46045 | MR Resolved | Low Power: Vertical_banner at 15'-4". Gigapower LLC Fiber Optic Com at 23'-1": Attach. Bond to ground wire. Gigapower LLC Fiber Optic Com at 23'-1": Attach. Bond to ground wire. Gigapower LLC Guy at 23'-1": Attach. Bond to ground wire | 41.4111 | -75.6277 | APP_306525
P:0049 | 67 | 58204N46056 | MR Resolved | Low Power: Drip_loop at 24'-10". Secondary at 29'-10": Raise 12" to 30'-10". Secondary at 29'-5": Raise 12" to 30'-5". Secondary at 29'-3": Raise 12" to 30'-3". Dunmore Boro, Lackawanna Co. Street Light at 27'-9": Raise 6" to 28'-3". Dunmore Boro, Lackawanna Co. Drip Loop at 24'-10": Raise 6" to 25'-4", Insulate drip loop. Gigapower LLC Fiber Optic Com at 24'-6": Attach. Gigapower LLC Fiber Optic Com at 24'-6": Attach | 41.4114 | -75.6278 | APP_306525
P:0143 | 68 | 58196N46057 | No MR | Low Power: Drip_loop at 25'-3". | 41.4114 | -75.628 | APP_306525
P:0052 | 69 | 58202N46067 | MR Resolved | Low Power: Secondary at 29'-0". Gigapower LLC Fiber Optic Com at 22'-8": Attach | 41.4117 | -75.6278 | APP_306525
P:0146 | 70 | 58206N46071 | MR Resolved | Low Power: Service at 26'-0". Pole Top: Replace 45' class 1 pole with 35' class 1 pole. Secondary at 26'-11": Raise 1" to 27'-0". Service at 26'-0": Raise 6" to 26'-6". Gigapower LLC Fiber Optic Com at 23'-0": Attach. North Penn Long Distance Corporation Fiber Optic Com at 21'-8": Raise 4" to 22'-0", Transfer to new pole at 22'-0". Comcast - Duryea CATV Com at 20'-8": Raise 4" to 21'-0", Transfer to new pole at 21'-0". Comcast - Duryea CATV Com at 20'-8": Raise 4" to 21'-0", Transfer to new pole at 21'-0". Verizon Pennsylvania Inc. Telco Com at 19'-8": Lower 8" to 19'-0", Transfer to new pole at 19'-0". Verizon Pennsylvania Inc. Telco Com at 17'-9": Raise 3" to 18'-0", Transfer to new pole at 18'-0". PPL Company Strand at 14'-5": Raise 13" to 15'-6" | 41.4117 | -75.6277 | APP_306525
P:0054 | 71 | 58201N46075 | No MR | Low Power: Drip_loop at 27'-10". Gigapower LLC Fiber Optic Com at 23'-11": Attach | 41.4119 | -75.6279 | APP_306525
P:0050 | 72 | 58211N46050 | MR Resolved | Low Power: Secondary at 26'-7". Secondary at 27'-1": Raise 10" to 27'-11". Secondary at 26'-7": Raise 10" to 27'-5". Gigapower LLC Fiber Optic Com at 23'-8": Attach. Gigapower LLC Down Guy at 23'-8": Attach. Install on aux eye and place on replaced Gigapower LLC anchor rod with 18' lead at 304° and attach 6.6M (1/4" EHS) (7/0) guy. Gigapower LLC Fiber Optic Com at 23'-4": Attach. North Penn Long Distance Corporation Down Guy at 22'-4": Transfer North Penn Long Distance Corporation Down Guy from anchor at 18' lead at 304° to the replaced Gigapower LLC anchor at 18' lead. Verizon Pennsylvania Inc. Down Guy at 19'-3": Transfer Verizon Pennsylvania Inc. Down Guy from anchor at 18' lead at 304° to the replaced Gigapower LLC anchor at 18' lead. Verizon Pennsylvania Inc. Down Guy at 18'-2": Transfer Verizon Pennsylvania Inc. Down Guy from anchor at 18' lead at 304° to the replaced Gigapower LLC anchor at 18' lead. Gigapower LLC Guy at 16'-0": Attach | 41.4112 | -75.6276 | APP_306525
P:0047 | 73 | 58220N46044 | No MR | Low Power: Drip_loop at 26'-4". Gigapower LLC Fiber Optic Com at 22'-10": Attach | 41.411 | -75.6272 | APP_306525
P:0048 | 74 | 58231N46037 | MR Resolved | Low Power: Street_light at 24'-4". Dunmore Boro, Lackawanna Co. Street Light at 24'-4": Ground Bracket. Gigapower LLC Fiber Optic Com at 21'-9": Attach. Gigapower LLC Guy at 21'-9": Attach | 41.4109 | -75.6268 | APP_306525
P:0045 | 75 | 58241N46031 | MR Resolved | Low Power: Drip_loop at 22'-5". PPL Company Riser at 22'-9": Extend 16" to 24'-1". PPL Company Drip Loop at 22'-5": Raise 16" to 23'-9". Gigapower LLC Guy at 15'-6": Attach | 41.4107 | -75.6265 | APP_306525
P:0029 | 76 | 57939N46182 | MR Resolved | Low Power: Secondary at 26'-2". Primary at 35'-4": Raise 36" to 38'-4". Primary at 32'-5": Raise 36" to 35'-5". Primary at 28'-6": Raise 36" to 31'-6". Secondary at 26'-2": Raise 36" to 29'-2". Gigapower LLC Fiber Optic Com at 21'-2": Attach. Bond to ground wire. Gigapower LLC Guy at 21'-2": Attach | 41.415 | -75.6372 | APP_306525
P:0030 | 77 | 57927N46190 | MR Resolved | Low Power: Secondary at 25'-6". XO Communications, Inc. Fiber Optic Com at 21'-10": Lower 10" to 21'-0". Gigapower LLC Fiber Optic Com at 21'-10": Attach. Comcast - Duryea CATV Com at 21'-0": Lower 12" to 20'-0". CTSI, LLC, Dba Frontier Communications Telco Com at 18'-6": Raise 9" to 19'-3", Attach to pole at 19'-3". CTSI, LLC, Dba Frontier Communications Telco Com at 18'-6": Raise 9" to 19'-3", Attach to pole at 19'-3" | 41.4152 | -75.6377 | APP_306525
P:0027 | 78 | 57922N46193 | MR Resolved | Low Power: Secondary at 25'-4". Pole Top: Replace 60' class 1 pole with 40' class 3 pole. Secondary at 25'-4": Raise 80" to 32'-0". Gigapower LLC Fiber Optic Com at 22'-0": Attach. XO Communications, Inc. Fiber Optic Com at 20'-7": Raise 5" to 21'-0", Transfer to new pole at 21'-0". Comcast - Duryea CATV Com at 19'-11": Raise 1" to 20'-0", Transfer to new pole at 20'-0". CTSI, LLC, Dba Frontier Communications Telco Com at 19'-0": Transfer to new pole at 19'-0". CTSI, LLC, Dba Frontier Communications Telco Com at 18'-0": Transfer to new pole at 18'-0" | 41.4153 | -75.6378 | APP_306525
P:0026 | 79 | 57915N46196 | MR Resolved | Low Power: Secondary at 24'-2". Secondary at 24'-2": Raise 60" to 29'-2". Gigapower LLC Fiber Optic Com at 20'-10": Attach | 41.4154 | -75.638 | APP_306525
P:0023 | 80 | 57912N46199 | No MR | Low Power: Secondary at 24'-11". Gigapower LLC Fiber Optic Com at 21'-6": Attach | 41.4155 | -75.6382 | APP_306525
P:0025 | 81 | 57901N46206 | MR Resolved | Gigapower LLC Fiber Optic Com at 23'-8": Attach. Attach to PPL vang | 41.4157 | -75.6385 | APP_306525
P:0028 | 82 | 57892N46213 | MR Resolved | Low Power: Secondary at 26'-4". Gigapower LLC Fiber Optic Com at 23'-0": Attach. Gigapower LLC Fiber Optic Com at 23'-0": Attach. Gigapower LLC Guy at 23'-0": Attach. XO Communications, Inc. Fiber Optic Com at 22'-0": Bond to ground wire | 41.4159 | -75.6389 | APP_306525
P:0016 | 83 | 57894N46216 | MR Resolved | Low Power: Service at 26'-0". Gigapower LLC Fiber Optic Com at 21'-2": Attach. Gigapower LLC Guy at 15'-6": Attach | 41.4159 | -75.6388 | APP_306525
P:0031 | 84 | 57884N46218 | MR Resolved | Low Power: Street_light at 23'-5". Dunmore Boro, Lackawanna Co. Street Light at 23'-5": Ground Bracket. Gigapower LLC Guy at 15'-6": Attach. Attach to PPL vang | 41.416 | -75.6393 | APP_306525
P:0013 | 85 | 57885N46222 | MR Resolved | Low Power: Service at 26'-4". Gigapower LLC Fiber Optic Com at 22'-6": Attach. Gigapower LLC Guy at 22'-6": Attach | 41.4161 | -75.6391 | APP_306525
P:0014 | 86 | 57874N46229 | No MR | Low Power: Vertical_banner at 14'-7". Gigapower LLC Fiber Optic Com at 19'-1": Attach | 41.4162 | -75.6394 | APP_306525
P:0083 | 87 | 58099N46099 | No MR | Low Power: Service at 29'-7". Gigapower LLC Fiber Optic Com at 19'-0": Attach | 41.4126 | -75.6315 | APP_306525
P:0051 | 88 | 58192N46052 | MR Resolved | Gigapower LLC Fiber Optic Com at 23'-8": Attach | 41.4113 | -75.6281 | APP_306525
P:0037 | 89 | 58222N45986 | MR Resolved | Low Power: Drip_loop at 23'-10". PPL Company Street Light at 24'-2": Ground Bracket. Gigapower LLC Fiber Optic Com at 22'-6": Attach. Bond to ground wire | 41.4093 | -75.6271 | APP_306525
P:0118 | 047.A | 73 | No MR | Gigapower LLC Fiber Optic Com at 19'-6": Attach | 41.4124 | -75.6328 | APP_306525
P:0080 | 028.A | 73 | No MR | Gigapower LLC Fiber Optic Com at 20'-6": Attach | 41.412 | -75.6301 | APP_306525
P:0121 | 17.1 | 612 | MR Resolved | Pole Top: Replace 25' class 4 pole with 30' class 1 pole. Gigapower LLC Guy at 16'-0": Attach. Verizon Pennsylvania Inc. Guy at 12'-11": Raise 31" to 15'-6", Transfer to new pole at 15'-6" | 41.4107 | -75.6276 | APP_306525
P:0035 | 001.A |  | No MR |  | 41.4088 | -75.6262 | APP_306525
P:0247 | 4.1 | 99 | MR Resolved | Verizon Pennsylvania Inc. Fiber Optic Com at 22'-6": Attach. Verizon Pennsylvania Inc. Telco Com at 22'-2": Lower 6" to 21'-8". Verizon Pennsylvania Inc. Guy at 22'-2": Lower 6" to 21'-8". Verizon Pennsylvania Inc. Telco Com at 21'-10": Lower 6" to 21'-4". Gigapower LLC Guy at 15'-6": Attach | 41.4096 | -75.6277 | APP_306525
P:0217 | 11 | 58173N46016 | No MR | Low Power: Drip_loop at 26'-3". Gigapower LLC Guy at 19'-0": Attach | 41.4102 | -75.6289 | APP_306525
P:0238 | 22.1 | 82; FEAT 30 | No MR | Low Power: Neutral at 27'-5". | 41.4109 | -75.6302 | APP_306525
P:0232 | 25 | 58127N46044 | MR Resolved | Low Power: Riser at 23'-3". Pole Top: Replace 40' class 4 pole with 50' class 1 pole. Cut pole top to 38'-6" (45' total pole length). Primary at 32'-4": Raise 62" to 37'-6". Primary at 32'-4": Raise 62" to 37'-6". Primary at 32'-2": Raise 69" to 37'-11". PPL Company Cutout Arrestor at 30'-0": Raise 30" to 32'-6". Neutral at 23'-8": Raise 70" to 29'-6". PPL Company Riser at 23'-3": Extend 33" to 26'-0". North Penn Long Distance Corporation Fiber Optic Com at 20'-2": Raise 10" to 21'-0", Replace 40' class 4 pole with 50' class 1 pole. Transfer to new pole at 21'-0". North Penn Long Distance Corporation Fiber Optic Com at 20'-2": Raise 10" to 21'-0", Replace 40' class 4 pole with 50' class 1 pole. Transfer to new pole at 21'-0". CTSI, LLC, Dba Frontier Communications Fiber Optic Com at 19'-2": Raise 10" to 20'-0", Transfer to new pole at 20'-0". CTSI, LLC, Dba Frontier Communications Fiber Optic Com at 19'-2": Raise 10" to 20'-0", Transfer to new pole at 20'-0". Verizon Pennsylvania Inc. Telco Com at 18'-2": Raise 10" to 19'-0", Transfer to new pole at 19'-0". Verizon Pennsylvania Inc. Telco Com at 17'-3": Raise 9" to 18'-0", Transfer to new pole at 18'-0". Gigapower LLC Guy at 16'-6": Attach. North Penn Long Distance Corporation Guy at 16'-0": Attach. CTSI, LLC, Dba Frontier Communications Guy at 15'-6": Attach | 41.4111 | -75.6306 | APP_306525
P:0249 | 55.1 | 58034N46102 | No MR | Low Power: Neutral at 29'-6". | 41.4127 | -75.6339 | APP_306525
P:0257 | 063.D | 55; _5_064N46161 | No MR | Gigapower LLC Fiber Optic Com at 22'-0": Attach | 41.4143 | -75.6327 | APP_306525
P:0024 | 22 | 57879N46276 | MR Resolved | Low Power: Drip_loop at 21'-8". Pole Top: Replace 40' class 5 pole with 45' class 3 pole. Primary at 31'-6": Raise 66" to 37'-0". PPL Company Down Guy at 30'-8": Raise 66" to 36'-2". PPL Company Cutout Arrestor at 29'-0": Raise 66" to 34'-6". PPL Company Transformer at 26'-0": Raise 60" to 31'-0". Secondary at 23'-8": Raise 58" to 28'-6". Dunmore Boro, Lackawanna Co. Street Light at 22'-4": Raise 8" to 23'-0", Transfer to new pole at 22'-7". Dunmore Boro, Lackawanna Co. Drip Loop at 21'-8": Raise 8" to 22'-4", Transfer to new pole at 22'-4". Gigapower LLC Fiber Optic Com at 21'-0": Attach. Bond to ground wire. Gigapower LLC Down Guy at 21'-0": Attach. Place on existing anchor rod with 9' lead at 39° and attach 6.6M (1/4" EHS) (7/0) guy. North Penn Long Distance Corporation Fiber Optic Com at 20'-8": Lower 8" to 20'-0", Transfer to new pole at 20'-0". North Penn Long Distance Corporation Down Guy at 20'-8": Lower 8" to 20'-0", Transfer to new pole at 20'-0". Comcast - Duryea CATV Com at 19'-8": Lower 8" to 19'-0", Transfer to new pole at 19'-0". Comcast - Duryea Down Guy at 19'-8": Lower 8" to 19'-0", Transfer Comcast - Duryea Down Guy from anchor at 9' lead at 39° to the existing anchor at 8' lead. Verizon Pennsylvania Inc. Telco Com at 18'-5": Lower 5" to 18'-0", Transfer to new pole at 18'-0". Verizon Pennsylvania Inc. Down Guy at 18'-5": Lower 5" to 18'-0", Transfer to new pole at 18'-0" | 41.4175 | -75.6393 | APP_306526
P:0021 | 23 | 57873N46268 | MR Resolved | Low Power: Drip_loop at 25'-7". North Penn Long Distance Corporation Fiber Optic Com at 21'-10": Lower 12" to 20'-10". Gigapower LLC Fiber Optic Com at 21'-10": Attach. Comcast - Duryea CATV Com at 20'-10": Lower 12" to 19'-10" | 41.4173 | -75.6396 | APP_306526
P:0022 | 24 | 57866N46261 | MR Resolved | Low Power: Street_light at 21'-7". Dunmore Boro, Lackawanna Co. Street Light at 21'-7": Ground Bracket. Gigapower LLC Fiber Optic Com at 21'-3": Attach. Bond to ground wire. North Penn Long Distance Corporation Fiber Optic Com at 21'-3": Lower 12" to 20'-3". Comcast - Duryea CATV Com at 20'-3": Lower 15" to 19'-0". Verizon Pennsylvania Inc. Telco Com at 19'-0": Lower 12" to 18'-0" | 41.4171 | -75.6398 | APP_306526
P:0019 | 25 | 57861N46254 | No MR | Low Power: Secondary at 27'-5". Gigapower LLC Fiber Optic Com at 22'-11": Attach | 41.4169 | -75.64 | APP_306526
P:0020 | 26 | 57854N46245 | MR Resolved | Low Power: Secondary at 26'-11". Gigapower LLC Fiber Optic Com at 23'-5": Attach. Gigapower LLC Down Guy at 23'-5": Attach. Install an aux eye attachment on existing anchor rod with 15' lead at 221° and attach 6.6M (1/4" EHS) (7/0) guy | 41.4168 | -75.6402 | APP_306526
P:0015 | 27 | 57852N46244 | MR Resolved | Low Power: Vertical_banner at 14'-5". Neutral at 26'-6": Attach. Power Guy at 25'-8": Attach. Gigapower LLC Fiber Optic Com at 23'-0": Attach. Gigapower LLC Fiber Optic Com at 23'-0": Attach. North Penn Long Distance Corporation Fiber Optic Com at 21'-5": Raise 7" to 22'-0". North Penn Long Distance Corporation Fiber Optic Com at 21'-5": Raise 7" to 22'-0". Comcast - Duryea CATV Com at 21'-0": Bolt to pole at 21'-0" | 41.4167 | -75.6403 | APP_306526
P:0032 | 28 | 57849N46241 | MR Unresolved | Low Power: Secondary at 23'-1". | 41.4166 | -75.6404 | APP_306526
P:0018 | 29 | 57842N46252 | MR Resolved | Low Power: Vertical_banner at 15'-4". Neutral at 25'-6": Attach. Power Guy at 24'-8": Attach. North Penn Long Distance Corporation Fiber Optic Com at 20'-9": Lower 21" to 19'-0". Gigapower LLC Fiber Optic Com at 20'-0": Attach. Bond to ground wire. Verizon Pennsylvania Inc. Telco Com at 19'-7": Lower 19" to 18'-0" | 41.4169 | -75.6406 | APP_306526
P:0017 | 30 | 57835N46257 | MR Resolved | Low Power: Vertical_banner at 14'-7". Service at 26'-0": Raise 18" to 27'-6". Service at 26'-0": Raise 18" to 27'-6". Secondary at 26'-0": Raise 18" to 27'-6". PPL Company Drip Loop at 24'-6": Raise 18" to 26'-0". Gigapower LLC Fiber Optic Com at 22'-6": Attach. Power Guy at 15'-6": Attach | 41.4171 | -75.6409 | APP_306526
P:0011 | 31 | 57868N46232 | No MR | Low Power: Drip_loop at 24'-3". Gigapower LLC Fiber Optic Com at 19'-3": Attach | 41.4164 | -75.6398 | APP_306526
P:0010 | 32 | 57857N46239 | No MR | Low Power: Vertical_banner at 14'-8". Gigapower LLC Fiber Optic Com at 21'-1": Attach. Power Guy at 15'-6": Attach | 41.4165 | -75.64 | APP_306526
P:0253 | 1 | 57994N46256 | No MR | Low Power: Fuse Holder at 25'-6". Gigapower LLC Fiber Optic Com at 23'-6": Attach | 41.4169 | -75.6352 | APP_306524
P:0254 | 2 | 58001N46251 | MR Resolved | Low Power: Drip_loop at 24'-9". Gigapower LLC Fiber Optic Com at 21'-9": Attach. Bond to ground wire | 41.4168 | -75.6349 | APP_306524
P:0191 | 3 | 58007N46248 | No MR | Low Power: Drip_loop at 29'-3". Gigapower LLC Fiber Optic Com at 21'-4": Attach | 41.4167 | -75.6347 | APP_306524
P:0200 | 4 | 58019N46252 | No MR | Low Power: Secondary at 32'-9". Gigapower LLC Fiber Optic Com at 22'-0": Attach | 41.4168 | -75.6343 | APP_306524
P:0199 | 5 | 58024N46262 | No MR | Low Power: Drip_loop at 22'-5". Gigapower LLC Fiber Optic Com at 18'-3": Attach. Gigapower LLC Guy at 18'-3": Attach | 41.417 | -75.6341 | APP_306524
P:0201 | 6 | 58028N46268 | MR Resolved | Gigapower LLC Guy at 18'-0": Attach. This pole has an open complex application with Verizon to be replaced from a previous PPL application. Please do not attach to the pole until the pole replacement has been completed. North Penn Long Distance Corporation Strand at 15'-0": Remove | 41.4172 | -75.6339 | APP_306524
P:0189 | 7 | 58023N46238 | MR Resolved | Low Power: Secondary at 28'-8". Gigapower LLC Fiber Optic Com at 23'-5": Attach. Bond to ground wire | 41.4164 | -75.6341 | APP_306524
P:0187 | 8 | 58033N46232 | MR Resolved | Low Power: Drip_loop at 23'-7". Secondary at 25'-4": Raise 24" to 27'-4". Secondary at 25'-0": Raise 24" to 27'-0". Dunmore Boro, Lackawanna Co. Street Light at 24'-0": Ground Bracket. Gigapower LLC Fiber Optic Com at 21'-8": Attach | 41.4162 | -75.6337 | APP_306524
P:0198 | 9 | 58038N46240 | MR Resolved | Low Power: Secondary at 23'-11". Secondary at 23'-11": Raise 24" to 25'-11". Gigapower LLC Fiber Optic Com at 21'-5": Attach | 41.4164 | -75.6335 | APP_306524
P:0197 | 10 | 58044N46250 | No MR | Low Power: Drip_loop at 23'-2". Gigapower LLC Fiber Optic Com at 20'-5": Attach. Bond to ground wire. Gigapower LLC Guy at 20'-5": Attach. Bond to ground wire | 41.4167 | -75.6333 | APP_306524
P:0202 | 11 | 58047N46254 | MR Resolved | North Penn Long Distance Corporation Down Guy at 16'-6": Lower 6" to 16'-0". Gigapower LLC Down Guy at 16'-6": Attach. Place on existing anchor rod with 15' lead at 31° and attach 6.6M (1/4" EHS) (7/0) guy. North Penn Long Distance Corporation Guy at 16'-6": Lower 6" to 16'-0". Gigapower LLC Guy at 16'-6": Attach. Comcast - Duryea Guy at 16'-0": Lower 6" to 15'-6" | 41.4168 | -75.6332 | APP_306524
P:0190 | 12 | 58046N46225 | No MR | Low Power: Secondary at 26'-10". Gigapower LLC Fiber Optic Com at 21'-9": Attach | 41.416 | -75.6333 | APP_306524
P:0167 | 13 | 58057N46218 | No MR | Low Power: Drip_loop at 24'-10". Gigapower LLC Fiber Optic Com at 21'-9": Attach | 41.4158 | -75.6329 | APP_306524
P:0196 | 14 | 58062N46226 | No MR | Low Power: Secondary at 27'-11". Gigapower LLC Fiber Optic Com at 21'-4": Attach | 41.416 | -75.6327 | APP_306524
P:0195 | 15 | 58071N46241 | MR Resolved | Low Power: Drip_loop at 21'-5". Service at 25'-3": Raise 36" to 28'-3". Secondary at 25'-3": Raise 36" to 28'-3". Service at 25'-3": Raise 36" to 28'-3". Service at 25'-3": Raise 36" to 28'-3". PPL Company Down Guy at 24'-6": Raise 36" to 27'-6". PPL Company Drip Loop at 24'-2": Raise 36" to 27'-2". Dunmore Boro, Lackawanna Co. Street Light at 21'-8": Ground bracket. Gigapower LLC Fiber Optic Com at 20'-5": Attach. Gigapower LLC Down Guy at 20'-5": Attach. Place on existing anchor rod with 13' lead at 33° and attach 6.6M (1/4" EHS) (7/0) guy. Verizon Pennsylvania Inc. Down Guy at 17'-2": Transfer Verizon Pennsylvania Inc. Down Guy from anchor at 13' lead at 33° to the new Gigapower LLC anchor at 9' lead | 41.4163 | -75.6325 | APP_306524
P:0170 | 16 | 58065N46213 | MR Resolved | Low Power: Secondary at 25'-7". Gigapower LLC Fiber Optic Com at 22'-7": Attach. Bond to ground wire | 41.4157 | -75.6326 | APP_306524
P:0169 | 17 | 58076N46207 | MR Resolved | Low Power: Drip_loop at 25'-10". Secondary at 26'-5": Raise 36" to 29'-5". Secondary at 26'-2": Raise 36" to 29'-2". PPL Company Drip Loop at 25'-10": Raise 36" to 28'-10". Gigapower LLC Fiber Optic Com at 22'-9": Attach | 41.4155 | -75.6323 | APP_306524
P:0159 | 18 | 58087N46200 | MR Resolved | Low Power: Drip_loop at 23'-10". Secondary at 25'-2": Raise 12" to 26'-2". Secondary at 24'-9": Raise 12" to 25'-9". Service at 24'-6": Raise 12" to 25'-6". Secondary at 24'-4": Raise 12" to 25'-4". PPL Company Drip Loop at 23'-10": Raise 12" to 24'-10". Gigapower LLC Fiber Optic Com at 22'-2": Attach. Bond to ground wire. Gigapower LLC Fiber Optic Com at 22'-2": Attach. Bond to ground wire. Gigapower LLC Fiber Optic Com at 22'-2": Attach. Bond to ground wire | 41.4153 | -75.6318 | APP_306524
P:0184 | 19 | 58093N46209 | MR Resolved | Low Power: Secondary at 25'-5". Gigapower LLC Fiber Optic Com at 22'-0": Attach. Power Guy at 15'-9": Raise 9" to 16'-6". Gigapower LLC Guy at 15'-6": Attach | 41.4155 | -75.6316 | APP_306524
P:0183 | 20 | 58098N46218 | MR Resolved | Low Power: Street_light at 21'-8". Pole Top: Replace 45' class 3 pole with 50' class 2 pole. Primary at 35'-10": Raise 77" to 42'-3". Primary at 35'-10": Raise 77" to 42'-3". Primary at 35'-10": Raise 77" to 42'-3". Power Guy at 35'-2": Raise 75" to 41'-5". PPL Company Cutout Arrestor at 32'-7": Raise 76" to 38'-11". PPL Company Transformer at 28'-5": Raise 71" to 34'-4". PPL Company Transformer at 28'-5": Raise 71" to 34'-4". PPL Company Transformer at 28'-5": Raise 71" to 34'-4". Service at 25'-7": Raise 39" to 28'-10". Secondary at 24'-10": Raise 42" to 28'-4". Secondary at 24'-8": Raise 40" to 28'-0". PPL Company Drip Loop at 24'-4": Raise 38" to 27'-6". Dunmore Boro, Lackawanna Co. Street Light at 23'-2": Raise 22" to 25'-0", Transfer to new pole at 23'-6". Ground bracket. Gigapower LLC Fiber Optic Com at 23'-0": Attach. Bond to ground wire. Gigapower LLC Fiber Optic Com at 23'-0": Attach. Bond to ground wire. Gigapower LLC Guy at 23'-0": Attach. Bond to ground wire. Dunmore Boro, Lackawanna Co. Drip Loop at 22'-6": Raise 22" to 24'-4", Transfer to new pole at 24'-4". North Penn Long Distance Corporation Fiber Optic Com at 21'-5": Raise 7" to 22'-0", Transfer to new pole at 22'-0". North Penn Long Distance Corporation Guy at 21'-5": Raise 7" to 22'-0", Transfer to new pole at 22'-0". Comcast - Duryea CATV Com at 20'-5": Raise 7" to 21'-0", Transfer to new pole at 21'-0". Comcast - Duryea Guy at 20'-5": Raise 7" to 21'-0", Transfer to new pole at 21'-0". Verizon Pennsylvania Inc. Telco Com at 19'-3": Raise 9" to 20'-0", Transfer to new pole at 20'-0". Verizon Pennsylvania Inc. Telco Com at 19'-3": Raise 9" to 20'-0", Transfer to new pole at 20'-0". Verizon Pennsylvania Inc. Guy at 18'-9": Raise 9" to 19'-6", Transfer to new pole at 19'-6" | 41.4157 | -75.6314 | APP_306524
P:0229 | 21 | 58100N46222 | MR Resolved | Gigapower LLC Fiber Optic Com at 18'-10": Attach. Power Guy at 18'-10": Raise 12" to 19'-10". Gigapower LLC Guy at 15'-6": Attach | 41.4159 | -75.6313 | APP_306524
P:0205 | 22 | 58092N46201 | MR Resolved | Low Power: Street_light at 21'-3". Dunmore Boro, Lackawanna Co. Street Light at 21'-3": Ground Bracket. Gigapower LLC Fiber Optic Com at 20'-11": Attach. Gigapower LLC Guy at 20'-11": Attach | 41.4153 | -75.6316 | APP_306524
P:0208 | 23 | 58102N46195 | MR Resolved | Low Power: Secondary at 27'-9". Gigapower LLC Fiber Optic Com at 19'-9": Attach. Power Guy at 19'-5": Lower 47" to 15'-6" | 41.4152 | -75.6313 | APP_306524
P:0160 | 24 | 58084N46195 | MR Resolved | Low Power: Secondary at 25'-2". Pole Top: Replace 40' class 4 pole with 45' class 2 pole. Primary at 33'-6": Raise 47" to 37'-5". Secondary at 25'-2": Raise 22" to 27'-0". Gigapower LLC Fiber Optic Com at 22'-0": Attach. North Penn Long Distance Corporation Fiber Optic Com at 20'-11": Raise 1" to 21'-0", Transfer to new pole at 21'-0". Comcast - Duryea CATV Com at 19'-11": Raise 1" to 20'-0", Transfer to new pole at 20'-0". Verizon Pennsylvania Inc. Telco Com at 19'-2": Lower 2" to 19'-0", Transfer to new pole at 19'-0". Power Guy at 12'-11": Raise 31" to 15'-6" | 41.4152 | -75.6319 | APP_306524
P:0157 | 25 | 58079N46185 | MR Resolved | Low Power: Drip_loop at 24'-7". Gigapower LLC Fiber Optic Com at 22'-0": Attach. Bond to ground wire | 41.4149 | -75.6321 | APP_306524
P:0158 | 26 | 58073N46176 | MR Resolved | Low Power: Street_light at 23'-5". Gigapower LLC Fiber Optic Com at 22'-7": Attach. North Penn Long Distance Corporation Fiber Optic Com at 22'-7": Lower 12" to 21'-7". Comcast - Duryea CATV Com at 21'-7": Lower 15" to 20'-4". Verizon Pennsylvania Inc. Telco Com at 20'-4": Lower 12" to 19'-4" | 41.4147 | -75.6323 | APP_306524
P:0155 | 27 | 58067N46166 | MR Resolved | Low Power: Secondary at 27'-5". Secondary at 27'-5": Install ground rod and bond neutral to ground. Gigapower LLC Fiber Optic Com at 24'-4": Attach. Bond to ground wire | 41.4144 | -75.6325 | APP_306524
P:0179 | 28 | 57996N46213 | MR Resolved | Low Power: Drip_loop at 23'-3". Pole Top: Replace 45' class 1 pole with 45' class 2 pole. Secondary at 23'-10": Raise 86" to 31'-0". Service at 23'-10": Raise 86" to 31'-0". PPL Company Drip Loop at 23'-3": Raise 87" to 30'-6". Gigapower LLC Fiber Optic Com at 21'-0": Attach. North Penn Long Distance Corporation Strand at 19'-6": Raise 6" to 20'-0", Transfer to new pole at 20'-0". North Penn Long Distance Corporation Fiber Optic Com at 19'-6": Raise 6" to 20'-0", Transfer to new pole at 20'-0". Comcast - Duryea CATV Com at 18'-6": Raise 6" to 19'-0", Transfer to new pole at 19'-0". Verizon Pennsylvania Inc. Telco Com at 17'-2": Raise 10" to 18'-0", Transfer to new pole at 18'-0". Power Guy at 16'-1": Lower 43" to 12'-6". Gigapower LLC Guy at 11'-6": Attach. Comcast - Duryea Guy at 11'-0": Attach. North Penn Long Distance Corporation Guy at 10'-11": Lower 5" to 10'-6", Transfer to new pole at 10'-6". Verizon Pennsylvania Inc. Guy at 10'-0": Transfer to new pole at 10'-0". Verizon Pennsylvania Inc. Guy at 9'-3": Raise 3" to 9'-6", Transfer to new pole at 9'-6" | 41.4158 | -75.6351 | APP_306524
P:0194 | 29 | 58002N46223 | MR Resolved | Low Power: Street_light at 24'-2". Dunmore Boro, Lackawanna Co. Street Light at 24'-2": Ground Bracket. Gigapower LLC Fiber Optic Com at 22'-11": Attach. Bond to ground wire. Gigapower LLC Guy at 22'-11": Attach. Bond to ground wire. Comcast - Duryea CATV Com at 20'-11": Convert SW span to slack tension with a pole to pole guy. Comcast - Duryea Guy at 20'-9": Attach | 41.416 | -75.6349 | APP_306524
P:0192 | 31 | 58014N46243 | MR Resolved | Low Power: Drip_loop at 22'-8". Dunmore Boro, Lackawanna Co. Street Light at 22'-10": Ground Bracket. Gigapower LLC Fiber Optic Com at 20'-11": Attach | 41.4166 | -75.6344 | APP_306524
P:0177 | 32 | 58015N46201 | MR Resolved | Low Power: Street_light at 20'-9". Pole Top: Replace 40' class 3 pole with 55' class 1 pole. Cut pole top to 34'-0" (40' total pole length). Rake n Key 12" away from span bearing 40°. Secondary at 25'-1": Raise 41" to 28'-6". Service at 24'-6": Raise 42" to 28'-0". Service at 24'-6": Raise 42" to 28'-0". PPL Company Drip Loop at 23'-1": Raise 41" to 26'-6". Dunmore Boro, Lackawanna Co. Street Light at 22'-5": Raise 27" to 24'-8", Ground Bracket. Transfer to new pole at 23'-0". Gigapower LLC Fiber Optic Com at 22'-0": Attach. Dunmore Boro, Lackawanna Co. Drip Loop at 21'-7": Raise 27" to 23'-10", Transfer to new pole at 23'-10". North Penn Long Distance Corporation Fiber Optic Com at 19'-3": Raise 21" to 21'-0", Transfer to new pole at 21'-0". North Penn Long Distance Corporation Strand at 19'-3": Raise 21" to 21'-0", Transfer to new pole at 21'-0". Comcast - Duryea CATV Com at 18'-4": Raise 20" to 20'-0", Transfer to new pole at 20'-0". Verizon Pennsylvania Inc. Telco Com at 16'-7": Raise 29" to 19'-0", Transfer to new pole at 19'-0". Gigapower LLC Guy at 16'-0": Attach. Verizon Pennsylvania Inc. Telco Com at 15'-11": Raise 25" to 18'-0", Transfer to new pole at 18'-0". Verizon Pennsylvania Inc. Guy at 15'-11": Raise 25" to 18'-0", Transfer to new pole at 18'-0". North Penn Long Distance Corporation Guy at 13'-8": Raise 22" to 15'-6", Transfer to new pole at 15'-6". Verizon Pennsylvania Inc. Guy at 12'-8": Raise 28" to 15'-0", Transfer to new pole at 15'-0" | 41.4154 | -75.6344 | APP_306524
P:0186 | 33 | 58018N46206 | MR Resolved | Low Power: Drip_loop at 31'-5". Secondary at 32'-0": Resag span with bearing 32° up 18". Gigapower LLC Fiber Optic Com at 23'-6": Resag span with bearing 32° up 22", Attach. Gigapower LLC Guy at 23'-6": Attach. Comcast - Duryea Guy at 12'-9": Raise 33" to 15'-6", Ensure proper mid span clearance at or above 15'-6" over non-state road is met | 41.4155 | -75.6343 | APP_306524
P:0185 | 34 | 58024N46216 | MR Resolved | Low Power: Street_light at 20'-7". Pole Top: Replace 40' class 5 pole with 45' class 3 pole. Primary at 33'-8": Raise 49" to 37'-9". Power Guy at 32'-9": Raise 50" to 36'-11". PPL Company Cutout Arrestor at 31'-0": Raise 51" to 35'-3". PPL Company Transformer at 27'-3": Raise 54" to 31'-9". Secondary at 25'-1": Raise 47" to 29'-0". Resag span with bearing 212° up 18". Dunmore Boro, Lackawanna Co. Street Light at 22'-6": Raise 29" to 24'-11", Ground bracket. Transfer to new pole at 23'-0". Gigapower LLC Fiber Optic Com at 22'-0": Resag span with bearing 212° up 22", Attach. Bond to ground wire. Dunmore Boro, Lackawanna Co. Drip Loop at 21'-8": Raise 29" to 24'-1", Transfer to new pole at 24'-1". North Penn Long Distance Corporation Strand at 20'-3": Raise 9" to 21'-0", Transfer to new pole at 21'-0". Comcast - Duryea CATV Com at 19'-8": Raise 4" to 20'-0", Transfer to new pole at 20'-0". Comcast - Duryea CATV Com at 19'-8": Raise 4" to 20'-0", Transfer to new pole at 20'-0". Comcast - Duryea Guy at 19'-8": Raise 4" to 20'-0", Transfer to new pole at 20'-0". Verizon Pennsylvania Inc. Guy at 18'-6": Transfer to new pole at 18'-6". Verizon Pennsylvania Inc. Telco Com at 17'-11": Raise 13" to 19'-0", Transfer to new pole at 19'-0" | 41.4158 | -75.6341 | APP_306524
P:0188 | 35 | 58029N46224 | MR Resolved | Low Power: Secondary at 26'-5". Secondary at 26'-5": Raise 24" to 28'-5". Gigapower LLC Fiber Optic Com at 22'-1": Attach | 41.416 | -75.6339 | APP_306524
P:0175 | 36 | 58034N46189 | No MR | Gigapower LLC Fiber Optic Com at 22'-7": Attach. Power Guy at 15'-6": Attach | 41.4151 | -75.6338 | APP_306524
P:0246 | 37 | 58041N46182 | MR Resolved | Low Power: Drip_loop at 25'-6". Power Guy at 32'-2": Attach. Neutral at 31'-6": Attach. Pole Top: Replace 35' class 4 pole with 40' class 3 pole. Secondary at 27'-8": Raise 64" to 33'-0". Secondary at 26'-2": Raise 62" to 31'-4". Service at 26'-0": Raise 60" to 31'-0". Power Guy at 25'-7": Raise 55" to 30'-2". PPL Company Drip Loop at 25'-6": Raise 60" to 30'-6". Gigapower LLC Fiber Optic Com at 24'-0": Attach. Gigapower LLC Guy at 24'-0": Attach. North Penn Long Distance Corporation Strand at 22'-9": Raise 3" to 23'-0", Transfer to new pole at 23'-0". North Penn Long Distance Corporation Strand at 22'-9": Raise 3" to 23'-0", Transfer to new pole at 23'-0". North Penn Long Distance Corporation Fiber Optic Com at 22'-9": Raise 3" to 23'-0", Transfer to new pole at 23'-0". Comcast - Duryea CATV Com at 21'-10": Raise 2" to 22'-0", Transfer to new pole at 22'-0". Verizon Pennsylvania Inc. Strand at 21'-6": Transfer to new pole at 21'-6". Verizon Pennsylvania Inc. Guy at 21'-6": Transfer to new pole at 21'-6". Verizon Pennsylvania Inc. Telco Com at 20'-10": Lower 4" to 20'-6", Transfer to new pole at 20'-6". Verizon Pennsylvania Inc. Guy at 20'-10": Lower 4" to 20'-6", Transfer to new pole at 20'-6" | 41.4149 | -75.6335 | APP_306524
P:0165 | 38 | 58044N46195 | MR Resolved | Low Power: Secondary at 24'-5". Gigapower LLC Fiber Optic Com at 20'-1": Attach. Bond to ground wire | 41.4153 | -75.6334 | APP_306524
P:0168 | 39 | 58050N46206 | No MR | Low Power: Secondary at 27'-7". Gigapower LLC Fiber Optic Com at 22'-6": Attach | 41.4155 | -75.6331 | APP_306524
P:0204 | 40 | 58050N46180 | MR Resolved | Low Power: Secondary at 30'-2". Gigapower LLC Down Guy at 19'-2": Attach and install new anchor. Place on new Gigapower LLC anchor rod with 20' lead at 120° and attach 6.6M (1/4" EHS) (7/0) guy. Gigapower LLC Guy at 19'-2": Attach | 41.4148 | -75.6332 | APP_306524
P:0072 | 41 | 57955N46214 | MR Resolved | Low Power: Vertical_banner at 14'-8". Pole Top: Replace 45' class 5 pole with 50' class 3 pole. Primary at 39'-6": Raise 38" to 42'-8". Primary at 36'-11": Raise 40" to 40'-3". PPL Company Down Guy at 36'-2": Raise 39" to 39'-5". Primary at 34'-4": Raise 42" to 37'-10". Neutral at 30'-9": Raise 43" to 34'-4". Secondary at 30'-5": Raise 43" to 34'-0". Power Guy at 28'-3": Raise 63" to 33'-6". Gigapower LLC Fiber Optic Com at 27'-0": Attach. Gigapower LLC Fiber Optic Com at 27'-0": Attach. Gigapower LLC Down Guy at 27'-0": Attach. Install an aux eye attachment on existing anchor rod with 24' lead at 195° and attach 6.6M (1/4" EHS) (7/0) guy. North Penn Long Distance Corporation Fiber Optic Com at 26'-11": Lower 11" to 26'-0", Transfer to new pole at 26'-0". North Penn Long Distance Corporation Down Guy at 26'-11": Lower 11" to 26'-0", Transfer to new pole at 26'-0". ZitoMedia / Zito West Holding, LLC Fiber Optic Com at 26'-2": Lower 8" to 25'-6", Transfer to new pole at 25'-6". ZitoMedia / Zito West Holding, LLC Down Guy at 26'-2": Lower 8" to 25'-6", Transfer to new pole at 25'-6". ZitoMedia / Zito West Holding, LLC Fiber Optic Com at 25'-9": Lower 9" to 25'-0", Transfer to new pole at 25'-0". Comcast - Duryea CATV Com at 25'-2": Lower 14" to 24'-0", Transfer to new pole at 24'-0". Comcast - Duryea Down Guy at 25'-2": Lower 14" to 24'-0", Transfer to new pole at 24'-0". CTSI, LLC, Dba Frontier Communications Fiber Optic Com at 23'-6": Lower 6" to 23'-0", Transfer to new pole at 23'-0". CTSI, LLC, Dba Frontier Communications Fiber Optic Com at 23'-6": Lower 6" to 23'-0", Transfer to new pole at 23'-0". CTSI, LLC, Dba Frontier Communications Guy at 23'-6": Lower 6" to 23'-0", Transfer to new pole at 23'-0". Verizon Pennsylvania Inc. Telco Com at 22'-3": Lower 3" to 22'-0", Transfer to new pole at 22'-0". Verizon Pennsylvania Inc. Telco Com at 22'-3": Lower 3" to 22'-0", Transfer to new pole at 22'-0". Verizon Pennsylvania Inc. Down Guy at 22'-3": Lower 3" to 22'-0", Transfer to new pole at 22'-0". Verizon Pennsylvania Inc. Guy at 22'-3": Lower 3" to 22'-0", Transfer to new pole at 22'-0". Dunmore Boro, Lackawanna Co. Vertical Banner at 14'-8": Raise 4" to 15'-0", Transfer to new pole at 15'-0" | 41.4158 | -75.6367 | APP_306524
P:0069 | 42 | 57969N46210 | MR Resolved | Low Power: Street_light at 23'-8". Pole Top: Replace 45' class 2 pole with 50' class 2 pole. Primary at 39'-8": Raise 36" to 42'-8". Primary at 38'-10": Raise 36" to 41'-10". Primary at 36'-6": Raise 33" to 39'-3". Primary at 35'-7": Raise 33" to 38'-4". Power Guy at 35'-1": Raise 29" to 37'-6". PPL Company Down Guy at 34'-10": Raise 30" to 37'-4", Upgrade existing down guy strand to a 25M (1/2" UG) (7/0) strand size. Primary at 33'-5": Raise 29" to 35'-10". Primary at 32'-5": Raise 29" to 34'-10". Secondary at 28'-3": Raise 44" to 31'-11". Secondary at 28'-0": Raise 44" to 31'-8". Secondary at 28'-0": Raise 44" to 31'-8". PPL Company Drip Loop at 27'-6": Raise 44" to 31'-2". Neutral at 27'-4": Raise 44" to 31'-0". Dunmore Boro, Lackawanna Co. Street Light at 25'-8": Raise 16" to 27'-0", Ground Bracket. Transfer to new pole at 25'-0". Gigapower LLC Fiber Optic Com at 24'-6": Attach. Gigapower LLC Down Guy at 24'-6": Attach. Place on existing anchor rod with 15' lead at 31° and attach 6.6M (1/4" EHS) (7/0) guy. Dunmore Boro, Lackawanna Co. Drip Loop at 24'-6": Raise 16" to 25'-10", Transfer to new pole at 25'-10". North Penn Long Distance Corporation Fiber Optic Com at 23'-6": Transfer to new pole at 23'-6". North Penn Long Distance Corporation Down Guy at 23'-6": Transfer to new pole at 23'-6". Power Guy at 23'-0": Transfer to new pole at 23'-0". Comcast - Duryea CATV Com at 22'-8": Lower 2" to 22'-6", Transfer to new pole at 22'-6". Comcast - Duryea CATV Com at 22'-5": Lower 5" to 22'-0", Transfer to new pole at 22'-0". Comcast - Duryea CATV Com at 21'-11": Lower 5" to 21'-6", Transfer to new pole at 21'-6". Comcast - Duryea Down Guy at 21'-11": Lower 5" to 21'-6", Transfer to new pole at 21'-6". CTSI, LLC, Dba Frontier Communications Fiber Optic Com at 21'-2": Lower 2" to 21'-0", Transfer to new pole at 21'-0". CTSI, LLC, Dba Frontier Communications Down Guy at 21'-2": Lower 2" to 21'-0", Transfer to new pole at 21'-0". Verizon Pennsylvania Inc. Telco Com at 20'-6": Transfer to new pole at 20'-6". Verizon Pennsylvania Inc. Telco Com at 20'-6": Transfer to new pole at 20'-6". Verizon Pennsylvania Inc. Telco Com at 20'-0": Transfer to new pole at 20'-0". Verizon Pennsylvania Inc. Guy at 15'-3": Raise 3" to 15'-6", Transfer to new pole at 15'-6" | 41.4157 | -75.6361 | APP_306524
P:0070 | 43 | 57978N46205 | MR Resolved | Low Power: Vertical_banner at 13'-10". Dunmore Boro, Lackawanna Co. Street Light at 22'-8": Ground Bracket. North Penn Long Distance Corporation Fiber Optic Com at 22'-4": Lower 12" to 21'-4". Gigapower LLC Fiber Optic Com at 22'-4": Attach. Bond to ground wire. Comcast - Duryea CATV Com at 21'-10": Lower 12" to 20'-10". CTSI, LLC, Dba Frontier Communications Fiber Optic Com at 20'-10": Lower 14" to 19'-8". Verizon Pennsylvania Inc. Telco Com at 19'-10": Lower 14" to 18'-8". Verizon Pennsylvania Inc. Telco Com at 19'-10": Lower 14" to 18'-8". Verizon Pennsylvania Inc. Guy at 19'-10": Lower 14" to 18'-8" | 41.4155 | -75.6358 | APP_306524
P:0067 | 44 | 57991N46197 | No MR | Low Power: Drip_loop at 31'-10". Gigapower LLC Fiber Optic Com at 26'-6": Attach | 41.4153 | -75.6353 | APP_306524
P:0068 | 45 | 58004N46189 | MR Resolved | Low Power: Vertical_banner at 14'-9". Pole Top: Replace 45' class 3 pole with 50' class 3 pole. Primary at 37'-4": Raise 63" to 42'-7". Primary at 36'-11": Raise 63" to 42'-2". Power Guy at 36'-1": Raise 63" to 41'-4". Primary at 34'-9": Raise 65" to 40'-2". Primary at 34'-6": Raise 66" to 40'-0". Primary at 32'-4": Raise 65" to 37'-9". Primary at 32'-2": Raise 65" to 37'-7". Power Guy at 31'-5": Raise 64" to 36'-9". PPL Company Down Guy at 31'-2": Raise 65" to 36'-7". Secondary at 29'-0": Raise 67" to 34'-7". Neutral at 28'-7": Raise 65" to 34'-0". Dunmore Boro, Lackawanna Co. Street Light at 27'-2": Raise 16" to 28'-6", Transfer to new pole at 26'-6". Gigapower LLC Fiber Optic Com at 25'-6": Attach. Gigapower LLC Fiber Optic Com at 25'-6": Attach. Gigapower LLC Guy at 25'-6": Attach. Dunmore Boro, Lackawanna Co. Drip Loop at 24'-11": Raise 16" to 26'-3", Transfer to new pole at 26'-3". Loop Internet Fiber Optic Com at 24'-0": Raise 6" to 24'-6", Transfer to new pole at 24'-6". Loop Internet Guy at 24'-0": Raise 6" to 24'-6", Transfer to new pole at 24'-6". North Penn Long Distance Corporation Strand at 23'-0": Raise 6" to 23'-6", Transfer to new pole at 23'-6". North Penn Long Distance Corporation Fiber Optic Com at 23'-0": Raise 6" to 23'-6", Transfer to new pole at 23'-6". North Penn Long Distance Corporation Guy at 23'-0": Raise 6" to 23'-6", Transfer to new pole at 23'-6". Comcast - Duryea CATV Com at 21'-10": Raise 8" to 22'-6", Transfer to new pole at 22'-6". Comcast - Duryea CATV Com at 21'-10": Raise 8" to 22'-6", Transfer to new pole at 22'-6". CTSI, LLC, Dba Frontier Communications Fiber Optic Com at 20'-11": Raise 7" to 21'-6", Transfer to new pole at 21'-6". CTSI, LLC, Dba Frontier Communications Guy at 20'-11": Raise 7" to 21'-6", Transfer to new pole at 21'-6". CTSI, LLC, Dba Frontier Communications Fiber Optic Com at 20'-6": Raise 6" to 21'-0", Transfer to new pole at 21'-0". CTSI, LLC, Dba Frontier Communications Down Guy at 20'-6": Raise 6" to 21'-0", Transfer to new pole at 21'-0". Verizon Pennsylvania Inc. Telco Com at 19'-11": Raise 7" to 20'-6", Transfer to new pole at 20'-6". Verizon Pennsylvania Inc. Guy at 19'-11": Raise 7" to 20'-6", Transfer to new pole at 20'-6". Verizon Pennsylvania Inc. Telco Com at 19'-6": Raise 6" to 20'-0", Transfer to new pole at 20'-0". Verizon Pennsylvania Inc. Down Guy at 19'-6": Raise 6" to 20'-0", Transfer to new pole at 20'-0". Dunmore Boro, Lackawanna Co. Vertical Banner at 14'-9": Raise 3" to 15'-0", Transfer to new pole at 15'-0" | 41.4151 | -75.6349 | APP_306524
P:0255 | 46 | 58009N46198 | MR Resolved | Loop Internet Down Guy at 18'-4": Lower 6" to 17'-10". Loop Internet Guy at 18'-4": Lower 6" to 17'-10". Gigapower LLC Down Guy at 18'-4": Attach. Install an aux eye attachment on existing anchor rod with 10' lead at 35° and attach 6.6M (1/4" EHS) (7/0) guy. Gigapower LLC Guy at 18'-4": Attach. CTSI, LLC, Dba Frontier Communications Guy at 17'-4": Lower 6" to 16'-10". Verizon Pennsylvania Inc. Down Guy at 16'-10": Lower 6" to 16'-4". Verizon Pennsylvania Inc. Guy at 16'-10": Lower 6" to 16'-4" | 41.4154 | -75.6346 | APP_306524
P:0174 | 47 | 58013N46184 | MR Resolved | Low Power: Vertical_banner at 14'-8". Gigapower LLC Fiber Optic Com at 22'-2": Attach. Bond to ground wire | 41.4149 | -75.6346 | APP_306524
P:0171 | 48 | 58021N46179 | MR Resolved | Low Power: Street_light at 22'-5". Dunmore Boro, Lackawanna Co. Street Light at 22'-5": Ground Bracket. North Penn Long Distance Corporation Fiber Optic Com at 21'-1": Lower 12" to 20'-1". Gigapower LLC Fiber Optic Com at 21'-1": Attach. Comcast - Duryea CATV Com at 20'-1": Lower 12" to 19'-1" | 41.4148 | -75.6342 | APP_306524
P:0172 | 49 | 58030N46173 | MR Resolved | Low Power: Secondary at 26'-10". Secondary at 26'-10": Install ground rod and bond neutral to ground. Gigapower LLC Fiber Optic Com at 24'-0": Attach. Bond to ground wire | 41.4146 | -75.6339 | APP_306524
P:0164 | 50 | 58037N46176 | No MR | Gigapower LLC Fiber Optic Com at 24'-8": Attach | 41.4147 | -75.6336 | APP_306524
P:0173 | 51 | 58039N46168 | No MR | Low Power: Secondary at 25'-10". Gigapower LLC Fiber Optic Com at 20'-8": Attach | 41.4145 | -75.6336 | APP_306524
P:0176 | 52 | 58047N46163 | MR Resolved | Low Power: Transformer at 23'-5". Gigapower LLC Fiber Optic Com at 20'-6": Attach. Bond to ground wire | 41.4143 | -75.6333 | APP_306524
P:0153 | 53 | 58055N46158 | No MR | Low Power: Drip_loop at 27'-3". Gigapower LLC Fiber Optic Com at 22'-5": Attach | 41.4142 | -75.633 | APP_306524
P:0154 | 54 | 58064N46153 | MR Resolved | Low Power: Drip_loop at 22'-11". Secondary at 25'-6": Raise 6" to 26'-0". Service at 25'-3": Raise 6" to 25'-9". Cellco Partnership D/b/a Verizon Wireless Riser at 23'-5": Extend 14" to 24'-7". Cellco Partnership D/b/a Verizon Wireless Drip Loop at 22'-11": Raise 14" to 24'-1". Gigapower LLC Fiber Optic Com at 20'-8": Attach | 41.414 | -75.6327 | APP_306524
P:0151 | 55 | 58077N46145 | MR Resolved | Low Power: Drip_loop at 24'-9". Gigapower LLC Fiber Optic Com at 21'-5": Attach. North Penn Long Distance Corporation Fiber Optic Com at 21'-5": Lower 12" to 20'-5". Comcast - Duryea CATV Com at 20'-5": Lower 12" to 19'-5" | 41.4138 | -75.6322 | APP_306524
P:0152 | 56 | 58086N46140 | No MR | Low Power: Drip_loop at 30'-0". Gigapower LLC Fiber Optic Com at 22'-4": Attach | 41.4137 | -75.6319 | APP_306524
P:0149 | 57 | 58095N46134 | MR Resolved | Low Power: Street_light at 22'-3". Dunmore Boro, Lackawanna Co. Street Light at 24'-1": Raise 6" to 24'-7", Ground Bracket. Dunmore Boro, Lackawanna Co. Drip Loop at 23'-7": Raise 6" to 24'-1". Gigapower LLC Fiber Optic Com at 22'-2": Attach | 41.4135 | -75.6316 | APP_306524
P:0150 | 58 | 58104N46128 | MR Resolved | Low Power: Secondary at 25'-9". Gigapower LLC Fiber Optic Com at 21'-1": Attach. Bond to ground wire | 41.4133 | -75.6313 | APP_306524
P:0147 | 59 | 58116N46122 | MR Resolved | Low Power: Secondary at 24'-7". Pole Top: Replace 35' class 4 pole with 40' class 3 pole. Primary at 27'-4": Raise 75" to 33'-7". Gigapower LLC Fiber Optic Com at 25'-0": Attach. Secondary at 24'-7": Raise 77" to 31'-0". North Penn Long Distance Corporation Fiber Optic Com at 21'-3": Raise 33" to 24'-0", Transfer to new pole at 24'-0". Comcast - Duryea CATV Com at 20'-5": Raise 31" to 23'-0", Transfer to new pole at 23'-0". Verizon Pennsylvania Inc. Telco Com at 19'-3": Raise 33" to 22'-0", Transfer to new pole at 22'-0" | 41.4131 | -75.6309 | APP_306524
P:0148 | 60 | 58123N46118 | MR Resolved | Low Power: Street_light at 22'-1". Secondary at 25'-9": Raise 12" to 26'-9". Secondary at 25'-3": Raise 12" to 26'-3". Secondary at 25'-3": Raise 12" to 26'-3". PPL Company Drip Loop at 24'-11": Raise 12" to 25'-11". Dunmore Boro, Lackawanna Co. Street Light at 24'-6": Raise 8" to 25'-2", Ground Bracket. Dunmore Boro, Lackawanna Co. Drip Loop at 23'-8": Raise 8" to 24'-4". Dunmore Boro, Lackawanna Co. Alarm Cable at 23'-0": Remove. Gigapower LLC Fiber Optic Com at 22'-5": Attach. Gigapower LLC Fiber Optic Com at 22'-5": Attach. Dunmore Boro, Lackawanna Co. Alarm Cable at 22'-5": Remove. Gigapower LLC Guy at 22'-5": Attach | 41.413 | -75.6306 | APP_306524
P:0207 | 61 | 58126N46116 | MR Resolved | Low Power: Drip_loop at 23'-10". Secondary at 24'-5": Install ground rod and bond neutral to ground. Gigapower LLC Down Guy at 21'-4": Attach. Place on replaced Verizon Pennsylvania Inc. anchor rod with 25' lead at 98° and attach 6.6M (1/4" EHS) (7/0) guy. Gigapower LLC Guy at 21'-4": Attach. Bond to ground wire. North Penn Long Distance Corporation Fiber Optic Com at 20'-10": Bond to ground wire. North Penn Long Distance Corporation Fiber Optic Com at 20'-10": Bond to ground wire. North Penn Long Distance Corporation Down Guy at 20'-10": Transfer North Penn Long Distance Corporation Down Guy from anchor at 25' lead at 98° to the replaced Verizon Pennsylvania Inc. anchor at 25' lead. North Penn Long Distance Corporation Guy at 20'-10": Bond to ground wire. Verizon Pennsylvania Inc. Down Guy at 19'-11": Transfer Verizon Pennsylvania Inc. Down Guy from anchor at 25' lead at 98° to the replaced Verizon Pennsylvania Inc. anchor at 25' lead | 41.413 | -75.6305 | APP_306524
P:0113 | 62 | 58116N46105 | MR Resolved | Low Power: Secondary at 26'-9". Gigapower LLC Fiber Optic Com at 23'-9": Attach. Bond to ground wire. Dunmore Boro, Lackawanna Co. Alarm Cable at 22'-6": Remove | 41.4127 | -75.6309 | APP_306524
P:0066 | 63 | 57992N46165 | MR Resolved | Low Power: Vertical_banner at 16'-5". Secondary at 26'-11": Raise 6" to 27'-5". Neutral at 26'-11": Raise 6" to 27'-5", Install ground rod and bond neutral to ground. PPL Company Drip Loop at 26'-6": Raise 6" to 27'-0". Dunmore Boro, Lackawanna Co. Street Light at 25'-7": Ground Bracket. Dunmore Boro, Lackawanna Co. Drip Loop at 24'-10": Raise 6" to 25'-4", Guard drip loop. Gigapower LLC Fiber Optic Com at 24'-5": Attach. Bond to ground wire. Gigapower LLC Fiber Optic Com at 24'-5": Attach. Bond to ground wire. North Penn Long Distance Corporation Guy at 11'-1": Raise 70" to 16'-11" | 41.4145 | -75.6354 | APP_306524
P:0065 | 64 | 57999N46177 | MR Resolved | Low Power: Vertical_banner at 15'-2". Loop Internet Fiber Optic Com at 22'-0": Lower 14" to 20'-10". Loop Internet Guy at 22'-0": Lower 14" to 20'-10". Gigapower LLC Fiber Optic Com at 21'-10": Attach. Bond to ground wire. North Penn Long Distance Corporation Strand at 21'-0": Lower 14" to 19'-10". Comcast - Duryea CATV Com at 20'-0": Lower 14" to 18'-10". CTSI, LLC, Dba Frontier Communications Fiber Optic Com at 19'-0": Lower 14" to 17'-10". Verizon Pennsylvania Inc. Telco Com at 19'-0": Lower 14" to 17'-10" | 41.4148 | -75.6351 | APP_306524
P:0116 | 65 | 58001N46160 | MR Resolved | Low Power: Secondary at 23'-10". Secondary at 23'-10": Raise 6" to 24'-4". Gigapower LLC Fiber Optic Com at 21'-7": Attach. Bond to ground wire. Gigapower LLC Fiber Optic Com at 21'-7": Attach. Bond to ground wire. Gigapower LLC Down Guy at 21'-7": Attach. Place on replaced Verizon Pennsylvania Inc. anchor rod with 12' lead at 303° and attach 6.6M (1/4" EHS) (7/0) guy. Comcast - Duryea Down Guy at 19'-10": Transfer Comcast - Duryea Down Guy from anchor at 12' lead at 303° to the replaced Verizon Pennsylvania Inc. anchor at 12' lead. Verizon Pennsylvania Inc. Down Guy at 17'-8": Transfer Verizon Pennsylvania Inc. Down Guy from anchor at 12' lead at 303° to the replaced Verizon Pennsylvania Inc. anchor at 12' lead | 41.4144 | -75.635 | APP_306524
P:0115 | 66 | 58011N46154 | MR Resolved | Low Power: Street_light at 22'-5". Dunmore Boro, Lackawanna Co. Street Light at 22'-5": Ground Bracket. Gigapower LLC Fiber Optic Com at 21'-9": Attach | 41.4142 | -75.6347 | APP_306524
P:0093 | 67 | 58020N46148 | MR Resolved | Low Power: Drip_loop at 22'-7". Dunmore Boro, Lackawanna Co. Street Light at 23'-0": Ground Bracket. Dunmore Boro, Lackawanna Co. Drip Loop at 22'-7": Guard drip loop. North Penn Long Distance Corporation Strand at 21'-11": Lower 12" to 20'-11". North Penn Long Distance Corporation Strand at 21'-11": Lower 12" to 20'-11". North Penn Long Distance Corporation Strand at 21'-11": Lower 12" to 20'-11". Gigapower LLC Fiber Optic Com at 21'-11": Attach. Gigapower LLC Fiber Optic Com at 21'-11": Attach. Gigapower LLC Fiber Optic Com at 21'-11": Attach. Comcast - Duryea CATV Com at 20'-11": Lower 12" to 19'-11". Comcast - Duryea CATV Com at 20'-11": Lower 12" to 19'-11". Comcast - Duryea CATV Com at 20'-11": Lower 12" to 19'-11". CTSI, LLC, Dba Frontier Communications Telco Com at 19'-11": Lower 12" to 18'-11". Verizon Pennsylvania Inc. Telco Com at 19'-2": Lower 12" to 18'-2". Verizon Pennsylvania Inc. Guy at 19'-2": Lower 12" to 18'-2". Verizon Pennsylvania Inc. Telco Com at 18'-11": Lower 12" to 17'-11" | 41.414 | -75.6343 | APP_306524
P:0162 | 68 | 58026N46158 | MR Resolved | Low Power: Drip_loop at 22'-9". Dunmore Boro, Lackawanna Co. Street Light at 23'-0": Ground Bracket. Dunmore Boro, Lackawanna Co. Drip Loop at 22'-9": Guard drip loop. Gigapower LLC Fiber Optic Com at 22'-6": Attach. Bond to ground wire. North Penn Long Distance Corporation Strand at 21'-0": Raise 6" to 21'-6". North Penn Long Distance Corporation Strand at 21'-0": Raise 6" to 21'-6". North Penn Long Distance Corporation Guy at 21'-0": Raise 6" to 21'-6" | 41.4142 | -75.6341 | APP_306524
P:0161 | 69 | 58032N46168 | MR Resolved | Low Power: Drip_loop at 23'-8". Dunmore Boro, Lackawanna Co. Street Light at 23'-11": Ground Bracket. Gigapower LLC Fiber Optic Com at 22'-8": Attach | 41.4145 | -75.6339 | APP_306524
P:0094 | 70 | 58030N46143 | MR Resolved | Low Power: Drip_loop at 23'-5". Pole Top: Replace 35' class 3 pole with 45' class 3 pole. PPL Company Cutout Arrestor at 27'-11": Raise 118" to 37'-9". Primary at 27'-11": Raise 118" to 37'-9". Primary at 27'-11": Raise 118" to 37'-9". Secondary at 24'-9": Raise 69" to 30'-6". Secondary at 24'-5": Raise 67" to 30'-0". PPL Company Drip Loop at 23'-5": Raise 73" to 29'-6". Gigapower LLC Fiber Optic Com at 22'-0": Attach. North Penn Long Distance Corporation Strand at 19'-10": Raise 14" to 21'-0", Transfer to new pole at 21'-0". Comcast - Duryea CATV Com at 19'-0": Raise 12" to 20'-0", Transfer to new pole at 20'-0". CTSI, LLC, Dba Frontier Communications Telco Com at 18'-0": Raise 12" to 19'-0", Transfer to new pole at 19'-0". Verizon Pennsylvania Inc. Telco Com at 17'-5": Raise 7" to 18'-0", Transfer to new pole at 18'-0" | 41.4138 | -75.634 | APP_306524
P:0091 | 71 | 58038N46137 | MR Resolved | Low Power: Drip_loop at 27'-3". Gigapower LLC Fiber Optic Com at 19'-7": Attach. Bond to ground wire | 41.4137 | -75.6337 | APP_306524
P:0063 | 72 | 57987N46157 | MR Resolved | Low Power: Vertical_banner at 15'-3". Power Guy at 30'-0": Attach. Dunmore Boro, Lackawanna Co. Street Light at 24'-9": Raise 6" to 25'-3", Ground Bracket. Dunmore Boro, Lackawanna Co. Drip Loop at 24'-1": Raise 6" to 24'-7". Gigapower LLC Fiber Optic Com at 23'-0": Attach. Gigapower LLC Guy at 23'-0": Attach. Comcast - Duryea Guy at 22'-0": Attach | 41.4142 | -75.6356 | APP_306524
P:0064 | 73 | 57989N46152 | No MR | Low Power: Secondary at 25'-8". Gigapower LLC Fiber Optic Com at 19'-6": Attach | 41.4141 | -75.6355 | APP_306524
P:0061 | 74 | 57992N46143 | No MR | Low Power: Secondary at 28'-10". Gigapower LLC Fiber Optic Com at 17'-6": Attach. Gigapower LLC Guy at 17'-6": Attach | 41.4138 | -75.6353 | APP_306524
P:0062 | 75 | 57996N46132 | No MR | Low Power: Bundled Primary at 27'-0". Gigapower LLC Fiber Optic Com at 18'-11": Attach. Gigapower LLC Guy at 18'-11": Attach | 41.4135 | -75.6351 | APP_306524
P:0059 | 76 | 57993N46129 | MR Resolved | Low Power: Drip_loop at 23'-4". PPL Company Down Guy at 24'-4": Transfer PPL Company Down Guy from anchor at 10' lead at 253° to the replaced PPL Company anchor at 10' lead. Gigapower LLC Down Guy at 18'-9": Attach. Place on replaced PPL Company anchor rod with 10' lead at 253° and attach 6.6M (1/4" EHS) (7/0) guy. Gigapower LLC Guy at 18'-9": Attach. Comcast - Duryea Down Guy at 16'-10": Transfer Comcast - Duryea Down Guy from anchor at 10' lead at 253° to the replaced PPL Company anchor at 10' lead | 41.4135 | -75.6352 | APP_306524
P:0124 | 77 | 58005N46122 | MR Resolved | Gigapower LLC Fiber Optic Com at 21'-11": Attach. Install new cable on a 3' fiberglass arm to reduce the break angle. Gigapower LLC Fiber Optic Com at 21'-11": Attach. Power Guy at 17'-2": Lower 21" to 15'-5". Gigapower LLC Guy at 14'-11": Attach | 41.4133 | -75.6349 | APP_306524
P:0123 | 78 | 58004N46119 | No MR | Low Power: Drip_loop at 25'-6". Gigapower LLC Fiber Optic Com at 20'-0": Attach | 41.4132 | -75.6348 | APP_306524
P:0096 | 79 | 58010N46130 | No MR | Low Power: Drip_loop at 25'-6". Gigapower LLC Fiber Optic Com at 20'-8": Attach. Gigapower LLC Fiber Optic Com at 20'-8": Attach. Gigapower LLC Guy at 20'-8": Attach | 41.4135 | -75.6347 | APP_306524
P:0095 | 80 | 58013N46135 | No MR | Low Power: Secondary at 25'-2". Gigapower LLC Fiber Optic Com at 21'-4": Attach | 41.4136 | -75.6346 | APP_306524
P:0098 | 81 | 58015N46139 | MR Resolved | Low Power: Secondary at 28'-10". North Penn Long Distance Corporation Strand at 21'-11": Lower 12" to 20'-11". Gigapower LLC Fiber Optic Com at 21'-11": Attach. Comcast - Duryea CATV Com at 20'-11": Lower 12" to 19'-11" | 41.4138 | -75.6345 | APP_306524
P:0126 | 82 | 58014N46116 | No MR | Low Power: Secondary at 24'-8". Gigapower LLC Fiber Optic Com at 18'-8": Attach | 41.4131 | -75.6346 | APP_306524
P:0125 | 83 | 58023N46111 | No MR | Low Power: Secondary at 27'-10". Gigapower LLC Fiber Optic Com at 21'-10": Attach | 41.413 | -75.6343 | APP_306524
P:0182 | 028.A | 12 | No MR | Gigapower LLC Fiber Optic Com at 19'-7": Attach | 41.416 | -75.6356 | APP_306524
P:0144 | 032.A | 22 | No MR | Gigapower LLC Fiber Optic Com at 19'-0": Attach | 41.4156 | -75.6348 | APP_306524
P:0250 | 76.1 | 12 | No MR | Gigapower LLC Guy at 17'-7": Attach | 41.4138 | -75.6354 | APP_306524
P:0180 | 036.A | 31 | No MR | Gigapower LLC Fiber Optic Com at 19'-7": Attach | 41.4152 | -75.6341 | APP_306524
P:0163 | 050.A | 52 | No MR | Gigapower LLC Fiber Optic Com at 23'-10": Attach | 41.4149 | -75.6335 | APP_306524
P:0203 | 38.1 | NT; 51 | MR Resolved | Low Power: Street_light at 22'-4". Pole Top: Replace 35' class 5 pole with 35' class 2 pole. Street Light Feed at 27'-8": Lower 2" to 27'-6". Neutral at 27'-0": Lower 3" to 26'-9", Attach. PPL Company Down Guy at 26'-2": Lower 3" to 25'-11", Attach. Place on existing anchor rod with 5' lead at 31° and attach 10M (3/8" UG) (7/0) guy. Dunmore Boro, Lackawanna Co. Street Light at 24'-3": Lower 4" to 23'-11", Ground Bracket. Transfer to new pole at 22'-0". Dunmore Boro, Lackawanna Co. Drip Loop at 23'-4": Lower 4" to 23'-0", Transfer to new pole at 23'-0". Gigapower LLC Strand at 20'-0": Attach. Gigapower LLC Down Guy at 20'-0": Attach. Place on existing anchor rod with 5' lead at 31° and attach 6.6M (1/4" EHS) (7/0) guy. Attach to existing sidewalk brace at 9'-2". Verizon Pennsylvania Inc. Strand at 19'-4": Lower 4" to 19'-0", Transfer to new pole at 19'-0". Verizon Pennsylvania Inc. Down Guy at 19'-4": Lower 4" to 19'-0", Transfer to new pole at 19'-0". Verizon Pennsylvania Inc. Sidewalk Brace at 9'-2": Transfer to new pole at 9'-2" | 41.4153 | -75.6332 | APP_306524
P:0231 | 77.1 | 58000N46120 | No MR | Low Power: Drip_loop at 26'-0". | 41.4133 | -75.6351 | APP_306524
P:0252 | 001.A | 11 | MR Resolved | Gigapower LLC Fiber Optic Com at 19'-3": Attach. Gigapower LLC Fiber Optic Com at 19'-3": Attach. Gigapower LLC Down Guy at 19'-3": Attach. Place on replaced Verizon Pennsylvania Inc. anchor rod with 13' lead at 301° and attach 6.6M (1/4" EHS) (7/0) guy. North Penn Long Distance Corporation Down Guy at 18'-3": Transfer North Penn Long Distance Corporation Down Guy from anchor at 13' lead at 301° to the replaced Verizon Pennsylvania Inc. anchor at 13' lead. Verizon Pennsylvania Inc. Down Guy at 16'-10": Transfer Verizon Pennsylvania Inc. Down Guy from anchor at 13' lead at 301° to the replaced Verizon Pennsylvania Inc. anchor at 13' lead | 41.417 | -75.6353 | APP_306524
P:0193 | 30 | 58008N46234 | MR Resolved | Low Power: Secondary at 28'-9". Secondary at 28'-9": Raise 24" to 30'-9". Gigapower LLC Fiber Optic Com at 21'-4": Attach. North Penn Long Distance Corporation Strand at 21'-0": Lower 8" to 20'-4". Comcast - Duryea CATV Com at 20'-0": Lower 8" to 19'-4" | 41.4163 | -75.6347 | APP_306524
P:0251 | 84 | 57974N46159 | No MR | Power Guy at 19'-6": Attach. Gigapower LLC Guy at 18'-6": Attach. Comcast - Duryea Guy at 18'-0": Attach | 41.4143 | -75.6359 | APP_306524