## MakeReadySummary
Pole_ID | SCID | Pole_tag | Make_Ready_State | Make_ready_notes | Latitude | Longitude | jobname
P:0089 | 1 | 58086N46413 | No MR | Low Power: Drip_loop at 26'-7". Gigapower LLC Fiber Optic Com at 23'-2": Attach. Bond to ground wire. Gigapower LLC Guy at 23'-2": Attach. Bond to ground wire | 41.4212 | -75.6316 | APP_306539
P:0037 | 2 | 58079N46418 | MR Resolved | Low Power: Drip_loop at 24'-2". Secondary at 25'-3": Install ground rod and bond neutral to ground. Gigapower LLC Fiber Optic Com at 21'-2": Attach. Bond to ground wire. Gigapower LLC Fiber Optic Com at 21'-2": Attach. Bond to ground wire | 41.4213 | -75.6319 | APP_306539
P:0036 | 3 | 58068N46426 | MR Resolved | Low Power: Drip_loop at 22'-8". Pole Top: Replace 40' class 4 pole with 45' class 2 pole. Primary at 33'-6": Raise 56" to 38'-2". Primary at 32'-6": Raise 56" to 37'-2". PPL Company Cutout Arrestor at 32'-0": Raise 56" to 36'-8". Secondary at 26'-7": Raise 23" to 28'-6". Secondary at 26'-3": Raise 27" to 28'-6". Secondary at 25'-11": Raise 25" to 28'-0". Dunmore Boro, Lackawanna Co. Street Light at 24'-4": Raise 17" to 25'-9", Transfer to new pole at 23'-6". Gigapower LLC Fiber Optic Com at 23'-0": Attach. Gigapower LLC Fiber Optic Com at 23'-0": Attach. Dunmore Boro, Lackawanna Co. Drip Loop at 22'-8": Raise 16" to 24'-0", Transfer to new pole at 23'-0". North Penn Long Distance Corporation Fiber Optic Com at 21'-3": Raise 9" to 22'-0", Transfer to new pole at 21'-0". North Penn Long Distance Corporation Fiber Optic Com at 21'-3": Raise 9" to 22'-0", Transfer to new pole at 21'-0". CTSI, LLC, Dba Frontier Communications Telco Com at 20'-3": Raise 9" to 21'-0", Transfer to new pole at 20'-0". Comcast - Duryea CATV Com at 19'-3": Raise 9" to 20'-0", Transfer to new pole at 19'-0". Verizon Pennsylvania Inc. Telco Com at 18'-4": Raise 8" to 19'-0", Transfer to new pole at 18'-0". Verizon Pennsylvania Inc. Telco Com at 18'-2": Raise 10" to 19'-0", Transfer to new pole at 18'-0". Power Guy at 12'-7": Raise 35" to 15'-6" | 41.4215 | -75.6322 | APP_306539
P:0039 | 4 | 58059N46432 | MR Resolved | Low Power: Secondary at 25'-11". Gigapower LLC Fiber Optic Com at 23'-4": Attach. Bond to ground wire. North Penn Long Distance Corporation Fiber Optic Com at 23'-0": Lower 8" to 22'-4". CTSI, LLC, Dba Frontier Communications Telco Com at 22'-0": Lower 8" to 21'-4". Comcast - Duryea CATV Com at 20'-8": Lower 4" to 20'-4" | 41.4217 | -75.6326 | APP_306539
P:0098 | 5 | 58071N46436 | No MR | Low Power: Secondary at 27'-3". Gigapower LLC Fiber Optic Com at 20'-11": Attach | 41.4218 | -75.6321 | APP_306539
P:0097 | 6 | 58049N46439 | MR Resolved | Low Power: Secondary at 23'-5". Secondary at 23'-5": Raise 24" to 25'-5". Gigapower LLC Fiber Optic Com at 21'-0": Attach | 41.4219 | -75.633 | APP_306539
P:0096 | 7 | 58041N46445 | MR Resolved | Low Power: Street_light at 20'-8". Pole Top: Replace 35' class 4 pole with 40' class 3 pole. Primary at 28'-8": Raise 57" to 33'-5". Secondary at 24'-2": Raise 16" to 25'-6". Dunmore Boro, Lackawanna Co. Street Light at 22'-2": Raise 28" to 24'-6", Transfer to new pole at 23'-0". Gigapower LLC Fiber Optic Com at 22'-0": Attach. Dunmore Boro, Lackawanna Co. Drip Loop at 21'-4": Raise 28" to 23'-8", Transfer to new pole at 23'-8". North Penn Long Distance Corporation Fiber Optic Com at 19'-10": Raise 14" to 21'-0", Transfer to new pole at 21'-0". CTSI, LLC, Dba Frontier Communications Telco Com at 18'-10": Raise 14" to 20'-0", Transfer to new pole at 20'-0". Comcast - Duryea CATV Com at 17'-8": Raise 16" to 19'-0", Transfer to new pole at 19'-0". Verizon Pennsylvania Inc. Telco Com at 16'-3": Raise 21" to 18'-0", Transfer to new pole at 18'-0" | 41.4221 | -75.6333 | APP_306539
P:0038 | 8 | 58033N46451 | MR Resolved | Low Power: Transformer at 23'-8". Pole Top: Replace 40' class 4 pole with 45' class 3 pole. Primary at 30'-9": Raise 84" to 37'-9". PPL Company Cutout Arrestor at 29'-4": Raise 68" to 35'-0". PPL Company Transformer at 25'-9": Raise 40" to 29'-1". Secondary at 24'-9": Raise 15" to 26'-0". PPL Company Drip Loop at 24'-7": Raise 11" to 25'-6". Gigapower LLC Fiber Optic Com at 22'-0": Attach. Bond to ground wire. North Penn Long Distance Corporation Fiber Optic Com at 19'-6": Raise 18" to 21'-0", Transfer to new pole at 21'-0". CTSI, LLC, Dba Frontier Communications Telco Com at 18'-6": Raise 18" to 20'-0", Transfer to new pole at 20'-0". Comcast - Duryea CATV Com at 17'-6": Raise 18" to 19'-0", Transfer to new pole at 19'-0". Verizon Pennsylvania Inc. Telco Com at 16'-6": Raise 18" to 18'-0", Transfer to new pole at 18'-0" | 41.4222 | -75.6335 | APP_306539
P:0103 | 9 | 58022N46458 | MR Resolved | Low Power: Secondary at 26'-9". Pole Top: Replace 40' class 3 pole with 45' class 3 pole. Primary at 31'-6": Raise 75" to 37'-9". Secondary at 26'-9": Lower 15" to 25'-6". Secondary at 26'-9": Lower 9" to 26'-0". Gigapower LLC Fiber Optic Com at 22'-0": Attach. North Penn Long Distance Corporation Fiber Optic Com at 19'-5": Raise 19" to 21'-0", Transfer to new pole at 21'-0". CTSI, LLC, Dba Frontier Communications Telco Com at 18'-5": Raise 19" to 20'-0", Transfer to new pole at 20'-0". Comcast - Duryea CATV Com at 17'-7": Raise 17" to 19'-0", Transfer to new pole at 19'-0". Verizon Pennsylvania Inc. Telco Com at 16'-6": Raise 18" to 18'-0", Transfer to new pole at 18'-0" | 41.4225 | -75.6339 | APP_306539
P:0026 | 10 | 58013N46464 | MR Resolved | Low Power: Drip_loop at 22'-10". Pole Top: Replace 40' class 4 pole with 45' class 1 pole. Primary at 31'-8": Raise 76" to 38'-0". Primary at 31'-5": Raise 76" to 37'-9". Power Guy at 30'-6": Raise 76" to 36'-10". Secondary at 26'-5": Raise 1" to 26'-6". Secondary at 26'-4": Lower 4" to 26'-0". Dunmore Boro, Lackawanna Co. Street Light at 24'-11": Raise 5" to 25'-4". Dunmore Boro, Lackawanna Co. Drip Loop at 22'-10": Raise 2" to 23'-0", Guard drip loop. Gigapower LLC Fiber Optic Com at 22'-0": Attach. Gigapower LLC Fiber Optic Com at 22'-0": Attach. North Penn Long Distance Corporation Fiber Optic Com at 21'-6": Lower 6" to 21'-0", Transfer to new pole at 21'-0". North Penn Long Distance Corporation Fiber Optic Com at 21'-6": Lower 6" to 21'-0", Transfer to new pole at 21'-0". CTSI, LLC, Dba Frontier Communications Telco Com at 20'-6": Lower 6" to 20'-0", Transfer to new pole at 20'-0". Comcast - Duryea CATV Com at 19'-6": Lower 6" to 19'-0", Transfer to new pole at 19'-0". Comcast - Duryea CATV Com at 19'-6": Lower 6" to 19'-0", Transfer to new pole at 19'-0". Verizon Pennsylvania Inc. Telco Com at 17'-11": Raise 1" to 18'-0", Replace 40' class 4 pole with 40' class 3 pole. Transfer to new pole at 18'-0". Verizon Pennsylvania Inc. Telco Com at 17'-11": Raise 1" to 18'-0", Replace 40' class 4 pole with 40' class 3 pole. Transfer to new pole at 18'-0" | 41.4226 | -75.6342 | APP_306539
P:0027 | 11 | 58018N46472 | MR Resolved | Low Power: Drip_loop at 24'-1". Gigapower LLC Fiber Optic Com at 20'-8": Attach. North Penn Long Distance Corporation Fiber Optic Com at 20'-8": Lower 12" to 19'-8". Comcast - Duryea Strand at 19'-8": Lower 12" to 18'-8". Verizon Pennsylvania Inc. Telco Com at 18'-0": Lower 4" to 17'-8" | 41.4228 | -75.6341 | APP_306539
P:0024 | 12 | 58004N46471 | MR Resolved | Low Power: Drip_loop at 23'-7". Secondary at 25'-5": Raise 36" to 28'-5", Install ground rod and bond neutral to ground. Power Guy at 24'-8": Raise 36" to 27'-8". PPL Company Drip Loop at 23'-7": Raise 36" to 26'-7". Gigapower LLC Fiber Optic Com at 20'-6": Attach. Bond to ground wire | 41.4228 | -75.6346 | APP_306539
P:0021 | 13 | 57994N46477 | No MR | Low Power: Drip_loop at 24'-8". Gigapower LLC Fiber Optic Com at 21'-1": Attach | 41.423 | -75.635 | APP_306539
P:0023 | 14 | 57987N46483 | No MR | Low Power: Drip_loop at 30'-10". Gigapower LLC Fiber Optic Com at 27'-5": Attach | 41.4232 | -75.6352 | APP_306539
P:0019 | 15 | 57982N46483 | MR Resolved | Low Power: Drip_loop at 21'-11". ION Holdco LLC Fiber Optic Com at 21'-9": Lower 16" to 20'-5". Gigapower LLC Fiber Optic Com at 21'-5": Attach. ZitoMedia / Zito West Holding, LLC Fiber Optic Com at 20'-11": Lower 18" to 19'-5". Comcast - Duryea CATV Com at 19'-10": Lower 17" to 18'-5" | 41.4232 | -75.6354 | APP_306539
P:0022 | 16 | 57986N46484 | No MR | Low Power: Neutral at 27'-0". Gigapower LLC Fiber Optic Com at 22'-2": Attach | 41.4233 | -75.6353 | APP_306539
P:0040 | 17 | 57982N46488 | No MR | Low Power: Secondary at 26'-1". Gigapower LLC Fiber Optic Com at 19'-5": Attach | 41.4233 | -75.6354 | APP_306539
P:0041 | 18 | 57975N46492 | MR Resolved | Low Power: Secondary at 24'-3". Pole Top: Replace 40' class 4 pole with 45' class 3 pole. Primary at 33'-2": Raise 58" to 38'-0". Primary at 32'-5": Raise 58" to 37'-3". Primary at 32'-5": Raise 58" to 37'-3". PPL Company Cutout Arrestor at 29'-3": Raise 58" to 34'-1". PPL Company Transformer at 26'-7": Raise 58" to 31'-5". Secondary at 24'-3": Raise 33" to 27'-0". Gigapower LLC Fiber Optic Com at 23'-0": Attach. Bond to ground wire. North Penn Long Distance Corporation Fiber Optic Com at 21'-6": Raise 6" to 22'-0", Transfer to new pole at 22'-0". CTSI, LLC, Dba Frontier Communications Telco Com at 20'-6": Raise 6" to 21'-0", Transfer to new pole at 21'-0". Comcast - Duryea CATV Com at 19'-2": Raise 10" to 20'-0", Transfer to new pole at 20'-0". Comcast - Duryea Guy at 19'-2": Raise 10" to 20'-0", Transfer to new pole at 20'-0". Verizon Pennsylvania Inc. Telco Com at 17'-10": Raise 14" to 19'-0", Transfer to new pole at 19'-0" | 41.4235 | -75.6357 | APP_306539
P:0043 | 19 | 57964N46499 | MR Resolved | Low Power: Vertical_banner at 15'-0". Primary at 36'-10": Replace POB's with VSB's. Primary at 36'-9": Replace POB's with VSB's. Gigapower LLC Fiber Optic Com at 23'-1": Attach | 41.4237 | -75.6361 | APP_306539
P:0042 | 20 | 57955N46504 | MR Resolved | Low Power: Vertical_banner at 14'-11". Secondary at 27'-1": Raise 16" to 28'-5". Secondary at 26'-7": Raise 16" to 27'-11". Secondary at 25'-11": Raise 16" to 27'-3". Dunmore Boro, Lackawanna Co. Street Light at 24'-9": Raise 15" to 26'-0". Gigapower LLC Fiber Optic Com at 23'-1": Attach. Dunmore Boro, Lackawanna Co. Drip Loop at 22'-10": Raise 15" to 24'-1" | 41.4238 | -75.6364 | APP_306539
P:0063 | 22 | 57945N46510 | MR Resolved | Low Power: Secondary at 29'-3". North Penn Long Distance Corporation Fiber Optic Com at 23'-11": Lower 39" to 20'-8". ZitoMedia / Zito West Holding, LLC Fiber Optic Com at 22'-11": Lower 39" to 19'-8". CTSI, LLC, Dba Frontier Communications Telco Com at 22'-0": Lower 40" to 18'-8". Gigapower LLC Fiber Optic Com at 21'-8": Attach. Bond to ground wire. Comcast - Duryea Strand at 20'-5": Lower 33" to 17'-8". Comcast - Duryea CATV Com at 20'-5": Lower 33" to 17'-8" | 41.424 | -75.6367 | APP_306539
P:0094 | 23 | 57934N46517 | MR Resolved | Low Power: Secondary at 26'-4". Secondary at 26'-4": Raise 12" to 27'-4". Gigapower LLC Fiber Optic Com at 22'-0": Attach. Bond to ground wire | 41.4242 | -75.6371 | APP_306539
P:0107 | 24 | 57948N46494 | No MR | Low Power: Secondary at 28'-3". Gigapower LLC Fiber Optic Com at 22'-4": Attach | 41.4235 | -75.6366 | APP_306539
P:0049 | 25 | 57942N46483 | No MR | Low Power: Secondary at 25'-10". Gigapower LLC Fiber Optic Com at 21'-8": Attach | 41.4232 | -75.6369 | APP_306539
P:0048 | 26 | 57937N46475 | No MR | Low Power: Secondary at 27'-2". Gigapower LLC Fiber Optic Com at 21'-6": Attach | 41.423 | -75.6371 | APP_306539
P:0101 | 27 | 57932N46467 | No MR | Low Power: Secondary at 25'-4". Gigapower LLC Fiber Optic Com at 20'-3": Attach | 41.4228 | -75.6373 | APP_306539
P:0047 | 28 | 57926N46457 | MR Resolved | Low Power: Drip_loop at 25'-9". Gigapower LLC Fiber Optic Com at 22'-4": Attach. Bond to ground wire | 41.4225 | -75.6375 | APP_306539
P:0046 | 29 | 57920N46447 | MR Resolved | Low Power: Secondary at 27'-3". PPL Company Down Guy at 23'-6": Raise 12" to 24'-6". Gigapower LLC Fiber Optic Com at 23'-6": Attach | 41.4223 | -75.6378 | APP_306539
P:0059 | 30 | 57921N46441 | MR Resolved | Low Power: Vertical_banner at 14'-10". Dunmore Boro, Lackawanna Co. Street Light at 26'-5": Raise 6" to 26'-11". Dunmore Boro, Lackawanna Co. Drip Loop at 25'-3": Raise 6" to 25'-9". Gigapower LLC Fiber Optic Com at 24'-9": Attach. Gigapower LLC Guy at 24'-9": Attach | 41.4221 | -75.6377 | APP_306539
P:0058 | 31 | 57915N46431 | No MR | Low Power: Secondary at 26'-1". Gigapower LLC Fiber Optic Com at 20'-4": Attach | 41.4218 | -75.6379 | APP_306539
P:0057 | 32 | 57907N46418 | MR Resolved | Low Power: Secondary at 27'-4". Secondary at 27'-4": Install ground rod and bond neutral to ground. Gigapower LLC Fiber Optic Com at 22'-3": Attach | 41.4215 | -75.6382 | APP_306539
P:0056 | 33 | 57901N46409 | MR Resolved | Low Power: Drip_loop at 26'-1". Gigapower LLC Fiber Optic Com at 23'-2": Attach. Bond to ground wire. North Penn Long Distance Corporation Fiber Optic Com at 22'-9": Lower 7" to 22'-2". CTSI, LLC, Dba Frontier Communications Fiber Optic Com at 21'-9": Lower 7" to 21'-2". Comcast - Duryea CATV Com at 20'-9": Lower 7" to 20'-2". Verizon Pennsylvania Inc. Telco Com at 19'-6": Lower 4" to 19'-2" | 41.4213 | -75.6384 | APP_306539
P:0055 | 34 | 57896N46399 | MR Resolved | Low Power: Secondary at 27'-6". Gigapower LLC Fiber Optic Com at 23'-0": Attach. North Penn Long Distance Corporation Fiber Optic Com at 20'-4": Raise 20" to 22'-0". CTSI, LLC, Dba Frontier Communications Fiber Optic Com at 19'-4": Raise 20" to 21'-0". Comcast - Duryea CATV Com at 17'-5": Raise 31" to 20'-0". Verizon Pennsylvania Inc. Telco Com at 16'-4": Raise 32" to 19'-0" | 41.421 | -75.6386 | APP_306539
P:0053 | 35 | 57893N46394 | MR Resolved | Low Power: Drip_loop at 23'-7". Secondary at 24'-4": Raise 12" to 25'-4". PPL Company Drip Loop at 23'-7": Raise 12" to 24'-7". Gigapower LLC Fiber Optic Com at 20'-6": Attach. Gigapower LLC Fiber Optic Com at 20'-6": Attach | 41.4209 | -75.6388 | APP_306539
P:0088 | 36 | 57889N46388 | MR Resolved | Low Power: Secondary at 28'-2". Gigapower LLC Fiber Optic Com at 18'-6": Attach. Gigapower LLC Down Guy at 18'-6": Attach and install new anchor. Place on new Gigapower LLC anchor rod with 15' lead at 213° and attach 6.6M (1/4" EHS) (7/0) guy | 41.4207 | -75.6389 | APP_306539
P:0087 | 37 | 57888N46385 | No MR |  | 41.4207 | -75.6389 | APP_306539
P:0052 | 38 | 57884N46388 | MR Resolved | Low Power: Vertical_banner at 14'-10". Dunmore Boro, Lackawanna Co. Street Light at 26'-4": Raise 12" to 27'-4". Gigapower LLC Fiber Optic Com at 24'-8": Attach. Gigapower LLC Fiber Optic Com at 24'-8": Attach. Dunmore Boro, Lackawanna Co. Drip Loop at 24'-0": Raise 12" to 25'-0" | 41.4207 | -75.6391 | APP_306539
P:0054 | 39 | 57874N46394 | No MR | Low Power: Secondary at 30'-0". Gigapower LLC Fiber Optic Com at 23'-1": Attach | 41.4209 | -75.6395 | APP_306539
P:0102 | 40 | 57893N46382 | No MR | Low Power: Vertical_banner at 14'-11". Gigapower LLC Fiber Optic Com at 24'-3": Attach. Gigapower LLC Fiber Optic Com at 24'-3": Attach | 41.4205 | -75.6388 | APP_306539
P:0051 | 41 | 57891N46378 | No MR | Low Power: Secondary at 29'-0". Secondary at 29'-0": Resag span with bearing 216° up 18". Gigapower LLC Fiber Optic Com at 22'-9": Attach | 41.4204 | -75.6388 | APP_306539
P:0050 | 42 | 57884N46368 | MR Resolved | Low Power: Street_light at 22'-2". Secondary at 28'-5": Resag span with bearing 36° up 18". Dunmore Boro, Lackawanna Co. Street Light at 23'-11": Raise 9" to 24'-8". Dunmore Boro, Lackawanna Co. Drip Loop at 23'-0": Raise 9" to 23'-9". Gigapower LLC Fiber Optic Com at 22'-5": Attach | 41.4201 | -75.6391 | APP_306539
P:0011 | 43 | 57903N46376 | MR Resolved | Low Power: Vertical_banner at 14'-9". Dunmore Boro, Lackawanna Co. Street Light at 24'-2": Raise 6" to 24'-8". Dunmore Boro, Lackawanna Co. Drip Loop at 23'-5": Raise 6" to 23'-11". Gigapower LLC Fiber Optic Com at 22'-4": Attach. ION Holdco LLC Guy at 16'-0": Attach | 41.4203 | -75.6384 | APP_306539
P:0003 | 44 | 57913N46370 | MR Resolved | Low Power: Drip_loop at 23'-1". Secondary at 28'-6": Raise 24" to 30'-6". Neutral at 27'-10": Raise 24" to 29'-10". Secondary at 27'-6": Raise 24" to 29'-6". Dunmore Boro, Lackawanna Co. Street Light at 25'-10": Raise 18" to 27'-4". Gigapower LLC Fiber Optic Com at 23'-7": Attach. Bond to ground wire. Gigapower LLC Fiber Optic Com at 23'-7": Attach. Bond to ground wire. Dunmore Boro, Lackawanna Co. Drip Loop at 23'-1": Raise 18" to 24'-7". ION Holdco LLC Guy at 22'-7": Attach. ION Holdco LLC Guy at 21'-2": Raise 17" to 22'-7". ION Holdco LLC Fiber Optic Com at 21'-1": Raise 18" to 22'-7". ION Holdco LLC Fiber Optic Com at 21'-1": Raise 18" to 22'-7" | 41.4202 | -75.638 | APP_306539
P:0091 | 45 | 57926N46361 | MR Resolved | Low Power: Neutral at 28'-10". PPL Company Down Guy at 35'-7": Transfer PPL Company Down Guy from anchor at 17' lead at 7° to the new PPL Company anchor at 23' lead. PPL Company Down Guy at 31'-11": Transfer PPL Company Down Guy from anchor at 17' lead at 7° to the new PPL Company anchor at 23' lead. Gigapower LLC Fiber Optic Com at 24'-8": Attach. Gigapower LLC Down Guy at 24'-8": Attach and install new anchor. Place on new PPL Company anchor rod with 23' lead at 16° and attach 6.6M (1/4" EHS) (7/0) guy. Gigapower LLC Fiber Optic Com at 24'-4": Attach. Gigapower LLC Down Guy at 24'-4": Attach. Place on existing anchor rod with 21' lead at 126° and attach 6.6M (1/4" EHS) (7/0) guy. ION Holdco LLC Fiber Optic Com at 22'-8": Raise 12" to 23'-8". ION Holdco LLC Down Guy at 22'-8": Raise 12" to 23'-8". ION Holdco LLC Fiber Optic Com at 22'-4": Raise 12" to 23'-4". ION Holdco LLC Down Guy at 22'-4": Raise 12" to 23'-4". ZitoMedia / Zito West Holding, LLC Down Guy at 21'-5": Transfer ZitoMedia / Zito West Holding, LLC Down Guy from anchor at 21' lead at 126° to the existing anchor at 18' lead | 41.4199 | -75.6376 | APP_306539
P:0093 | 46 | 57907N46360 | No MR | Low Power: Open Secondary at 23'-7". Gigapower LLC Fiber Optic Com at 17'-5": Attach | 41.4199 | -75.6382 | APP_306539
P:0001 | 47 | 57900N46349 | MR Resolved | Low Power: Street_light at 20'-1". Dunmore Boro, Lackawanna Co. Street Light at 20'-1": Ground Bracket. Gigapower LLC Fiber Optic Com at 19'-3": Attach | 41.4196 | -75.6385 | APP_306539
P:0014 | 48 | 57894N46339 | MR Resolved | Low Power: Open Secondary at 21'-6". Gigapower LLC Fiber Optic Com at 17'-0": Attach. Gigapower LLC Down Guy at 17'-0": Attach. Place on existing anchor rod with 16' lead at 213° and attach 6.6M (1/4" EHS) (7/0) guy | 41.4194 | -75.6387 | APP_306539
P:0006 | 49 | 57919N46379 | No MR | Low Power: Secondary at 25'-7". Gigapower LLC Fiber Optic Com at 19'-10": Attach | 41.4204 | -75.6378 | APP_306539
P:0005 | 50 | 57926N46391 | No MR | Low Power: Secondary at 29'-5". Gigapower LLC Fiber Optic Com at 20'-5": Attach | 41.4207 | -75.6375 | APP_306539
P:0008 | 51 | 57933N46403 | No MR | Low Power: Drip_loop at 28'-8". Gigapower LLC Fiber Optic Com at 23'-10": Attach | 41.421 | -75.6373 | APP_306539
P:0007 | 52 | 57940N46413 | No MR | Low Power: Drip_loop at 26'-4". Gigapower LLC Fiber Optic Com at 20'-4": Attach | 41.4213 | -75.637 | APP_306539
P:0010 | 53 | 57947N46425 | No MR | Low Power: Secondary at 26'-2". Gigapower LLC Fiber Optic Com at 22'-3": Attach | 41.4216 | -75.6368 | APP_306539
P:0013 | 54 | 57949N46429 | MR Resolved | Low Power: Drip_loop at 22'-11". Secondary at 26'-3": Raise 24" to 28'-3". Dunmore Boro, Lackawanna Co. Street Light at 25'-4": Raise 20" to 27'-0". Gigapower LLC Fiber Optic Com at 23'-6": Attach. Dunmore Boro, Lackawanna Co. Drip Loop at 22'-11": Raise 19" to 24'-6" | 41.4217 | -75.6367 | APP_306539
P:0016 | 55 | 57953N46435 | No MR | Low Power: Secondary at 29'-1". Gigapower LLC Fiber Optic Com at 22'-1": Attach | 41.4219 | -75.6365 | APP_306539
P:0015 | 56 | 57959N46445 | No MR | Low Power: Drip_loop at 32'-3". Gigapower LLC Fiber Optic Com at 18'-9": Attach | 41.4222 | -75.6363 | APP_306539
P:0018 | 57 | 57966N46456 | No MR | Low Power: Drip_loop at 30'-3". Gigapower LLC Fiber Optic Com at 26'-4": Attach | 41.4225 | -75.636 | APP_306539
P:0020 | 58 | 57972N46466 | No MR | Low Power: Secondary at 30'-11". Gigapower LLC Fiber Optic Com at 24'-1": Attach | 41.4227 | -75.6358 | APP_306539
P:0017 | 59 | 57977N46474 | No MR | Low Power: Drip_loop at 28'-4". Gigapower LLC Fiber Optic Com at 23'-10": Attach | 41.4229 | -75.6356 | APP_306539
P:0060 | 60 | 57913N46451 | No MR | Low Power: Drip_loop at 28'-4". Gigapower LLC Fiber Optic Com at 24'-1": Attach | 41.4224 | -75.638 | APP_306539
P:0061 | 61 | 57906N46455 | MR Resolved | Low Power: Secondary at 26'-1". Gigapower LLC Fiber Optic Com at 22'-11": Attach. Bond to ground wire. ION Holdco LLC Fiber Optic Com at 22'-5": Lower 6" to 21'-11". ZitoMedia / Zito West Holding, LLC Fiber Optic Com at 21'-4": Lower 7" to 20'-9". CTSI, LLC, Dba Frontier Communications Fiber Optic Com at 20'-9": Lower 12" to 19'-9". Comcast - Duryea CATV Com at 20'-5": Lower 20" to 18'-9". Verizon Pennsylvania Inc. Telco Com at 19'-5": Lower 20" to 17'-9" | 41.4225 | -75.6382 | APP_306539
P:0062 | 62 | 57898N46460 | No MR | Low Power: Secondary at 29'-0". Gigapower LLC Fiber Optic Com at 22'-10": Attach | 41.4226 | -75.6385 | APP_306539
P:0012 | 63 | 57960N46421 | MR Resolved | Low Power: Secondary at 29'-4". Secondary at 29'-4": Raise 18" to 30'-10". Gigapower LLC Fiber Optic Com at 25'-2": Attach | 41.4215 | -75.6363 | APP_306539
P:0086 | 64 | 57969N46416 | No MR | Low Power: Secondary at 27'-0". Gigapower LLC Fiber Optic Com at 21'-11": Attach | 41.4214 | -75.636 | APP_306539
P:0076 | 65 | 57978N46410 | MR Resolved | Low Power: Vertical_banner at 15'-5". Dunmore Boro, Lackawanna Co. Street Light at 22'-5": Raise 6" to 22'-11". Dunmore Boro, Lackawanna Co. Drip Loop at 21'-5": Raise 6" to 21'-11". Gigapower LLC CATV Com at 20'-10": Attach. Gigapower LLC Fiber Optic Com at 20'-10": Attach. North Penn Long Distance Corporation Fiber Optic Com at 20'-5": Lower 7" to 19'-10". ZitoMedia / Zito West Holding, LLC Fiber Optic Com at 19'-5": Lower 7" to 18'-10". Comcast - Duryea CATV Com at 18'-10": Lower 11" to 17'-11" | 41.4212 | -75.6356 | APP_306539
P:0074 | 66 | 57986N46422 | No MR | Low Power: Drip_loop at 30'-3". Gigapower LLC CATV Com at 19'-9": Attach | 41.4215 | -75.6353 | APP_306539
P:0073 | 67 | 57994N46435 | No MR | Low Power: Drip_loop at 27'-2". Gigapower LLC CATV Com at 21'-6": Attach. Gigapower LLC CATV Com at 21'-6": Attach | 41.4219 | -75.635 | APP_306539
P:0072 | 68 | 57998N46443 | MR Resolved | Low Power: Drip_loop at 24'-8". Gigapower LLC CATV Com at 21'-7": Attach. Gigapower LLC Down Guy at 21'-7": Attach and install new anchor. Place on new Gigapower LLC anchor rod with 10' lead at 33° and attach 6.6M (1/4" EHS) (7/0) guy | 41.4221 | -75.6348 | APP_306539
P:0071 | 69 | 58002N46429 | MR Resolved | Low Power: Secondary at 27'-0". Dunmore Boro, Lackawanna Co. Street Light at 33'-4": Lower 30" to 30'-10". Dunmore Boro, Lackawanna Co. Drip Loop at 32'-7": Lower 30" to 30'-1". Secondary at 27'-0": Raise 66" to 32'-6". Gigapower LLC CATV Com at 21'-5": Attach. Gigapower LLC Down Guy at 21'-5": Attach. Place on existing anchor rod with 18' lead at 303° and attach 6.6M (1/4" EHS) (7/0) guy. North Penn Long Distance Corporation Fiber Optic Com at 21'-5": Lower 12" to 20'-5". North Penn Long Distance Corporation Down Guy at 21'-5": Lower 12" to 20'-5". Comcast - Duryea CATV Com at 20'-5": Lower 12" to 19'-5". Comcast - Duryea Down Guy at 20'-5": Lower 12" to 19'-5". Comcast - Duryea CATV Com at 20'-0": Lower 12" to 19'-0". Verizon Pennsylvania Inc. Down Guy at 18'-3": Transfer Verizon Pennsylvania Inc. Down Guy from anchor at 18' lead at 303° to the existing anchor at 18' lead | 41.4217 | -75.6347 | APP_306539
P:0070 | 70 | 58008N46425 | MR Resolved | Low Power: Drip_loop at 23'-6". Gigapower LLC CATV Com at 21'-0": Attach. Bond to ground wire. Bond to ground wire.. North Penn Long Distance Corporation Fiber Optic Com at 20'-4": Lower 4" to 20'-0". Comcast - Duryea CATV Com at 19'-4": Lower 4" to 19'-0" | 41.4216 | -75.6345 | APP_306539
P:0069 | 71 | 58017N46419 | MR Resolved | Low Power: Secondary at 26'-7". North Penn Long Distance Corporation Fiber Optic Com at 22'-0": Lower 36" to 19'-0". Comcast - Duryea CATV Com at 21'-0": Lower 36" to 18'-0". Gigapower LLC CATV Com at 20'-0": Attach. Bond to ground wire.. Verizon Pennsylvania Inc. Telco Com at 18'-5": Lower 17" to 17'-0" | 41.4214 | -75.6341 | APP_306539
P:0068 | 72 | 58029N46413 | MR Resolved | Low Power: Street_light at 20'-6". Dunmore Boro, Lackawanna Co. Street Light at 22'-1": Raise 12" to 23'-1". Dunmore Boro, Lackawanna Co. Drip Loop at 21'-4": Raise 12" to 22'-4". Gigapower LLC CATV Com at 21'-1": Attach | 41.4212 | -75.6337 | APP_306539
P:0067 | 73 | 58039N46406 | MR Resolved | Low Power: Drip_loop at 23'-4". PPL Company Transformer at 26'-4": Raise 20" to 28'-0". Secondary at 24'-3": Raise 16" to 25'-7". PPL Company Drip Loop at 23'-4": Raise 16" to 24'-8". Gigapower LLC CATV Com at 20'-7": Attach. North Penn Long Distance Corporation Fiber Optic Com at 20'-3": Lower 8" to 19'-7". Comcast - Duryea CATV Com at 19'-3": Lower 8" to 18'-7" | 41.4211 | -75.6334 | APP_306539
P:0066 | 74 | 58046N46402 | No MR | Low Power: Secondary at 24'-8". Gigapower LLC CATV Com at 21'-0": Attach | 41.4209 | -75.6331 | APP_306539
P:0065 | 75 | 58053N46398 | No MR | Low Power: Secondary at 29'-0". Gigapower LLC CATV Com at 21'-9": Attach | 41.4208 | -75.6329 | APP_306539
P:0077 | 76 | 57987N46405 | No MR | Low Power: Vertical_banner at 13'-1". Gigapower LLC Fiber Optic Com at 22'-8": Attach | 41.4211 | -75.6353 | APP_306539
P:0078 | 77 | 57996N46399 | No MR | Low Power: Secondary at 30'-4". Gigapower LLC Fiber Optic Com at 21'-4": Attach | 41.4209 | -75.6349 | APP_306539
P:0079 | 78 | 58005N46393 | No MR | Low Power: Secondary at 28'-3". Gigapower LLC Fiber Optic Com at 24'-2": Attach. Gigapower LLC Fiber Optic Com at 24'-2": Attach | 41.4207 | -75.6346 | APP_306539
P:0080 | 79 | 57998N46383 | No MR | Low Power: Drip_loop at 23'-11". Gigapower LLC Fiber Optic Com at 20'-7": Attach | 41.4204 | -75.6349 | APP_306539
P:0081 | 80 | 58013N46388 | MR Resolved | Low Power: Vertical_banner at 12'-6". Gigapower LLC Fiber Optic Com at 21'-0": Attach. North Penn Long Distance Corporation Fiber Optic Com at 20'-7": Lower 7" to 20'-0". Comcast - Duryea CATV Com at 19'-7": Lower 7" to 19'-0" | 41.4206 | -75.6343 | APP_306539
P:0082 | 81 | 58022N46382 | No MR | Low Power: Vertical_banner at 15'-3". Gigapower LLC Fiber Optic Com at 23'-7": Attach | 41.4204 | -75.634 | APP_306539
P:0083 | 82 | 58033N46376 | MR Resolved | Low Power: Vertical_banner at 15'-6". Pole Top: Replace 40' class 2 pole with 45' class 2 pole. Primary at 33'-4": Raise 53" to 37'-9". Power Guy at 32'-8": Raise 51" to 36'-11". PPL Company Cutout Arrestor at 31'-0": Raise 51" to 35'-3". PPL Company Transformer at 28'-1": Raise 56" to 32'-9". Secondary at 25'-5": Raise 13" to 26'-6". PPL Company Drip Loop at 24'-10": Raise 14" to 26'-0". Dunmore Boro, Lackawanna Co. Street Light at 22'-10": Raise 24" to 24'-10", Transfer to new pole at 23'-0". Gigapower LLC Fiber Optic Com at 22'-0": Attach. Dunmore Boro, Lackawanna Co. Drip Loop at 21'-9": Raise 24" to 23'-9", Transfer to new pole at 23'-9". North Penn Long Distance Corporation Fiber Optic Com at 20'-5": Raise 7" to 21'-0", Transfer to new pole at 21'-0". ZitoMedia / Zito West Holding, LLC Fiber Optic Com at 19'-5": Raise 7" to 20'-0", Transfer to new pole at 20'-0". Comcast - Duryea CATV Com at 18'-11": Raise 1" to 19'-0", Transfer to new pole at 19'-0". Verizon Pennsylvania Inc. Telco Com at 17'-9": Raise 3" to 18'-0", Transfer to new pole at 18'-0". Dunmore Boro, Lackawanna Co. Vertical Banner at 15'-6": Transfer to new pole at 15'-6" | 41.4202 | -75.6336 | APP_306539
P:0084 | 83 | 58043N46369 | MR Resolved | Low Power: Drip_loop at 23'-5". PPL Company Street Light at 23'-7": Ground Bracket. Gigapower LLC Fiber Optic Com at 21'-2": Attach. Bond to ground wire | 41.42 | -75.6333 | APP_306539
P:0095 | 84 | 58084N46426 | No MR | Low Power: Secondary at 24'-3". Gigapower LLC Fiber Optic Com at 20'-3": Attach | 41.4215 | -75.6317 | APP_306539
P:0045 | 85 | 57929N46441 | No MR | Low Power: Secondary at 29'-0". Gigapower LLC Fiber Optic Com at 24'-0": Attach | 41.4221 | -75.6374 | APP_306539
P:0044 | 86 | 57936N46436 | No MR | Low Power: Drip_loop at 27'-7". Gigapower LLC Fiber Optic Com at 22'-3": Attach. Gigapower LLC Guy at 19'-4": Attach | 41.422 | -75.6372 | APP_306539
P:0009 | 87 | 57942N46433 | No MR | Low Power: Secondary at 28'-0". Gigapower LLC Fiber Optic Com at 24'-7": Attach | 41.4218 | -75.6369 | APP_306539
P:0092 | 89 | 57924N46348 | MR Resolved | Low Power: Drip_loop at 20'-8". Neutral at 27'-2": Install ground rod and bond neutral to ground. Gigapower LLC Fiber Optic Com at 21'-4": Attach. Bond to ground wire. Gigapower LLC Down Guy at 21'-4": Attach. Place on existing anchor rod with 22' lead at 187° and attach aux eye and 6.6M (1/4" EHS) (7/0) guy. Dunmore Boro, Lackawanna Co. Street Light at 21'-2": Raise 24" to 23'-2". Gigapower LLC Fiber Optic Com at 21'-0": Attach. Bond to ground wire. Gigapower LLC Down Guy at 21'-0": Attach. Place on existing anchor rod with 25' lead at 304° and attach aux eye and 6.6M (1/4" EHS) (7/0) guy. Dunmore Boro, Lackawanna Co. Drip Loop at 20'-8": Raise 20" to 22'-4". ION Holdco LLC Fiber Optic Com at 19'-4": Raise 12" to 20'-4", Bond to ground wire. ION Holdco LLC Fiber Optic Com at 19'-0": Raise 12" to 20'-0", Bond to ground wire. ION Holdco LLC Down Guy at 19'-0": Raise 12" to 20'-0" | 41.4195 | -75.6376 | APP_306539
P:0004 | 046.A | P:0004 NT | No MR | Gigapower LLC Fiber Optic Com at 18'-11": Attach | 41.4201 | -75.6381 | APP_306539
P:0075 | 066.A | P:0075 160 | MR Resolved | North Penn Long Distance Corporation Fiber Optic Com at 19'-7": Lower 12" to 18'-7". Gigapower LLC CATV Com at 19'-7": Attach. Comcast - Duryea CATV Com at 18'-7": Lower 12" to 17'-7". Comcast - Duryea Down Guy at 18'-7": Lower 12" to 17'-7". Verizon Pennsylvania Inc. Down Guy at 17'-7": Lower 12" to 16'-7". Verizon Pennsylvania Inc. Guy at 17'-7": Lower 12" to 16'-7" | 41.4214 | -75.6354 | APP_306539
P:0035 | 005.A | P:0035 101 | MR Resolved | Gigapower LLC Fiber Optic Com at 20'-6": Attach. Gigapower LLC Fiber Optic Com at 20'-6": Attach. Gigapower LLC Down Guy at 20'-6": Attach. Place on existing anchor rod with 8' lead at 215° and attach aux eye and 6.6M (1/4" EHS) (7/0) guy | 41.4216 | -75.6323 | APP_306539
P:0025 | 011.A | P:0025 11 | MR Resolved | Gigapower LLC Fiber Optic Com at 19'-10": Attach. Gigapower LLC Down Guy at 19'-10": Attach. Place on existing anchor rod with 10' lead at 212° and attach 6.6M (1/4" EHS) (7/0) guy. North Penn Long Distance Corporation Fiber Optic Com at 19'-7": Lower 9" to 18'-10". North Penn Long Distance Corporation Down Guy at 19'-7": Lower 9" to 18'-10". Gigapower LLC Fiber Optic Com at 19'-6": Attach. North Penn Long Distance Corporation Fiber Optic Com at 19'-3": Lower 12" to 18'-3". Comcast - Duryea Strand at 18'-6": Lower 10" to 17'-8". Comcast - Duryea Down Guy at 18'-6": Lower 10" to 17'-8". Comcast - Duryea CATV Com at 18'-3": Lower 13" to 17'-2" | 41.4227 | -75.6342 | APP_306539
P:0100 | 20 | 57955N46504 | MR Resolved | Low Power: Vertical_banner at 14'-11". Secondary at 27'-1": Raise 16" to 28'-5". Secondary at 26'-7": Raise 16" to 27'-11". Secondary at 25'-11": Raise 16" to 27'-3". Dunmore Boro, Lackawanna Co. Street Light at 24'-9": Raise 15" to 26'-0". Gigapower LLC Fiber Optic Com at 23'-1": Attach. Dunmore Boro, Lackawanna Co. Drip Loop at 22'-10": Raise 15" to 24'-1" | 41.4223 | -75.6317 | APP_306543
P:0085 | 21 | 57961N46514 | MR Resolved | Low Power: Drip_loop at 24'-8". Gigapower LLC Fiber Optic Com at 22'-1": Attach. Bond to ground wire | 41.4222 | -75.6319 | APP_306543
P:0099 | 22 | 57945N46510 | MR Resolved | Low Power: Secondary at 29'-3". North Penn Long Distance Corporation Fiber Optic Com at 23'-11": Lower 39" to 20'-8". ZitoMedia / Zito West Holding, LLC Fiber Optic Com at 22'-11": Lower 39" to 19'-8". CTSI, LLC, Dba Frontier Communications Telco Com at 22'-0": Lower 40" to 18'-8". Gigapower LLC Fiber Optic Com at 21'-8": Attach. Bond to ground wire. Comcast - Duryea Strand at 20'-5": Lower 33" to 17'-8". Comcast - Duryea CATV Com at 20'-5": Lower 33" to 17'-8" | 41.4223 | -75.6321 | APP_306543
P:0031 | 23 | 57934N46517 | MR Resolved | Low Power: Secondary at 26'-4". Secondary at 26'-4": Raise 12" to 27'-4". Gigapower LLC Fiber Optic Com at 22'-0": Attach. Bond to ground wire | 41.4225 | -75.6324 | APP_306543
P:0032 | 24 | 57948N46494 | No MR | Low Power: Secondary at 28'-3". Gigapower LLC Fiber Optic Com at 22'-4": Attach | 41.4226 | -75.6328 | APP_306543
P:0033 | 25 | 57942N46483 | No MR | Low Power: Secondary at 25'-10". Gigapower LLC Fiber Optic Com at 21'-8": Attach | 41.4228 | -75.633 | APP_306543
P:0028 | 61 | 57906N46455 | MR Resolved | Low Power: Secondary at 26'-1". Gigapower LLC Fiber Optic Com at 22'-11": Attach. Bond to ground wire. ION Holdco LLC Fiber Optic Com at 22'-5": Lower 6" to 21'-11". ZitoMedia / Zito West Holding, LLC Fiber Optic Com at 21'-4": Lower 7" to 20'-9". CTSI, LLC, Dba Frontier Communications Fiber Optic Com at 20'-9": Lower 12" to 19'-9". Comcast - Duryea CATV Com at 20'-5": Lower 20" to 18'-9". Verizon Pennsylvania Inc. Telco Com at 19'-5": Lower 20" to 17'-9" | 41.4231 | -75.6338 | APP_306543
P:0029 | 62 | 57898N46460 | No MR | Low Power: Secondary at 29'-0". Gigapower LLC Fiber Optic Com at 22'-10": Attach | 41.4233 | -75.6337 | APP_306543
P:0064 | 63 | 57960N46421 | MR Resolved | Low Power: Secondary at 29'-4". Secondary at 29'-4": Raise 18" to 30'-10". Gigapower LLC Fiber Optic Com at 25'-2": Attach | 41.4236 | -75.6334 | APP_306543
P:0030 | 67 | 57994N46435 | No MR | Low Power: Drip_loop at 27'-2". Gigapower LLC CATV Com at 21'-6": Attach. Gigapower LLC CATV Com at 21'-6": Attach | 41.4221 | -75.6318 | APP_306543
P:0034 | 86 | 57936N46436 | No MR | Low Power: Drip_loop at 27'-7". Gigapower LLC Fiber Optic Com at 22'-3": Attach. Gigapower LLC Guy at 19'-4": Attach | 41.4229 | -75.6333 | APP_306543