## MakeReadySummary
Pole_ID | SCID | Pole_tag | Make_Ready_State | Make_ready_notes | Latitude | Longitude | jobname
P:0095 | 040 | 58515N46380 | No MR | Low Power: Secondary at 24'-5". Gigapower LLC Fiber Optic Com at 19'-11": Attach | 41.4201 | -75.616 | APP_306551
P:0102 | 047 | 58486N46350 | MR Resolved | Low Power: Drip_loop at 22'-7". PPL Company Down Guy at 28'-2": Transfer PPL Company Down Guy from anchor at 13' lead at 123° to the new PPL Company anchor at 20' lead. Secondary at 22'-10": Raise 24" to 24'-10". PPL Company Drip Loop at 22'-7": Raise 24" to 24'-7". Gigapower LLC Fiber Optic Com at 20'-4": Attach. Gigapower LLC Down Guy at 20'-4": Attach and install new anchor. Place on new PPL Company anchor rod with 20' lead at 123° and attach 10M (3/8" UG) (7/0) guy | 41.4193 | -75.6172 | APP_306551
P:0103 | 048 | 58474N46357 | MR Resolved | Low Power: Drip_loop at 21'-11". Pole Top: Replace 35' class 3 pole with 45' class 2 pole. Secondary at 24'-2": Raise 24" to 26'-2". Secondary at 24'-2": Raise 24" to 26'-2". PPL Company Drip Loop at 23'-3": Raise 24" to 25'-3". Dunmore Boro, Lackawanna Co. Street Light at 22'-7": Raise 3" to 22'-10", Transfer to new pole at 22'-6". Dunmore Boro, Lackawanna Co. Drip Loop at 21'-11": Raise 1" to 22'-0", Transfer to new pole at 22'-0". Gigapower LLC Fiber Optic Com at 21'-0": Attach. Power Guy at 20'-6": Lower 48" to 16'-6". North Penn Long Distance Corporation Fiber Optic Com at 19'-0": Raise 12" to 20'-0", Transfer to new pole at 20'-0". Comcast - Duryea CATV Com at 18'-0": Raise 12" to 19'-0", Transfer to new pole at 19'-0". Verizon Pennsylvania Inc. Telco Com at 17'-0": Raise 12" to 18'-0", Transfer to new pole at 18'-0". Gigapower LLC Guy at 15'-6": Attach. Power Guy at 10'-8": Raise 64" to 16'-0" | 41.4195 | -75.6176 | APP_306551
P:0104 | 049 | 58462N46365 | MR Resolved | Low Power: Secondary at 25'-0". Gigapower LLC Fiber Optic Com at 22'-0": Attach. Bond to ground wire | 41.4197 | -75.618 | APP_306551
P:0104 | 052 | 58439N46366 | MR Resolved | Low Power: Secondary at 24'-6". Comcast - Duryea CATV Com at 19'-9": Lower 12" to 18'-9". Gigapower LLC Fiber Optic Com at 19'-9": Attach. Bond to ground wire | 41.4198 | -75.6189 | APP_306551
P:0060 | 053 | 58438N46357 | MR Resolved | Low Power: Secondary at 27'-2". Gigapower LLC Fiber Optic Com at 20'-3": Attach | 41.4195 | -75.619 | APP_306551
P:0028 | 055 | 58490N46343 | No MR | Low Power: Drip_loop at 30'-2". Gigapower LLC Fiber Optic Com at 24'-1": Attach | 41.419 | -75.6169 | APP_306551
P:0015 | 056 | 58486N46343 | MR Resolved | Low Power: Vertical_banner at 16'-5". Dunmore Boro, Lackawanna Co. Street Light at 27'-2": Ground Bracket. Gigapower LLC Fiber Optic Com at 24'-0": Attach. Zayo Bandwidth Fiber Optic Com at 23'-5": Lower 5" to 23'-0", Transfer to new pole at 23'-0". CTSI, LLC, Dba Frontier Communications Telco Com at 22'-6": Lower 6" to 22'-0", Transfer to new pole at 22'-0". Comcast - Duryea CATV Com at 21'-9": Lower 9" to 21'-0", Transfer to new pole at 21'-0". Dunmore Boro, Lackawanna Co. Vertical Banner at 16'-5": Remove. Banner not on record. Please go through PPL's application process to get on record | 41.4191 | -75.6171 | APP_306551
P:0016 | 057 | 58477N46344 | MR Resolved | Low Power: Vertical_banner at 15'-8". Dunmore Boro, Lackawanna Co. Street Light at 25'-11": Ground Bracket. Dunmore Boro, Lackawanna Co. Drip Loop at 25'-7": Insulate drip loop. Gigapower LLC Fiber Optic Com at 25'-2": Attach. Zayo Bandwidth Fiber Optic Com at 24'-10": Lower 10" to 24'-0". CTSI, LLC, Dba Frontier Communications Telco Com at 24'-0": Lower 12" to 23'-0". Comcast - Duryea CATV Com at 23'-0": Lower 12" to 22'-0" | 41.4191 | -75.6175 | APP_306551
P:0017 | 058 | 58468N46345 | MR Resolved | Low Power: Vertical_banner at 15'-2". Dunmore Boro, Lackawanna Co. Street Light at 25'-1": Raise 18" to 26'-7", Ground Bracket. Gigapower LLC Fiber Optic Com at 24'-11": Attach. Gigapower LLC Fiber Optic Com at 24'-11": Attach. Gigapower LLC Guy at 24'-11": Attach. Dunmore Boro, Lackawanna Co. Drip Loop at 24'-3": Raise 18" to 25'-9", Insulate drip loop | 41.4191 | -75.6178 | APP_306551
P:0018 | 059 | 58460N46346 | MR Resolved | Low Power: Vertical_banner at 14'-10". Dunmore Boro, Lackawanna Co. Street Light at 26'-1": Ground Bracket. Gigapower LLC Fiber Optic Com at 24'-6": Attach | 41.4192 | -75.6182 | APP_306551
P:0019 | 060 | 58448N46347 | MR Resolved | Low Power: Vertical_banner at 15'-3". Dunmore Boro, Lackawanna Co. Street Light at 24'-8": Raise 18" to 26'-2", Ground Bracket. Dunmore Boro, Lackawanna Co. Drip Loop at 23'-9": Raise 18" to 25'-3". Gigapower LLC Fiber Optic Com at 23'-7": Attach. Gigapower LLC Guy at 16'-0": Attach | 41.4192 | -75.6186 | APP_306551
P:0020 | 061 | 58437N46348 | MR Resolved | Low Power: Vertical_banner at 15'-11". Dunmore Boro, Lackawanna Co. Street Light at 26'-11": Ground Bracket. Gigapower LLC Fiber Optic Com at 24'-9": Attach. Bond to ground wire. Zayo Bandwidth Fiber Optic Com at 24'-9": Lower 12" to 23'-9". Gigapower LLC Fiber Optic Com at 24'-9": Attach. Gigapower LLC Fiber Optic Com at 24'-9": Attach. Gigapower LLC Guy at 24'-3": Attach. CTSI, LLC, Dba Frontier Communications Telco Com at 23'-9": Lower 12" to 22'-9". Comcast - Duryea CATV Com at 22'-9": Lower 12" to 21'-9". Comcast - Duryea CATV Com at 22'-9": Lower 12" to 21'-9". Dunmore Boro, Lackawanna Co. Alarm Cable at 22'-1": Lower 16" to 20'-9", Remove | 41.4193 | -75.6191 | APP_306551
P:0034 | 062 | 58432N46344 | MR Resolved | Low Power: Street_light at 23'-9". Dunmore Boro, Lackawanna Co. Street Light at 23'-9": Ground Bracket. Gigapower LLC Fiber Optic Com at 23'-4": Attach. Gigapower LLC Guy at 23'-4": Attach | 41.4192 | -75.6193 | APP_306551
P:0021 | 063 | 58424N46350 | MR Resolved | Low Power: Vertical_banner at 16'-2". Dunmore Boro, Lackawanna Co. Street Light at 26'-10": Ground Bracket. Zayo Bandwidth Fiber Optic Com at 24'-0": Lower 12" to 23'-0". Gigapower LLC Fiber Optic Com at 24'-0": Attach. CTSI, LLC, Dba Frontier Communications Telco Com at 23'-2": Lower 14" to 22'-0". Comcast - Duryea CATV Com at 22'-4": Lower 16" to 21'-0". Dunmore Boro, Lackawanna Co. Alarm Cable at 20'-10": Lower 10" to 20'-0", Remove. Power Guy at 20'-0": Lower 12" to 19'-0". Power Guy at 19'-0": Lower 6" to 18'-6". Gigapower LLC Guy at 18'-0": Attach | 41.4194 | -75.6195 | APP_306551
P:0022 | 064 | 58417N46352 | MR Resolved | Low Power: Vertical_banner at 18'-5". Dunmore Boro, Lackawanna Co. Street Light at 25'-10": Ground Bracket. PPL Company Riser at 25'-1": Extend 12" to 26'-1". Gigapower LLC Fiber Optic Com at 22'-6": Attach. Bond to ground wire. Zayo Bandwidth Fiber Optic Com at 22'-2": Lower 8" to 21'-6". CTSI, LLC, Dba Frontier Communications Telco Com at 21'-2": Lower 8" to 20'-6". Dunmore Boro, Lackawanna Co. Alarm Cable at 20'-2": Remove. Comcast - Duryea CATV Com at 20'-0": Lower 6" to 19'-6". Comcast - Duryea CATV Com at 19'-8": Lower 6" to 19'-2" | 41.4194 | -75.6199 | APP_306551
P:0023 | 065 | 58405N46355 | MR Resolved | Low Power: Vertical_banner at 15'-0". Dunmore Boro, Lackawanna Co. Street Light at 22'-3": Raise 24" to 24'-3", Ground Bracket. Gigapower LLC Fiber Optic Com at 22'-0": Attach. Zayo Bandwidth Fiber Optic Com at 21'-0": Bolt to pole at 21'-0". Dunmore Boro, Lackawanna Co. Drip Loop at 20'-11": Raise 24" to 22'-11", Insulate drip loop. Dunmore Boro, Lackawanna Co. Alarm Cable at 19'-2": Remove | 41.4195 | -75.6203 | APP_306551
P:0024 | 066 | 58396N46359 | MR Resolved | Low Power: Vertical_banner at 15'-6". Dunmore Boro, Lackawanna Co. Street Light at 26'-7": Ground Bracket. Dunmore Boro, Lackawanna Co. Drip Loop at 25'-9": Insulate drip loop. Gigapower LLC Fiber Optic Com at 25'-0": Attach. Dunmore Boro, Lackawanna Co. Alarm Cable at 21'-9": Remove | 41.4196 | -75.6205 | APP_306551
P:0025 | 067 | 58387N46363 | MR Resolved | Low Power: Vertical_banner at 15'-0". PPL Company Drip Loop at 25'-8": Raise 18" to 27'-2". Dunmore Boro, Lackawanna Co. Street Light at 24'-11": Ground Bracket. Zayo Bandwidth Fiber Optic Com at 24'-6": Lower 24" to 22'-6". CTSI, LLC, Dba Frontier Communications Telco Com at 23'-6": Lower 24" to 21'-6". Comcast - Duryea CATV Com at 23'-6": Lower 36" to 20'-6". Gigapower LLC Fiber Optic Com at 23'-6": Attach. Dunmore Boro, Lackawanna Co. Alarm Cable at 22'-6": Remove. Attach to pole at 19'-6" | 41.4197 | -75.6208 | APP_306551
P:0106 | 068 | 58375N46367 | MR Resolved | Low Power: Vertical_banner at 15'-10". Zayo Bandwidth Guy at 23'-0": Lower 16" to 21'-8". Dunmore Boro, Lackawanna Co. Street Light at 23'-0": Ground Bracket. Zayo Bandwidth Fiber Optic Com at 23'-0": Lower 16" to 21'-8". Gigapower LLC Fiber Optic Com at 22'-8": Attach. Dunmore Boro, Lackawanna Co. Alarm Cable at 22'-8": Remove. CTSI, LLC, Dba Frontier Communications Telco Com at 22'-2": Lower 18" to 20'-8". Comcast - Duryea CATV Com at 21'-2": Lower 18" to 19'-8" | 41.4198 | -75.6212 | APP_306551
P:0047 | 001 | 58632N46438 | MR Resolved | Low Power: Drip_loop at 23'-5". Dunmore Boro, Lackawanna Co. Drip Loop at 23'-5": Guard drip loop. Gigapower LLC Fiber Optic Com at 23'-2": Attach. Bond to ground wire. Gigapower LLC Down Guy at 23'-2": Attach. Place on existing anchor rod with 18' lead at 33° and attach 10M (3/8" UG) (7/0) guy. Verizon Pennsylvania Inc. Down Guy at 20'-3": Transfer Verizon Pennsylvania Inc. Down Guy from anchor at 18' lead at 33° to the new Gigapower LLC anchor at 12' lead | 41.4216 | -75.6118 | APP_306552
P:0040 | 002 | 58584N46450 | MR Resolved | Low Power: Riser at 26'-0". Pole Top: Replace 40' class 5 pole with 45' class 3 pole. Primary at 32'-10": Raise 58" to 37'-8". PPL Company Down Guy at 31'-11": Raise 58" to 36'-9". Secondary at 28'-3": Raise 51" to 32'-6". Dunmore Boro, Lackawanna Co. Street Light at 27'-3": Lower 11" to 26'-4", Ground Bracket. Transfer to new pole at 25'-6". Dunmore Boro, Lackawanna Co. Drip Loop at 26'-0": Lower 18" to 24'-6", Transfer to new pole at 24'-6". PPL Company Riser at 26'-0": Extend 12" to 27'-0". Gigapower LLC Fiber Optic Com at 23'-6": Attach. North Penn Long Distance Corporation Fiber Optic Com at 20'-11": Raise 19" to 22'-6", Transfer to new pole at 22'-6". Comcast - Duryea CATV Com at 19'-11": Raise 19" to 21'-6", Transfer to new pole at 21'-6". Comcast - Duryea Down Guy at 19'-11": Raise 19" to 21'-6", Transfer to new pole at 21'-6". Verizon Pennsylvania Inc. Telco Com at 19'-0": Raise 18" to 20'-6", Transfer to new pole at 20'-6". Verizon Pennsylvania Inc. Down Guy at 19'-0": Raise 18" to 20'-6", Transfer to new pole at 20'-6" | 41.4221 | -75.6136 | APP_306552
P:0041 | 003 | 58598N46442 | MR Resolved | Low Power: Drip_loop at 21'-1". Pole Top: Replace 40' class 4 pole with 45' class 3 pole. Primary at 32'-11": Raise 58" to 37'-9". PPL Company Cutout Arrestor at 31'-0": Raise 58" to 35'-10". PPL Company Transformer at 28'-4": Raise 58" to 33'-2". Secondary at 24'-7": Raise 58" to 29'-5". Gigapower LLC Fiber Optic Com at 24'-0": Attach. Dunmore Boro, Lackawanna Co. Street Light at 22'-3": Raise 50" to 26'-5", Transfer to new pole at 25'-6". Dunmore Boro, Lackawanna Co. Drip Loop at 21'-1": Raise 47" to 25'-0", Transfer to new pole at 25'-0". North Penn Long Distance Corporation Fiber Optic Com at 20'-10": Raise 26" to 23'-0", Transfer to new pole at 23'-0". Comcast - Duryea CATV Com at 19'-10": Raise 26" to 22'-0", Transfer to new pole at 22'-0". Verizon Pennsylvania Inc. Telco Com at 19'-0": Raise 24" to 21'-0", Transfer to new pole at 21'-0" | 41.4218 | -75.6131 | APP_306552
P:0042 | 004 | 58612N46434 | MR Resolved | Low Power: Secondary at 26'-11". Secondary at 26'-11": Raise 24" to 28'-11", Install ground rod and bond neutral to ground. Gigapower LLC Fiber Optic Com at 22'-3": Attach. Gigapower LLC Down Guy at 22'-3": Attach. Place on existing anchor rod with 15' lead at 38° and attach aux eye and 6.6M (1/4" EHS) (7/0) guy | 41.4216 | -75.6126 | APP_306552
P:0043 | 005 | 58623N46423 | MR Resolved | Low Power: Street_light at 20'-0". Dunmore Boro, Lackawanna Co. Street Light at 22'-0": Raise 12" to 23'-0". Dunmore Boro, Lackawanna Co. Drip Loop at 21'-2": Raise 12" to 22'-2". Gigapower LLC Fiber Optic Com at 20'-5": Attach. Gigapower LLC Fiber Optic Com at 20'-5": Attach | 41.4212 | -75.6121 | APP_306552
P:0097 | 006 | 58634N46419 | No MR | Low Power: Riser at 21'-3". Gigapower LLC Fiber Optic Com at 18'-5": Attach | 41.4211 | -75.6117 | APP_306552
P:0045 | 007 | 58644N46413 | No MR | Low Power: Drip_loop at 21'-10". Gigapower LLC Fiber Optic Com at 20'-4": Attach | 41.4209 | -75.6114 | APP_306552
P:0046 | 008 | 58658N46404 | MR Resolved | Low Power: Drip_loop at 23'-4". Pole Top: Replace 40' class 4 pole with 45' class 3 pole. Primary at 33'-4": Raise 53" to 37'-9". PPL Company Down Guy at 32'-4": Raise 55" to 36'-11". PPL Company Cutout Arrestor at 30'-11": Raise 52" to 35'-3". PPL Company Transformer at 27'-6": Raise 51" to 31'-9". Secondary at 25'-4": Raise 56" to 30'-0", Bond to ground wire. PPL Company Drip Loop at 24'-11": Raise 53" to 29'-4". Dunmore Boro, Lackawanna Co. Street Light at 24'-4": Raise 25" to 26'-5", Ground Bracket. Transfer to new pole at 25'-6". Gigapower LLC Fiber Optic Com at 24'-0": Attach. Gigapower LLC Down Guy at 24'-0": Attach. Place on existing anchor rod with 20' lead at 122° and attach aux eye and 6.6M (1/4" EHS) (7/0) guy. Dunmore Boro, Lackawanna Co. Drip Loop at 23'-4": Raise 20" to 25'-0", Transfer to new pole at 25'-0". North Penn Long Distance Corporation Fiber Optic Com at 21'-11": Raise 13" to 23'-0", Transfer to new pole at 23'-0". North Penn Long Distance Corporation Down Guy at 21'-11": Raise 13" to 23'-0", Transfer to new pole at 23'-0". Comcast - Duryea CATV Com at 20'-11": Raise 13" to 22'-0", Transfer to new pole at 22'-0". Comcast - Duryea Down Guy at 20'-11": Raise 13" to 22'-0", Transfer to new pole at 22'-0". Verizon Pennsylvania Inc. Guy at 20'-3": Raise 9" to 21'-0", Transfer to new pole at 21'-0" | 41.4207 | -75.6109 | APP_306552
P:0074 | 009 | 58657N46395 | MR Resolved | Low Power: Drip_loop at 25'-5". Dunmore Boro, Lackawanna Co. Drip Loop at 25'-5": Raise 7" to 26'-0". Gigapower LLC Fiber Optic Com at 25'-0": Attach. Bond to ground wire. Gigapower LLC Down Guy at 25'-0": Attach. Place on existing anchor rod with 25' lead at 32° and attach 6.6M (1/4" EHS) (7/0) guy. Verizon Pennsylvania Inc. Down Guy at 22'-0": Transfer Verizon Pennsylvania Inc. Down Guy from anchor at 25' lead at 32° to the new Verizon Pennsylvania Inc. anchor at 19' lead | 41.4204 | -75.6109 | APP_306552
P:0090 | 010 | 58651N46384 | MR Resolved | Low Power: Drip_loop at 25'-6". Gigapower LLC Fiber Optic Com at 22'-6": Attach. Bond to ground wire | 41.4201 | -75.6111 | APP_306552
P:0073 | 011 | 58645N46374 | MR Resolved | Low Power: Street_light at 19'-4". Secondary at 23'-7": Raise 12" to 24'-7", Install ground rod and bond neutral to ground. Secondary at 23'-4": Raise 12" to 24'-4". Dunmore Boro, Lackawanna Co. Street Light at 20'-11": Raise 12" to 21'-11". Dunmore Boro, Lackawanna Co. Drip Loop at 20'-6": Raise 12" to 21'-6". Gigapower LLC Fiber Optic Com at 19'-5": Attach. Bond to ground wire | 41.4198 | -75.6113 | APP_306552
P:0002 | 012 | 58638N46363 | MR Resolved | Low Power: Secondary at 25'-0". Pole Top: Replace 35' class 4 pole with 40' class 3 pole. Primary at 27'-8": Raise 68" to 33'-4". Secondary at 25'-0": Raise 12" to 26'-0". Gigapower LLC Fiber Optic Com at 21'-0": Attach. North Penn Long Distance Corporation Fiber Optic Com at 19'-3": Raise 9" to 20'-0", Transfer to new pole at 20'-0". Comcast - Duryea CATV Com at 18'-3": Raise 9" to 19'-0", Transfer to new pole at 19'-0". Verizon Pennsylvania Inc. Telco Com at 17'-3": Raise 9" to 18'-0", Transfer to new pole at 18'-0" | 41.4195 | -75.6116 | APP_306552
P:0071 | 013 | 58632N46353 | MR Resolved | Low Power: Drip_loop at 21'-10". Pole Top: Replace 40' class 4 pole with 45' class 3 pole. Primary at 31'-9": Raise 72" to 37'-9". PPL Company Cutout Arrestor at 29'-6": Raise 66" to 35'-0". PPL Company Transformer at 25'-3": Raise 81" to 32'-0". Service at 23'-0": Raise 36" to 26'-0". Secondary at 22'-10": Raise 32" to 25'-6". Secondary at 22'-6": Raise 30" to 25'-0". PPL Company Drip Loop at 21'-10": Raise 32" to 24'-6". Gigapower LLC Fiber Optic Com at 21'-0": Attach. Bond to ground wire. North Penn Long Distance Corporation Fiber Optic Com at 18'-11": Raise 13" to 20'-0", Transfer to new pole at 20'-0". Comcast - Duryea CATV Com at 17'-11": Raise 13" to 19'-0", Transfer to new pole at 19'-0". Verizon Pennsylvania Inc. Telco Com at 16'-7": Raise 17" to 18'-0", Transfer to new pole at 18'-0" | 41.4193 | -75.6118 | APP_306552
P:0055 | 014 | 58633N46338 | MR Resolved | Low Power: Secondary at 24'-3". Secondary at 24'-3": Raise 12" to 25'-3". PPL Company Down Guy at 23'-7": Raise 12" to 24'-7". Gigapower LLC Fiber Optic Com at 21'-2": Attach. Gigapower LLC Down Guy at 21'-2": Attach. Place on existing anchor rod with 14' lead at 121° and attach 10M (3/8" UG) (7/0) guy. Verizon Pennsylvania Inc. Down Guy at 17'-8": Transfer Verizon Pennsylvania Inc. Down Guy from anchor at 14' lead at 121° to the new Verizon Pennsylvania Inc. anchor at 8' lead | 41.4189 | -75.6118 | APP_306552
P:0056 | 015 | 58625N46343 | MR Resolved | Low Power: Street_light at 21'-6". Dunmore Boro, Lackawanna Co. Street Light at 24'-0": Raise 12" to 25'-0", Ground Bracket. Ensure Bracket is transferred to new pole at or above 22'-6". Dunmore Boro, Lackawanna Co. Drip Loop at 22'-2": Raise 12" to 23'-2". Gigapower LLC Fiber Optic Com at 21'-6": Attach. Gigapower LLC Fiber Optic Com at 21'-6": Attach. Gigapower LLC Down Guy at 21'-6": Attach. Place on existing anchor rod with 14' lead at 217° and attach 10M (3/8" UG) (7/0) guy. North Penn Long Distance Corporation Down Guy at 20'-6": Attach. Place on existing anchor rod with 14' lead at 217° and attach 10M (3/8" UG) (7/0) guy | 41.419 | -75.6121 | APP_306552
P:0058 | 016 | 58614N46350 | MR Resolved | Low Power: Drip_loop at 21'-0". Gigapower LLC Fiber Optic Com at 20'-2": Attach. Bond to ground wire. North Penn Long Distance Corporation Fiber Optic Com at 20'-2": Lower 12" to 19'-2". Comcast - Duryea CATV Com at 19'-2": Lower 12" to 18'-2". Verizon Pennsylvania Inc. Telco Com at 18'-2": Lower 12" to 17'-2" | 41.4192 | -75.6125 | APP_306552
P:0057 | 017 | 58605N46355 | MR Resolved | Low Power: Drip_loop at 22'-6". Secondary at 23'-5": Raise 12" to 24'-5". Service at 23'-0": Raise 12" to 24'-0". PPL Company Drip Loop at 22'-6": Raise 12" to 23'-6". Gigapower LLC Fiber Optic Com at 20'-11": Attach | 41.4193 | -75.6128 | APP_306552
P:0059 | 018 | 58596N46361 | MR Resolved | Low Power: Drip_loop at 24'-6". North Penn Long Distance Corporation Fiber Optic Com at 20'-9": Lower 12" to 19'-9". Gigapower LLC Fiber Optic Com at 20'-9": Attach. Comcast - Duryea CATV Com at 19'-9": Lower 12" to 18'-9". Verizon Pennsylvania Inc. Telco Com at 18'-6": Lower 9" to 17'-9" | 41.4195 | -75.6131 | APP_306552
P:0053 | 019 | 58588N46365 | MR Resolved | Low Power: Drip_loop at 21'-5". Secondary at 25'-2": Raise 4" to 25'-6". Secondary at 24'-6": Raise 10" to 25'-4". Dunmore Boro, Lackawanna Co. Street Light at 23'-2": Raise 12" to 24'-2". Gigapower LLC Fiber Optic Com at 22'-0": Attach. Dunmore Boro, Lackawanna Co. Drip Loop at 21'-5": Raise 12" to 22'-5" | 41.4196 | -75.6134 | APP_306552
P:0084 | 020 | 58579N46370 | No MR | Low Power: Drip_loop at 25'-1". Gigapower LLC Fiber Optic Com at 21'-7": Attach | 41.4198 | -75.6137 | APP_306552
P:0083 | 021 | 58569N46376 | MR Resolved | Low Power: Service at 24'-3". Power Guy at 26'-11": Raise 6" to 27'-5". Power Guy at 26'-11": Raise 6" to 27'-5". Service at 25'-8": Raise 4" to 26'-0". Secondary at 24'-6": Raise 24" to 26'-6". Service at 24'-3": Raise 21" to 26'-0". Gigapower LLC Fiber Optic Com at 21'-0": Attach | 41.4199 | -75.6141 | APP_306552
P:0082 | 022 | P:0082 VZ83 NT | No MR | Gigapower LLC CATV Com at 22'-9": Attach. Gigapower LLC Fiber Optic Com at 22'-9": Attach | 41.4201 | -75.6144 | APP_306552
P:0052 | 023 | 58596N46379 | MR Resolved | Low Power: Secondary at 24'-5". Secondary at 24'-5": Install ground rod and bond neutral to ground. Gigapower LLC Fiber Optic Com at 21'-5": Attach. Bond to ground wire | 41.42 | -75.6131 | APP_306552
P:0051 | 024 | 58601N46387 | MR Resolved | Low Power: Street_light at 19'-9". Pole Top: Replace 35' class 5 pole with 45' class 3 pole. Primary at 26'-6": Raise 114" to 36'-0". Primary at 26'-3": Raise 117" to 36'-0". Secondary at 23'-5": Raise 37" to 26'-6". Gigapower LLC Fiber Optic Com at 22'-0": Attach. Dunmore Boro, Lackawanna Co. Street Light at 21'-6": Raise 39" to 24'-9", Transfer to new pole at 23'-0". Dunmore Boro, Lackawanna Co. Drip Loop at 21'-2": Raise 39" to 24'-5", Transfer to new pole at 24'-5". North Penn Long Distance Corporation Fiber Optic Com at 17'-3": Raise 45" to 21'-0", Transfer to new pole at 21'-0". Comcast - Duryea CATV Com at 16'-2": Raise 46" to 20'-0", Transfer to new pole at 20'-0". Verizon Pennsylvania Inc. Telco Com at 14'-8": Raise 52" to 19'-0", Transfer to new pole at 19'-0". Verizon Pennsylvania Inc. Telco Com at 13'-11": Raise 49" to 18'-0", Transfer to new pole at 18'-0" | 41.4202 | -75.613 | APP_306552
P:0050 | 025 | 58607N46397 | MR Resolved | Low Power: Cabinet at 13'-5". Pole Top: Replace 35' class 5 pole with 45' class 3 pole. Primary at 28'-1": Raise 117" to 37'-10". Primary at 27'-11": Raise 117" to 37'-8". PPL Company Cutout Arrestor at 25'-11": Raise 108" to 34'-11". PPL Company Transformer at 23'-5": Raise 102" to 31'-11". Secondary at 22'-3": Raise 57" to 27'-0". Gigapower LLC Fiber Optic Com at 22'-0": Attach. Comcast - Duryea Riser at 21'-6": Extend 60" to 26'-6", Transfer to new pole at 25'-6". PPL Company Drip Loop at 21'-4": Raise 95" to 29'-3". North Penn Long Distance Corporation Fiber Optic Com at 17'-11": Raise 37" to 21'-0", Transfer to new pole at 21'-0". Comcast - Duryea CATV Com at 16'-11": Raise 37" to 20'-0", Transfer to new pole at 20'-0". Verizon Pennsylvania Inc. Telco Com at 15'-3": Raise 45" to 19'-0", Transfer to new pole at 19'-0". Verizon Pennsylvania Inc. Telco Com at 14'-5": Raise 43" to 18'-0", Transfer to new pole at 18'-0". Comcast - Duryea Cabinet at 13'-5": Raise 19" to 15'-0", Transfer to new pole at 15'-0" | 41.4205 | -75.6127 | APP_306552
P:0049 | 026 | 58612N46404 | MR Resolved | Low Power: Street_light at 20'-1". Pole Top: Replace 35' class 5 pole with 45' class 3 pole. Primary at 28'-3": Raise 116" to 37'-11". Primary at 27'-10": Raise 116" to 37'-6". Secondary at 23'-5": Raise 37" to 26'-6". Secondary at 23'-0": Raise 36" to 26'-0". Gigapower LLC Fiber Optic Com at 22'-0": Attach. Dunmore Boro, Lackawanna Co. Street Light at 21'-9": Raise 35" to 24'-8", Transfer to new pole at 23'-0". Dunmore Boro, Lackawanna Co. Drip Loop at 20'-11": Raise 35" to 23'-10", Transfer to new pole at 23'-10". North Penn Long Distance Corporation Fiber Optic Com at 19'-2": Raise 22" to 21'-0", Transfer to new pole at 21'-0". Comcast - Duryea CATV Com at 18'-2": Raise 22" to 20'-0", Transfer to new pole at 20'-0". Verizon Pennsylvania Inc. Telco Com at 16'-3": Raise 33" to 19'-0", Transfer to new pole at 19'-0". Verizon Pennsylvania Inc. Telco Com at 15'-6": Raise 30" to 18'-0", Transfer to new pole at 18'-0" | 41.4207 | -75.6126 | APP_306552
P:0048 | 027 | 58618N46415 | MR Resolved | Low Power: Drip_loop at 23'-9". North Penn Long Distance Corporation Fiber Optic Com at 20'-11": Lower 12" to 19'-11". Gigapower LLC Fiber Optic Com at 20'-11": Attach. Bond to ground wire. Comcast - Duryea CATV Com at 19'-11": Lower 15" to 18'-8" | 41.421 | -75.6123 | APP_306552
P:0088 | 028 | 58579N46413 | MR Resolved | Low Power: Street_light at 20'-2". Gigapower LLC CATV Com at 19'-8": Attach. North Penn Long Distance Corporation Fiber Optic Com at 19'-1": Lower 5" to 18'-8". Comcast - Duryea CATV Com at 18'-1": Lower 5" to 17'-8" | 41.4209 | -75.6136 | APP_306552
P:0087 | 030 | 58574N46403 | No MR | Low Power: Drip_loop at 22'-10". Gigapower LLC CATV Com at 19'-7": Attach | 41.4207 | -75.6139 | APP_306552
P:0086 | 031 | 58568N46393 | MR Resolved | Low Power: Secondary at 22'-4". Pole Top: Replace 35' class 4 pole with 35' class 3 pole. PPL Company Down Guy at 26'-7": Raise 24" to 28'-7". Secondary at 22'-4": Raise 26" to 24'-6". Gigapower LLC CATV Com at 21'-0": Attach. North Penn Long Distance Corporation Fiber Optic Com at 18'-0": Raise 24" to 20'-0", Transfer to new pole at 20'-0". Comcast - Duryea CATV Com at 17'-0": Raise 24" to 19'-0", Transfer to new pole at 19'-0". Verizon Pennsylvania Inc. Telco Com at 16'-3": Raise 21" to 18'-0", Transfer to new pole at 18'-0". Power Guy at 14'-5": Raise 13" to 15'-6". PPL Company Sidewalk Brace at 11'-10": Lower 10" to 11'-0" | 41.4204 | -75.6141 | APP_306552
P:0089 | 029 | 58586N46424 | MR Resolved | Low Power: Secondary at 25'-10". Service at 26'-0": Raise 18" to 27'-6". Secondary at 25'-10": Raise 18" to 27'-4". Gigapower LLC CATV Com at 23'-8": Attach | 41.4212 | -75.6134 | APP_306552
P:0079 | 032 | 58558N46384 | MR Resolved | Low Power: Street_light at 21'-11". Gigapower LLC Fiber Optic Com at 21'-0": Attach. Gigapower LLC Fiber Optic Com at 21'-0": Attach. North Penn Long Distance Corporation Fiber Optic Com at 21'-0": Lower 12" to 20'-0". North Penn Long Distance Corporation Telco Com at 21'-0": Lower 12" to 20'-0". Comcast - Duryea CATV Com at 20'-0": Lower 12" to 19'-0". Comcast - Duryea CATV Com at 20'-0": Lower 12" to 19'-0" | 41.4201 | -75.6145 | APP_306552
P:0080 | 033 | 58551N46388 | MR Resolved | Low Power: Drip_loop at 23'-7". North Penn Long Distance Corporation Fiber Optic Com at 21'-0": Lower 12" to 20'-0". Gigapower LLC Fiber Optic Com at 21'-0": Attach. Bond to ground wire. Comcast - Duryea CATV Com at 20'-0": Lower 12" to 19'-0". Verizon Pennsylvania Inc. Telco Com at 18'-8": Lower 8" to 18'-0". Verizon Pennsylvania Inc. Guy at 18'-8": Lower 8" to 18'-0" | 41.4202 | -75.6147 | APP_306552
P:0081 | 034 | P:0081 81 NT1 | MR Resolved | Low Power: Secondary at 26'-0". Gigapower LLC Fiber Optic Com at 23'-4": Attach. Bond to ground wire. Gigapower LLC Down Guy at 23'-4": Attach. Place on existing anchor rod with 14' lead at 303° and attach 6.6M (1/4" EHS) (7/0) guy. Gigapower LLC Fiber Optic Com at 23'-0": Attach. Bond to ground wire. Verizon Pennsylvania Inc. Down Guy at 20'-0": Transfer Verizon Pennsylvania Inc. Down Guy from anchor at 14' lead at 303° to the new Gigapower LLC anchor at 8' lead. Verizon Pennsylvania Inc. Guy at 20'-0": Transfer to new pole at 20'-0" | 41.4204 | -75.615 | APP_306552
P:0039 | 035 | 58576N46451 | MR Resolved | Low Power: Secondary at 27'-2". Gigapower LLC Fiber Optic Com at 22'-10": Attach. Gigapower LLC Down Guy at 22'-10": Attach. Place on existing anchor rod with 14' lead at 33° and attach 6.6M (1/4" EHS) (7/0) guy. Verizon Pennsylvania Inc. Down Guy at 18'-7": Transfer Verizon Pennsylvania Inc. Down Guy from anchor at 14' lead at 33° to the new Verizon Pennsylvania Inc. anchor at 8' lead | 41.422 | -75.6138 | APP_306552
P:0038 | 036 | 58569N46440 | MR Resolved | Low Power: Drip_loop at 23'-0". North Penn Long Distance Corporation Fiber Optic Com at 22'-4": Lower 12" to 21'-4". Gigapower LLC Fiber Optic Com at 22'-4": Attach. Comcast - Duryea CATV Com at 21'-4": Lower 12" to 20'-4" | 41.4216 | -75.6141 | APP_306552
P:0063 | 037 | 58560N46427 | MR Resolved | Low Power: Street_light at 19'-5". PPL Company Riser at 21'-7": Extend 6" to 22'-1". Gigapower LLC Fiber Optic Com at 18'-9": Attach. North Penn Long Distance Corporation Fiber Optic Com at 18'-9": Lower 12" to 17'-9". Comcast - Duryea CATV Com at 17'-9": Lower 12" to 16'-9" | 41.4213 | -75.6144 | APP_306552
P:0062 | 038 | 58553N46416 | No MR | Low Power: Drip_loop at 23'-11". Gigapower LLC Fiber Optic Com at 20'-7": Attach | 41.421 | -75.6147 | APP_306552
P:0061 | 039 | 58549N46409 | MR Resolved | Low Power: Street_light at 20'-8". Dunmore Boro, Lackawanna Co. Street Light at 22'-4": Raise 12" to 23'-4". Dunmore Boro, Lackawanna Co. Drip Loop at 21'-10": Raise 12" to 22'-10". Gigapower LLC Fiber Optic Com at 21'-2": Attach. Gigapower LLC Fiber Optic Com at 21'-2": Attach. Gigapower LLC Down Guy at 21'-2": Attach. Place on replaced PPL Company anchor rod with 15' lead at 122° and attach 6.6M (1/4" EHS) (7/0) guy. North Penn Long Distance Corporation Fiber Optic Com at 20'-10": Lower 8" to 20'-2". North Penn Long Distance Corporation Fiber Optic Com at 20'-10": Lower 8" to 20'-2". North Penn Long Distance Corporation Down Guy at 20'-10": Lower 8" to 20'-2". Comcast - Duryea CATV Com at 19'-10": Lower 10" to 19'-0". Comcast - Duryea CATV Com at 19'-10": Lower 10" to 19'-0" | 41.4208 | -75.6148 | APP_306552
P:0064 | 040 | 58545N46404 | No MR | Low Power: Secondary at 26'-4". Gigapower LLC Fiber Optic Com at 21'-7": Attach. Gigapower LLC Guy at 21'-7": Attach | 41.4207 | -75.6149 | APP_306552
P:0094 | 041 | 58543N46405 | No MR | Gigapower LLC Guy at 17'-10": Attach | 41.4207 | -75.615 | APP_306552
P:0065 | 042 | 58540N46395 | MR Resolved | Low Power: Drip_loop at 23'-8". Secondary at 26'-9": Raise 18" to 28'-3". Secondary at 26'-9": Raise 18" to 28'-3". Secondary at 26'-4": Raise 18" to 27'-10". Dunmore Boro, Lackawanna Co. Drip Loop at 23'-8": Raise 4" to 24'-0". Gigapower LLC Fiber Optic Com at 23'-0": Attach. Gigapower LLC Fiber Optic Com at 23'-0": Attach | 41.4204 | -75.6151 | APP_306552
P:0066 | 043 | 58533N46384 | MR Resolved | Low Power: Drip_loop at 25'-3". Gigapower LLC Fiber Optic Com at 21'-7": Attach. Bond to ground wire. North Penn Long Distance Corporation Fiber Optic Com at 21'-3": Lower 8" to 20'-7". Comcast - Duryea CATV Com at 20'-3": Lower 11" to 19'-4" | 41.4201 | -75.6154 | APP_306552
P:0067 | 044 | 58525N46372 | MR Resolved | Low Power: Street_light at 21'-11". Secondary at 28'-7": Raise 12" to 29'-7". Dunmore Boro, Lackawanna Co. Street Light at 23'-11": Raise 12" to 24'-11". Dunmore Boro, Lackawanna Co. Drip Loop at 23'-1": Raise 12" to 24'-1". North Penn Long Distance Corporation Fiber Optic Com at 22'-4": Lower 12" to 21'-4". North Penn Long Distance Corporation Fiber Optic Com at 22'-4": Lower 12" to 21'-4". North Penn Long Distance Corporation Down Guy at 22'-4": Lower 12" to 21'-4". Gigapower LLC Fiber Optic Com at 22'-4": Attach. Gigapower LLC Fiber Optic Com at 22'-4": Attach. Gigapower LLC Down Guy at 22'-4": Attach. Place on replaced Gigapower LLC anchor rod with 16' lead at 127° and attach 10M (3/8" UG) (7/0) guy. Power Guy at 21'-9": Lower 11" to 20'-10". Comcast - Duryea CATV Com at 21'-4": Lower 12" to 20'-4". Comcast - Duryea Strand at 21'-4": Lower 12" to 20'-4" | 41.4199 | -75.6156 | APP_306552
P:0070 | 045 | 58523N46374 | MR Resolved | Low Power: Secondary at 26'-7". Gigapower LLC Fiber Optic Com at 21'-11": Attach. Gigapower LLC Down Guy at 21'-11": Attach. Place on replaced Gigapower LLC anchor rod with 18' lead at 204° and attach 6.6M (1/4" EHS) (7/0) guy. North Penn Long Distance Corporation Down Guy at 20'-11": Transfer North Penn Long Distance Corporation Down Guy from anchor at 18' lead at 204° to the replaced Gigapower LLC anchor at 18' lead. Verizon Pennsylvania Inc. Down Guy at 18'-1": Transfer Verizon Pennsylvania Inc. Down Guy from anchor at 18' lead at 204° to the replaced Gigapower LLC anchor at 18' lead | 41.4199 | -75.6157 | APP_306552
P:0068 | 046 | 58519N46362 | No MR | Low Power: Secondary at 28'-11". Gigapower LLC Fiber Optic Com at 22'-7": Attach | 41.4196 | -75.6159 | APP_306552
P:0069 | 047 | 58513N46352 | MR Resolved | Low Power: Street_light at 23'-4". Secondary at 26'-5": Raise 12" to 27'-5". Dunmore Boro, Lackawanna Co. Street Light at 25'-0": Raise 12" to 26'-0". Dunmore Boro, Lackawanna Co. Drip Loop at 24'-1": Raise 12" to 25'-1". Gigapower LLC Fiber Optic Com at 23'-9": Attach | 41.4193 | -75.6161 | APP_306552
P:0013 | 048 | 58509N46341 | MR Resolved | Low Power: Street_light at 23'-10". Dunmore Boro, Lackawanna Co. Street Light at 26'-0": Raise 6" to 26'-6", Ground Bracket. Dunmore Boro, Lackawanna Co. Drip Loop at 25'-2": Raise 6" to 25'-8". Gigapower LLC Fiber Optic Com at 23'-9": Attach. Gigapower LLC Fiber Optic Com at 23'-9": Attach. Gigapower LLC Guy at 23'-9": Attach. North Penn Long Distance Corporation Fiber Optic Com at 23'-3": Lower 6" to 22'-9" | 41.419 | -75.6163 | APP_306552
P:0072 | 073 | 58554N46304 | MR Resolved | PPL Company Down Guy at 23'-8": Attach and install new anchor. Place on new PPL Company anchor rod with 15' lead at 274° and attach 10M (3/8" UG) (7/0) guy. Gigapower LLC Down Guy at 22'-8": Attach and install new anchor. Place on new PPL Company anchor rod with 15' lead at 274° and attach 6.6M (1/4" EHS) (7/0) guy. Gigapower LLC Guy at 22'-8": Attach | 41.4179 | -75.6146 | APP_306552
P:0101 | 049 | 58508N46336 | MR Resolved | Low Power: Drip_loop at 23'-7". PPL Company Drip Loop at 23'-7": Raise 12" to 24'-7". Gigapower LLC Down Guy at 20'-6": Attach. Place on existing anchor rod with 17' lead at 178° and attach 6.6M (1/4" EHS) (7/0) guy. Gigapower LLC Guy at 20'-6": Attach | 41.4189 | -75.6163 | APP_306552
P:0012 | 050 | 58519N46338 | MR Resolved | Low Power: Drip_loop at 24'-10". Zayo Bandwidth Fiber Optic Com at 22'-10": Lower 20" to 21'-2". CTSI, LLC, Dba Frontier Communications Telco Com at 22'-3": Lower 27" to 20'-0". Gigapower LLC Fiber Optic Com at 22'-3": Attach. Bond to ground wire. Bond to ground wire. Comcast - Duryea CATV Com at 21'-2": Lower 26" to 19'-0" | 41.4189 | -75.6159 | APP_306552
P:0011 | 052 | 58533N46337 | MR Resolved | Low Power: Drip_loop at 23'-10". Dunmore Boro, Lackawanna Co. Street Light at 27'-7": Raise 18" to 29'-1". Gigapower LLC Fiber Optic Com at 24'-4": Attach. Dunmore Boro, Lackawanna Co. Drip Loop at 23'-10": Raise 18" to 25'-4". Comcast - Duryea Down Guy at 21'-9": Attach and install new anchor. Place on new North Penn Long Distance Corporation anchor rod with 6' lead at 20° and attach 10M (3/8" UG) (7/0) guy. Dunmore Boro, Lackawanna Co. Traffic Cable at 21'-8": Remove. PPL to remove un-used alarm cable. North Penn Long Distance Corporation Down Guy at 20'-11": Attach and install new anchor. Place on new North Penn Long Distance Corporation anchor rod with 6' lead at 20° and attach 6.6M (1/4" EHS) (7/0) guy. North Penn Long Distance Corporation Sidewalk Brace at 10'-0": Attach | 41.4189 | -75.6154 | APP_306552
P:0010 | 053 | 58543N46336 | MR Resolved | Low Power: Drip_loop at 22'-10". Dunmore Boro, Lackawanna Co. Street Light at 23'-9": Raise 6" to 24'-3", Ground Bracket. Dunmore Boro, Lackawanna Co. Drip Loop at 22'-10": Raise 6" to 23'-4". Gigapower LLC Fiber Optic Com at 22'-2": Attach. Dunmore Boro, Lackawanna Co. Traffic Cable at 21'-5": Remove. PPL to remove unused attachment | 41.4188 | -75.615 | APP_306552
P:0009 | 054 | 58551N46334 | MR Resolved | Low Power: Drip_loop at 23'-1". Dunmore Boro, Lackawanna Co. Street Light at 23'-5": Ground Bracket. Dunmore Boro, Lackawanna Co. Drip Loop at 23'-1": Guard drip loop. Dunmore Boro, Lackawanna Co. Traffic Cable at 22'-11": Remove. PPL to remove unused attachment. Gigapower LLC Fiber Optic Com at 22'-7": Attach. Zayo Bandwidth Fiber Optic Com at 22'-7": Lower 13" to 21'-6". CTSI, LLC, Dba Frontier Communications Telco Com at 21'-10": Lower 16" to 20'-6". Comcast - Duryea CATV Com at 20'-10": Lower 16" to 19'-6" | 41.4188 | -75.6147 | APP_306552
P:0001 | 055 | 58566N46331 | MR Resolved | Low Power: Drip_loop at 25'-7". Dunmore Boro, Lackawanna Co. Street Light at 25'-10": Ground Bracket. Gigapower LLC Fiber Optic Com at 23'-8": Attach. Gigapower LLC Fiber Optic Com at 23'-8": Attach. Gigapower LLC Guy at 23'-8": Attach. Dunmore Boro, Lackawanna Co. Traffic Cable at 21'-11": PPL to remove unused attachment | 41.4188 | -75.6142 | APP_306552
P:0100 | 056 | 58565N46328 | MR Resolved | Low Power: Drip_loop at 30'-9". Gigapower LLC Down Guy at 24'-3": Attach and install new anchor. Place on new Gigapower LLC anchor rod with 8' lead at 220° and attach 10M (3/8" UG) (7/0) guy. Gigapower LLC Guy at 24'-3": Attach. Gigapower LLC Sidewalk Brace at 16'-6": Attach | 41.4187 | -75.6143 | APP_306552
P:0037 | 057 | 58574N46342 | MR Resolved | Low Power: Secondary at 26'-7". Secondary at 26'-7": Raise 12" to 27'-7". Gigapower LLC Fiber Optic Com at 23'-2": Attach | 41.419 | -75.6139 | APP_306552
P:0054 | 058 | 58581N46354 | MR Resolved | Low Power: Street_light at 22'-4". North Penn Long Distance Corporation Fiber Optic Com at 21'-3": Lower 12" to 20'-3". Gigapower LLC Fiber Optic Com at 21'-3": Attach. Comcast - Duryea CATV Com at 20'-3": Lower 12" to 19'-3" | 41.4193 | -75.6137 | APP_306552
P:0078 | 059 | 58555N46380 | MR Resolved | Low Power: Secondary at 23'-2". North Penn Long Distance Corporation Down Guy at 19'-7": Attach. Place on existing anchor rod with 13' lead at 32° and attach 6.6M (1/4" EHS) (7/0) guy. Gigapower LLC Fiber Optic Com at 19'-7": Attach. Bond to ground wire | 41.42 | -75.6146 | APP_306552
P:0077 | 060 | 58549N46370 | No MR | Low Power: Secondary at 24'-1". Gigapower LLC Fiber Optic Com at 19'-5": Attach | 41.4198 | -75.6148 | APP_306552
P:0076 | 061 | 58543N46359 | MR Resolved | Low Power: Drip_loop at 21'-9". Gigapower LLC Fiber Optic Com at 20'-8": Attach. Bond to ground wire | 41.4195 | -75.615 | APP_306552
P:0044 | 062 | 58578N46326 | MR Resolved | Low Power: Drip_loop at 27'-2". Dunmore Boro, Lackawanna Co. Street Light at 28'-6": Raise 11" to 29'-5", Ground Bracket. Dunmore Boro, Lackawanna Co. Drip Loop at 27'-2": Raise 10" to 28'-0". Gigapower LLC Strand at 27'-0": Attach. Gigapower LLC Guy at 27'-0": Attach. North Penn Long Distance Corporation Fiber Optic Com at 26'-0": Transfer to new pole at 26'-0". North Penn Long Distance Corporation Guy at 26'-0": Transfer to new pole at 26'-0". North Penn Long Distance Corporation Guy at 26'-0": Transfer to new pole at 26'-0". Zayo Bandwidth Fiber Optic Com at 25'-0": Transfer to new pole at 25'-0". Comcast - Duryea CATV Com at 24'-0": Transfer to new pole at 24'-0". Comcast - Duryea Guy at 24'-0": Transfer to new pole at 24'-0". CTSI, LLC, Dba Frontier Communications Telco Com at 23'-1": Transfer to new pole at 23'-0". Verizon Pennsylvania Inc. Strand at 22'-0": Transfer to new pole at 22'-0". Verizon Pennsylvania Inc. Fiber Optic Com at 21'-0": Transfer to new pole at 21'-0". Verizon Pennsylvania Inc. Strand at 20'-0": Transfer to new pole at 20'-0". Verizon Pennsylvania Inc. Guy at 20'-0": Transfer to new pole at 20'-0". Verizon Pennsylvania Inc. Strand at 19'-0": Transfer to new pole at 19'-0". Verizon Pennsylvania Inc. Strand at 18'-0": Transfer to new pole at 18'-0". Verizon Pennsylvania Inc. Guy at 18'-0": Transfer to new pole at 18'-0" | 41.4186 | -75.6138 | APP_306552
P:0036 | 063 | 58582N46334 | MR Resolved | Gigapower LLC Down Guy at 19'-9": Attach. Place on existing anchor rod with 9' lead at 51° and attach 10M (3/8" UG) (7/0) guy. Gigapower LLC Guy at 19'-9": Attach. North Penn Long Distance Corporation Down Guy at 19'-3": Upgrade existing down guy strand to a 10M (3/8" UG) (7/0) strand size. Verizon Pennsylvania Inc. Down Guy at 17'-7": Attach and install new anchor. Place on new Gigapower LLC anchor rod with 4' lead at 49° and attach 10M (3/8" UG) (7/0) guy. Verizon Pennsylvania Inc. Down Guy at 16'-8": Transfer Verizon Pennsylvania Inc. Down Guy from anchor at 9' lead at 51° to the new Gigapower LLC anchor at 4' lead | 41.4188 | -75.6135 | APP_306552
P:0003 | 064 | 58586N46323 | MR Resolved | Low Power: Drip_loop at 27'-6". North Penn Long Distance Corporation Fiber Optic Com at 25'-0": Lower 12" to 24'-0", Transfer to new pole at 24'-0". Gigapower LLC Fiber Optic Com at 25'-0": Attach. Bond to ground wire. Zayo Bandwidth Fiber Optic Com at 24'-0": Lower 12" to 23'-0", Transfer to new pole at 23'-0". CTSI, LLC, Dba Frontier Communications Telco Com at 23'-0": Lower 12" to 22'-0", Transfer to new pole at 22'-0". Comcast - Duryea CATV Com at 22'-0": Lower 12" to 21'-0", Transfer to new pole at 21'-0". Verizon Pennsylvania Inc. Telco Com at 21'-0": Lower 12" to 20'-0", Transfer to new pole at 20'-0". Verizon Pennsylvania Inc. Telco Com at 21'-0": Lower 12" to 20'-0", Transfer to new pole at 20'-0". Verizon Pennsylvania Inc. Telco Com at 21'-0": Lower 12" to 20'-0", Transfer to new pole at 20'-0". Verizon Pennsylvania Inc. Telco Com at 21'-0": Lower 12" to 20'-0", Transfer to new pole at 20'-0" | 41.4185 | -75.6135 | APP_306552
P:0004 | 065 | 58593N46320 | MR Resolved | Low Power: Secondary at 24'-4". Secondary at 24'-4": Raise 18" to 25'-10". Gigapower LLC Fiber Optic Com at 22'-3": Attach | 41.4184 | -75.6133 | APP_306552
P:0005 | 066 | 58597N46318 | MR Resolved | Low Power: Street_light at 22'-2". Dunmore Boro, Lackawanna Co. Street Light at 24'-2": Raise 18" to 25'-8", Ground Bracket. Dunmore Boro, Lackawanna Co. Drip Loop at 23'-7": Raise 18" to 25'-1". Gigapower LLC Fiber Optic Com at 23'-2": Attach | 41.4184 | -75.6131 | APP_306552
P:0006 | 067 | 58609N46315 | MR Resolved | Low Power: Drip_loop at 25'-3". Dunmore Boro, Lackawanna Co. Street Light at 25'-5": Ground Bracket. Gigapower LLC Fiber Optic Com at 23'-4": Attach. Bond to ground wire | 41.4183 | -75.6127 | APP_306552
P:0007 | 068 | 58620N46313 | No MR | Low Power: Neutral at 25'-4". Gigapower LLC Fiber Optic Com at 21'-9": Attach | 41.4182 | -75.6123 | APP_306552
P:0027 | 069 | 58573N46318 | No MR | Low Power: Secondary at 26'-3". Gigapower LLC Fiber Optic Com at 21'-10": Attach | 41.4184 | -75.614 | APP_306552
P:0026 | 070 | 58568N46309 | No MR | Low Power: Secondary at 26'-1". Gigapower LLC Fiber Optic Com at 20'-0": Attach | 41.4181 | -75.6142 | APP_306552
P:0029 | 071 | 58563N46301 | MR Resolved | Low Power: Drip_loop at 21'-8". Dunmore Boro, Lackawanna Co. Street Light at 22'-4": Raise 12" to 23'-4", Ground Bracket. Dunmore Boro, Lackawanna Co. Drip Loop at 21'-8": Raise 10" to 22'-6". Gigapower LLC Fiber Optic Com at 21'-3": Attach. Bond to ground wire. Gigapower LLC Guy at 21'-3": Attach. Gigapower LLC Fiber Optic Com at 20'-11": Attach. Gigapower LLC Guy at 20'-11": Attach | 41.4179 | -75.6143 | APP_306552
P:0035 | 072 | 58562N46299 | MR Resolved | Low Power: Service at 13'-8". Pole Top: Replace 30' class 5 pole with 35' class 3 pole. Secondary at 24'-8": Raise 22" to 26'-6". Power Guy at 23'-6": Lower 6" to 23'-0". Service at 23'-3": Raise 27" to 25'-6". Comcast - Duryea Guy at 22'-6": Lower 12" to 21'-6", Transfer to new pole at 21'-6". Gigapower LLC Guy at 22'-0": Attach. Verizon Pennsylvania Inc. Guy at 21'-8": Lower 8" to 21'-0", Transfer to new pole at 21'-0". PPL Company Riser at 14'-5": Extend 139" to 26'-0". Service at 13'-8": Raise 142" to 25'-6" | 41.4178 | -75.6144 | APP_306552
P:0030 | 074 | 58574N46294 | MR Resolved | Low Power: Drip_loop at 27'-0". Gigapower LLC Fiber Optic Com at 20'-0": Attach. Comcast - Duryea CATV Com at 19'-4": Transfer to new pole at 19'-4". Comcast - Duryea CATV Com at 19'-0": Transfer to new pole at 19'-0". Verizon Pennsylvania Inc. Fiber Optic Com at 18'-4": Transfer to new pole at 18'-4". Verizon Pennsylvania Inc. Fiber Optic Com at 18'-0": Transfer to new pole at 18'-0" | 41.4177 | -75.614 | APP_306552
P:0031 | 075 | 58581N46289 | MR Resolved | Low Power: Riser at 23'-5". Gigapower LLC Fiber Optic Com at 20'-1": Attach. Unknown Unknown Type at 19'-7": PPL to remove unknown attachment | 41.4176 | -75.6137 | APP_306552
P:0014 | 076 | 58497N46342 | MR Resolved | Low Power: Drip_loop at 28'-0". Dunmore Boro, Lackawanna Co. Street Light at 28'-2": Ground Bracket. Gigapower LLC Fiber Optic Com at 25'-10": Attach | 41.419 | -75.6167 | APP_306552
P:0075 | 077 | 58536N46347 | MR Resolved | Low Power: Service at 24'-9". Secondary at 25'-3": Raise 18" to 26'-9". Service at 24'-11": Raise 20" to 26'-7". Power Guy at 24'-10": Raise 18" to 26'-4". Service at 24'-9": Raise 22" to 26'-7". Service at 24'-9": Raise 22" to 26'-7". Gigapower LLC Fiber Optic Com at 22'-2": Attach. Gigapower LLC Guy at 22'-2": Attach | 41.4192 | -75.6153 | APP_306552
P:0091 | 078 | 58534N46345 | No MR | Gigapower LLC Guy at 18'-4": Attach. Gigapower LLC Guy at 18'-4": Attach | 41.4191 | -75.6154 | APP_306552